## CE2&UA Cutover 12.11
| CRQ |  | ID | Task description | Responsible | START CET | END CET | Duration | Predecesor | Status | Comments |  | Status | Comments
| CHG0064107 |  |  | GOLIVE: 12th of November, start downtime: 2100 CET
|  |  |  | CHG0064107 |  | Estimates
|  |  |  | Database backup and recovery estimations from Ishan | DB's |  | Restore | Estimated by
[5 empty] | Old | New
|  |  |  | ODS DB CE2 and Ukraine | webecep | webeuap
|  |  |  | LINX DB | gmcgcep | gmcgfip
|  |  |  | LINX DB Ukraine | gmcgeep | gmcguap
|  |  |  | chrptcep | chrptcep
|  |  |  | leadsep(EE,LA,LT) | leadsep
|  |  |  | PG(EE,FI,LT, LV) | PG
In scope DB's: ODS, GOMAC, HDS
Out of scope DB: Leads?
|  | 1 |  | Pre-cutover checks / activities
|  | 1.1 |  | Maintanance page (content to be confirmed and who prepare, when) | Gurvinder Singh/ Svitlana Melnyk/ Janis |  |  |  |  | complete
|  | 1.2 |  | Agree prompt on IVR/CTI | Laszlo Somogyi | [8 empty] | Is IVR directly linked with ODS dB and do we need to stop sale orders or sales
|  | 1.3 |  | GO/NOGO for cutover with Business | Oksana | [8 empty] | got GO from UA.
|  | 1.4 |  | CRQ for Outage () | Gurvinder Singh |  |  |  |  | complete
|  | 1.5 |  | QAP signoff | Attilla Domokos |  |  |  |  | complete
|  | 1.6 |  | UAT signoff (new PROD) | Mihaly / Attila |  |  |  |  | complete
|  | 1.7 |  | outage + communication | Gurvinder Singh |  |  |  |  | In Progress
|  | 1.8 |  | Global Privacy approval | Anastacia Izmaylova |  |  |  |  | complete
|  | 1.9 |  | Project Risks approval | Michał Ziółkowski |  |  |  |  | complete
|  | 1.10 |  | SOX approval | Karolina Przybysz |  |  |  |  | complete
|  | 1.11 |  | Service Team approval (communication) | Jarosław Żurawski |  |  |  |  | complete
|  | 1.12 |  | Firewall port communication from celerity to MQ in Amsterdam/Corby for concorde applictaion | Gwidon |  |  |  |  | complete | Need to check with Gwidon if all ports are opened Source: Concorde Database(172.26.180.80) target amslxgi3pmq1.dc.avon.net (10.160.140.20) port 1414 cbylxwebepmq1.uk.avon.com (172.20.29.99 ) port 1414
|  | 2 |  | PREPARATIONS / CHECKS / SCRIPTING
|  | 2.1 |  | Preparation activities
|  | 2.1.1 |  | Check all dblinks in webeuap, gmcgfip, gmcguap and confirm if they need to undergo any changes. | Ivan Ferrer (webe) (chrptcep), Gergo (gmc) |  |  |  |  | completed | Gergo completed his part;
|  | 2.1.2 |  | Check whether we have got any changes in DDLs we would need to run during cutover (check with Michal for EXT) | Ivan Ferror |  |  |  |  | completed | Michal to provide script to Ivan Ferror
|  | 2.2 |  | Maintenence pages / prompts / communication
|  | 2.2.1 |  | Check / prepare maintenance page for MAS | Imre Balla |  |  |  |  | Complete | Netscalar will set up
|  | 2.2.2 |  | Check / prepare maintenance page for MAO | Carol |  |  |  |  | Complete | Available with MW team.
|  | 2.2.3 |  | Check / prepare maintenance page for Avon Grow (EE,FI,LA, LT) | Jackson / Owen Wan |  |  |  |  | Complete | mail sent for status update
|  | 2.2.4 |  | Check / prepare maintenance page for IMB (for all CE2 & UA markets) | Alexandru |  |  |  |  | Complete | mail sent for status update
|  | 2.3 |  | Prepare communication for business | Gurvinder Singh |  |  |  |  | In progress | mail sent for status update
|  | 2.4 |  | Create new release of service-registry-for-ipaas-infra-tf | Zoltan |  |  |  |  | In progress | To be performed on 12th Morning
|  | 2.5 |  | Scripts preparation | [5 empty] | Complete
|  | 2.5.1 |  | Level 0 backup scripts | HCL DB team - ishan |  |  |  |  | Complete
|  | 2.5.2 |  | WEBECEP (ODS db) clone and upgrade from production | HCL DB team - ishan |  |  |  |  | Complete
|  | 2.5.3 |  | gmcgcep | HCL DB team - ishan |  |  |  |  | Complete
|  | 2.5.4 |  | scripts to install db objects (external tables for ETL users) | Ivan Ferror |  |  |  |  | Complete
|  | 2.5.5 |  | review prod deployment process GI3, AGS classic | Maykon |  |  |  |  | Complete
|  | 2.5.6 |  | setup new deployment script on new env - AGS, GI3 | Maykon / Eduardo |  |  |  |  | Complete
|  | 2.6 |  | New PROD - Environment readiness (incl. Smoke tests) | [5 empty] | Complete
|  | 2.6.1 |  | autosys jobs checked, confirmed, turned on in controlled way | Michal |  |  |  |  | Complete
|  | 2.6.2 |  | Put webe jobs on HOLD before trial cutover | Michal / Miguel |  |  |  |  | Complete
|  | 2.6.3 |  | NAS mounts / NAS folders | Maykon |  |  |  |  | Complete
|  | 2.6.4 |  | webserver config (httpd) | Maykon |  |  |  |  | Complete
|  | 2.6.5 |  | websphere preparations | Maykon |  |  |  |  | Complete
|  | 2.6.6 |  | application deployment | Maykon |  |  |  |  | Complete
|  | 2.6.7 |  | symbolic links creation | Maykon |  |  |  |  | Complete
|  | 2.6.8 |  | teamsite preparation | Anton |  |  |  |  | Complete
|  | 2.6.9 |  | enable config for new prod deployment | Anton |  |  |  |  | Complete
|  | 2.6.10 |  | Check CCA properties in AGS during the login | Anandhi |  |  |  |  | Complete
|  | 2.6.11 |  | content refresh scripts | Michal |  |  |  |  | Complete
|  | 2.6.12 |  | perl modules instalation | Maykon |  |  |  |  | Complete
|  | 2.6.13 |  | perl scripts validation | Michal |  |  |  |  | Complete
|  | 2.6.14 |  | shell scripts validation | Michal |  |  |  |  | Complete
|  | 2.6.15 |  | autosys setup to new batch servers | Miguel |  |  |  |  | Complete
|  | 2.6.16 |  | import GI3 & AGS3 & AGS classic new certificates to the applications that invokes it | Maykon |  |  |  |  | Complete
|  | 2.6.17 |  | MAO - AGS3 cert | Maykon |  |  |  |  | Complete
|  | 2.6.18 |  | import external weservice certificates to the new AGS and AGS3 env | Maykon |  |  |  |  | Complete
|  | 2.6.19 |  | import external weservice certificates to the new Gi3 | Maykon |  |  |  |  | Complete
|  | 2.6.20 |  | submit the request for external URLs to be added to FireWall | Maykon |  |  |  |  | Complete
|  | 2.7 |  | AGS3 / MAO verification
|  | 2.7.1 |  | AGS3 - deploy of newest version on prod (on QA already deployed) | Andras Gaal |  |  |  |  | In progress
|  | 2.8 |  | Another preparations
|  | 2.8.1 |  | hostfiles | Maykon |  |  |  |  | Complete
|  | 2.8.2 |  | prepare new AKAMAI for AGS classic & AGS3 | Maykon |  |  |  |  | Complete
|  | 2.8.3 |  | create new NetScalers for AGS classic and AGS3 | HCL Network Team |  |  |  |  | Complete
|  | 2.8.4 |  | validate new servers backup - all prod non-data servers | Vineet / backup team |  |  |  |  | Complete | Need to validate
|  | 2.8.5 |  | Open connectivity from MAS PROD env (AWS) to AGS classic endpoint! | Imre Sz |  |  |  |  | Complete
|  | 2.8.6 |  | Check connectivity from MAS PROD env (AWS) to AGS classic endpoint! | Imre Balla |  |  |  |  | Complete
|  | 2.8.7 |  | Resync NAS folders GI3 | Maykon |  |  |  |  | Complete
|  | 2.8.7 |  | Deploy GI3 property files | Anandhi |  |  |  |  | Complete
|  | 2.8.9 |  | Reduce DNS TTL 5 mins | Amit |  |  |  |  | Complete
|  | 2.8.10 |  | Validate DNS TTL | Amit |  |  |  |  | Complete
|  | 2.8.11 |  | SMTP servers to be installed to batch and app servers - Check if it was done | Maykon |  |  |  |  | Complete
|  | 2.8.12 |  | level 0 backup - 3 dbs Friday | Ishan |  |  |  |  | In progress | To be conducted on 11th Nov.
|  | 2.8.13 |  | we need to clear down old archive logs so arch dest does not get full | Ishan |  |  |  |  | In progress | During cutover
|  | 2.8.14 |  | hostfiles - provide for new users (same as for testing) | Anandhi |  |  |  |  | Complete
|  | 2.8.15 |  | Kristine, will raise ticket to update ags3 url on fuse end | kristine.tansengespiritu@avon.com, gwe.service.delivery@avon.com |  |  |  |  | Complete | https://fuseuniversal.atlassian.net/servicedesk/customer/portal/1/FCS-29874?created=true
|  | 2.8.16 |  | Setup Gi3 maint page (AMST) | Martket Content Team / Gurvinder / MW team | 2021-11-12 | 2021-11-12 |  |  | Complete | Gurvinder to confirm with market content team
|  | 2.8.17 |  | ODS - CDW | Michal |  |  |  |  | In progress | Need to check with Satyam
|  | 2.8.17.1 |  | MAS eligability feed change | Michal |  |  |  |  | In progress
|  | 2.8.18 | CUTOVER - make sure AMIT is here + Vitaly on call at least | Change LINX endpoint for AGS 3 (MAO) AGP service. | Middleware |  |  | 15 mins |  |  | https://avonproducts.atlassian.net/wiki/spaces/MAW/pages/3173221196/2021-11-12+20.00+CEST+-+AGP+config+change
|  | 3 |  | CUTOVER
|  | 3.1 |  | Initial activities |  |  |  |  | 1-2.8
|  | 3.1.1 |  | Maintenance Pages set up |  | 2021-11-12 21:00 | 2021-11-12 22:00 | 60 mins
|  | 3.1.1.1 |  | GI3 Maintenance pages set up | MW Team |  |  | 30 mins |  | Not Started
|  | 3.1.1.1.1 |  | Setup Gi3 maint page (AMST) | MW Team |  |  |  |  | Not Started
|  | 3.1.1.1.2 |  | Making the DNS changes - all CE2 & UA markets | Amit |  |  | 30 mins |  | Not Started
|  | 3.1.1.1.3 |  | Akmai changes - all CE2 & UA markets | Maykon |  |  | 30mins |  | Not Started
|  | 3.1.1.1.4 |  | Validate Gi3 maint page | Anandhi |  |  | 15 mins |  | Not Started
|  | 3.1.1.2 |  | MAO Maintenance pages set up | [5 empty] | Not Started
ENT-MIDDLEWARE WAS |  | 3.1.1.2.1 |  | MAO - Setup the maint page EE,FI,LV,LT Markets | MW Team |  |  | 30 mins |  | Not Started
ENT-MIDDLEWARE WAS |  | 3.1.1.2.2 |  | MAO - Setup the maint page (for few markets)-Ukraine Markets | Terraform Team - Kapender / Nirdesh - to be confirmed from Vineet |  |  | 30mins |  | Not Started |  |  |  |  | 0
|  | 3.1.1.2.3 |  | MAO - validate MAO connectivity | Tatiana Darkshevich |  |  |  |  | Not Started | To confirm with Carol |  |  |  | 0
|  |  |  | Enable maintenance page for OSA | Oleksandr Ovdiy |  |  | 20 mins |  | Not Started
|  | 3.1.1.3 |  | Avon On - disable connections 5 markets | Sai |  |  | 60 mins |  | Not Started |  |  |  |  | 0
|  | 3.1.1.3.1 |  | Disable single sign on to place orders | Sai |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.1.1.3.2 |  | Disable single sign on to history of orders / returns | Sai |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.1.1.3.3 |  | Disable signe sign on to cutomer orders | Sai |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.1.1.3.4 |  | Disable make a payment from dashboard, from my account page, decision landing page, menu | Sai |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.1.1.3.5 |  | Disable edit phone number and email from my profile page | Sai |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.1.1.3.6 |  | Disable single sign on to Avon Office | Sai |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.1.1.3.7 |  | Disable single sign on to Avon Connect | Sai |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.1.1.3.8 |  | Disable IMB dashboard | Sai |  |  |  |  | Not Started |  |  |  |  | 0
i |  | 3.1.1.3.9 |  | Disable IMB ordering | Sai |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.1.1.3.10 |  | Disable single sign on for Avon Grow | Sai |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.1.1.3.11 |  | Disable self appointment from login page | Sai |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.1.1.3.12 |  | Potentially include task related to digital | Sai |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.1.1.4 |  | MAS Maintenance pages set up - five markets | Imre Balla |  |  | 15 mins |  | Not Started |  |  |  |  | 0
|  | 3.1.1.5 |  | Avon Grow Maintenance pages set up - ( EE, LA, LT,FI) | Jackson/Owen |  |  | 10 mins |  | Not Started |  |  |  |  | 0
|  | 3.1.1.6 |  | FUSE - 5 markets | kristine.tansengespiritu@avon.com, gwe.service.delivery@avon.com |  |  |  |  | Not Started | KristineOpened the ticket for the changes |  |  |  | 0
|  | 3.1.1.7 |  | IMB Maintenance pages set up - 5 Markets | Alexandru |  |  | 30 mins |  | Not Started |  |  |  |  | 0
|  | 3.1.1.8 |  | Leads Maintenance pages set up - 3 markets - EE, LA, LT | Imre Balla |  |  | 30mins |  | Not Started |  |  |  |  | 0
|  | 3.1.1.9 |  | Payment gateway build in AMS env. | Maykon/ MW team |  |  | 10 mins |  | Not Started | https://amslxgi3pdmgr1.dc.avon.net:14001/ibm/console/login.do?action=secure |  |  |  | 0
|  | 3.1.1.10 |  | PG ripple start | Maykon /MW team |  |  | 10 mins |  | Not Started | https://amslxgi3pdmgr1.dc.avon.net:14001/ibm/console/login.do?action=secure
|  | 3.1.1.11 |  | Switch Germany eInvoices to https URL | Anandhi |  |  |  |  | Not Started
|  | 3.1.1.12 |  | Ripple start Germany GI3 cluster in AMS | MW team/ Ankur |  |  |  |  | Not Started
|  | 3.2 |  | PREPARATIONS BEFORE APPS STOP |  | 2021-11-12 22:00 | 2021-11-12 23:00 | 60 mins |  | Not Started |  |  |  |  | 0
| Aries Systems | 3.2.1 |  | Turn off order processing | Attila Fiel |  |  | 30 mins. |  | Not Started |  |  |  |  | 0
|  | 3.2.2 |  | Check whether all the invoices are printed | Attila Fiel |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.2.3 |  | Disable jobs in ARIES responsible for data refresh | Attila G |  |  | 15 mins. |  | Not Started |  |  |  |  | 0
| Ukraine | 3.2.4 |  | Turn off order processing | Eugene |  |  | 10 mins |  | Not Started |  |  |  |  | 0
|  | 3.2.5 |  | Check whether all the invoices are printed | Albina Kazantseva |  |  | 10 mins |  | Not Started | Business Team need to be involved |  |  |  | 0
|  | 3.2.6 |  | Disable jobs in Ukraine responsible for data refresh | Eugene |  |  | 10 mins |  | Not Started |  |  |  |  | 0
|  | 3.2.7 |  | Disable Oracle jobs and stop UA Batcher sessions | Eugene |  |  | 15 mins |  | Not Started |  |  |  |  | 0
|  | 3.2.8 |  | Stop Replication for MAO HDS | Eugene |  |  | 5 mins |  | Not Started |  |  |  |  | 0
|  | 3.2.9 |  | Change NOEL to dummy URL | Laszlo Gecse/BDP/HU <Laszlo.Gecse@avon.com> |  |  | 30 mins |  | Not Started |  |  |  |  | 0
|  | 3.2.10 |  | Update NOEL interface control table in CORBY WEBECEP | Michal |  |  | 5 mins |  | Not Started |  |  |  |  | 0
|  | 3.2.11 |  | Change LINX endpoint for AGS 3 (MAO) AGP service. | Middleware |  |  |  | Need to move to prepration section. Zoli to provide details | Not Started | https://avonproducts.atlassian.net/wiki/spaces/MAW/pages/3173221196/2021-11-12+20.00+CEST+-+AGP+config+change |  |  |  | 0
|  |  |  | Enable OSA maintenance page | [5 empty] | Not Started |  |  |  |  | 0
|  | 3.3 |  | APPLICATIONS STOP |  | 2021-11-12 23:00 | 2021-11-13 23:40 | 30 mins | 3.1, 3.2 | Not Started |  |  |  |  | 0
|  | 3.3.1 |  | migrate AKAMAI CE to AMS | Maykon |  |  | 10 mins |  | Not Started |  |  |  |  | 0
|  | 3.3.2 |  | switch DNS to point to AKAMAI | Amit Kumar / HCL NW team |  |  | 30 mins |  | Not Started |  |  |  |  | 0
|  | 3.3.3 |  | validate this application einvoice.eu.avon.com | Michal |  |  | 30 mins |  | Not Started
|  | 3.3.4 |  | stop old gi3 jvm - Estonia, finland, Latvia, Lithuania, ukraine & UA markets & UA) | MW Team |  |  | 5 mins |  | Not Started | Nordics and UA https://cbylxwebewdm1.uk.avon.com:14001/ibm/console |  |  |  | 0
ESO-OMS-ADMIN |  | 3.3.5 |  | Stop all GOMAC / Estonia, finland, Latvia, Lithuania, ukraine & UA markets | OMS Admins / Gergo |  |  | 10 mins | '3.1.1.9 | Not Started |  |  |  |  | 0
|  | 3.3.6 |  | Stop MAO Email sending Boomi process | Tibor Kepecs |  |  | 5 mins |  | Not Started | Stop MAO Email sending Boomi process. Remove EE,LV,LT,FI,UA from PROD APAC -> env variables -> Dynamic Process Properties -> DPP_MAOEmail_marketList |  |  |  | 0
|  | 3.3.7 |  | Stop ARIES SMS sending | Attila G |  |  | 5 mins |  | Not Started |  |  |  |  | 0
|  | 3.3.8 |  | Stop SMS Gateway/SMS Ordering Job | Pavel |  |  | 5 mins |  | Not Started |  |  |  |  | 0
|  | 3.3.9 |  | Gather the datacounts in webecep | Ivan Ferror |  |  | 10 mins |  | Not Started |  |  |  |  | 0
|  | 3.4 |  | DB ACTIVITIES |  | 2021-11-12 23:40 | 2021-11-13 07:40 | 480 mins (8 hours) | 3.3 | Not Started | 3.4.6.4 is not in duration, could be done independently |  |  |  | 0
|  | 3.4.1 |  | DATABASE REFRESH | Ishan |  |  | 8 hours |  | Not Started |  |  |  |  | 0
ENT-ORACLE |  | 3.4.1.1 |  | Drop DBs Clear archive filesystem | HCL DB team - ishan | 2021-11-12 23:40 | 2021-11-12 23:50 | 10 mins |  | Not Started |  |  |  |  | 0
ENT-ORACLE |  | 3.4.1.2 |  | restore database from level 0 backup | HCL DB team - ishan | 2021-11-12 23:50 | 13/11/202102:20:00 | 150 mins | 3.4.1.1 | Not Started |  |  |  |  | 0
ENT-ORACLE |  | 3.4.1.2.1 |  | webecep | HCL DB team - ishan/Nakul |  |  | 150 mins |  | Not Started |  |  |  |  | 0
|  | 3.4.1.2.2 |  | gmcgcep - CE2 | HCL DB team - ishan/Nakul |  |  |  |  | Not Started | Ishan to provide time ? |  |  |  | 0
|  | 3.4.1.2.3 |  | gmcgeep- Ukraine | HCL DB team - ishan/Nakul |  |  |  |  | Not Started |  |  |  |  | 0
ENT-ORACLE |  | 3.4.1.3 |  | level 1 backup + archive backup + copy | HCL DB team - ishan | 13/11/202102:20:00 | 13/11/202103:35:00 | 150 mins | 3.4.1.2 | Not Started | Can be done in parallel with others |  |  |  | 0
ENT-ORACLE |  | 3.4.1.3.1 |  | webecep | HCL DB team - ishan/Nakul |  |  | 120 mins |  | Not Started | Duration of longest recover (recovery done in parallel) |  |  |  | 0
ENT-ORACLE |  | 3.4.1.3.2 |  | gmcgcep - CE2 | HCL DB team - ishan/Nakul |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.4.1.3.3 |  | gmcgeep- Ukraine | HCL DB team - ishan/Nakul |  |  |  |  | Not Started | Ishan to provide time |  |  |  | 0
ENT-ORACLE |  | 3.4.1.3.3 |  | Copy backup - all three | HCL DB team - ishan/Nakul |  |  | 30 mins |  | Not Started |  |  |  |  | 0
ENT-ORACLE |  | 3.4.1.4 |  | recover databases | HCL DB team - ishan | 2021-11-13 03:35 | 2021-11-13 04:20 | 90 mins | 3.4.1.3 | Not Started |  |  |  |  | 0
ENT-ORACLE |  | 3.4.1.4.1 |  | webecep | Ishan, Nakul |  |  | 20 mins |  | Not Started |  |  |  |  | 0
ENT-ORACLE |  | 3.4.1.4.2 |  | gmcgcep - CE2 | Ishan, Nakul |  |  | 90 mins |  | Not Started |  |  |  |  | 0
|  |  |  | gmcgeep- Ukraine | Ishan, Nakul |  |  | 30mins |  | Not Started |  |  |  |  | 0
|  | 3.4.1.5 |  | upgrade databases | Ishan, Nakul | 2021-11-13 04:20 | 2021-11-13 05:35 | 80 mins | 3.4.1.4 | Not Started |  |  |  |  | 0
|  | 3.4.1.5.1 |  | webeuap | Ishan, Nakul |  |  | 40 mins |  | Not Started |  |  |  |  | 0
|  | 3.4.1.5.2 |  | Gomac - gmcgfip (CE2) | Ishan, Nakul |  |  | 80 mins |  | Not Started |  |  |  |  | 0
|  | 3.4.1.5.3 |  | Gomac - gmcguap (UA) | Ishan, Nakul |  |  | 40 mins |  | Not Started |  |  |  |  | 0
|  | 3.4.1.6 |  | Refresh Data | Ishan, Nakul | 2021-11-12 23:50 | 2021-11-13 01:05 | 115 mins | 3.4.1.1 | Not Started | export - copy - import - will be performed parallelly with other DB activities |  |  |  | 0
|  | 3.4.1.6.1 |  | chrptcep( EE,FI,LV,LT,UA) | Ishan, Nakul |  |  | 115 mins |  | Not Started |  |  |  |  | 0
|  | 3.4.1.6.2 |  | gather data counts for new webeuap | Ivan Ferror |  |  | 10 mins |  | Not Started |  |  |  |  | 0
[10 empty] | Not Started |  |  |  |  | 0
|  | 3.4.1.7 |  | Drop Partitions | Ishan, Nakul | 2021-11-13 05:35 | 2021-11-13 06:20 | 45 mins | 3.4.1.5.1 | Not Started |  |  |  |  | 0
|  | 3.4.1.7.1 |  | webeuap ( all except CE2 markets) | Ishan, Nakul |  |  | 40 mins |  | Not Started |  |  |  |  | 0
|  | 3.4.1.7.2 |  | Run scripts / create DB links - sent via email by Gergo | Ishan, Nakul |  |  | 10mins |  | Not Started |  |  |  |  | 0
[10 empty] | Not Started |  |  |  |  | 0
|  | 3.4.1.8 |  | Verify the partitions and data counts | Ivan Ferror | 2021-11-13 06:20 | 2021-11-13 06:30 | 10 mins | 3.4.1.5.1 | Not Started |  |  |  |  | 0
|  | 3.4.1.8.1 |  | truncate table monitor.session_login; webeuap | Ishan |  |  | 6 mins |  | Not Started |  |  |  |  | 0
[10 empty] | Not Started |  |  |  |  | 0
|  | 3.4.2 |  | SANITY CHECK - each db owner should check if db is accessible | db owners | 2021-11-13 06:30 | 2021-11-13 06:35 | 5 mins |  | Not Started |  |  |  |  | 0
|  | 3.4.2.1 |  | webeuap | Ivan Ferror |  |  | 5 mins | 3.4.1.7.2 | Not Started |  |  |  |  | 0
|  | 3.4.2.2 |  | chrptcep (EE,FI,LV,LT,UA) | Tatiana Darkshevich |  |  | 5 mins | 3.4.1.6.1 | Not Started |  |  |  |  | 0
|  | 3.4.3 |  | DML scripts execution (autojob details) - restoring backuped autosys jobs | Michal | 2021-11-13 06:35 | 2021-11-13 06:40 | 5 mins |  | Not Started |  |  |  |  | 0
|  | 3.4.3.1 |  | we need to clear down old archive logs so arch dest does not get full | Ishan |  |  | 10 mins |  | Not Started |  |  |  |  | 0
|  | 3.4.4 |  | Put DB's in restricted mode (only for DBA's) | Ishan |  |  | 5 mins |  | Not Started |  |  |  |  | 0
|  | 3.4.4.1 |  | webecep | Ishan |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.4.4.2 |  | gmcgcep - CE2 | Ishan |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.4.4.3 |  | gmcgeep- Ukraine | Ishan |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.4.4.4 |  | Test websphere data sources | MW team |  |  | 15 mins |  | Not Started | https://amslxgi3pdmgr1.dc.avon.net:14001/ibm/console |  |  |  | 0
|  | 3.4.4.5 |  | Run jobs to recalculate statistics - webeuap | Ishan |  |  | 120 mins | 3.4.1.7.2 | Not Started | doesn’t need to finish before moving on |  |  |  | 0
|  | 3.5 |  | APPLICATION ACTIVITIES TO BE DONE DURING DB ACTIVITIES |  | 2021-11-12 23:40 | 2021-11-13 00:40 | 120 mins | 3.3 | Not Started |  |  |  |  | 0
|  | 3.5.1 |  | APPLICATION ACTIVITIES TO BE DONE DURING DB ACTIVITIES | MW |  |  | 45 mins |  | Not Started | https://cbylxwebewdm1.uk.avon.com:15001/ibm/console following are the DataSources in WAS 8.5 for the CE2 markets: Maykon will provide list of datasource |  |  |  | 0
DCO-SPO-SERVER-SUPT-BR |  | 3.5.2 |  | change all CE2 markets to the new ip on /etc/hosts on dlslxpsmsgwap1 | Maykon |  |  | 10 mins |  | Not Started |  |  |  |  | 0
|  | 3.5.3 |  | increase AGS3 servers vcpu from 4 to 8 | Linux team/ Maykon/MW team |  |  | 120 mins |  | Not Started | amslxags3pap1-4
|  | 3.5.4 |  | Adjust SMGT/UK/IT?ES = report users | Maykon/Linux team |  |  | 60 mins |  | Not Started | CHG0062875
|  | 3.5.5 |  | validate SMG/UK/It/ES batch rports | Ivan/Michal |  |  | 30 mins |  | Not Started | CHG0062875
|  | 3.5.6 | 3.5.2.2 | MQ host name changes ARIES - | Attila G/ Tibor Obreczan |  |  | 5 mins |  | Not Started | Need to confirm |  |  |  | 0
|  | 3.5.7 |  | MQ host name changes Concord - | Eugene |  |  | 5 mins |  | Not Started |  |  |  |  | 0
|  | 3.5.8 |  | Syncronize PDF reports for Gi3 | Maykon |  |  | 30 mins |  | Not Started | https://avonproducts.atlassian.net/wiki/spaces/GI3/pages/3093004431/PDF+documents+and+their+handling |  |  |  | 0
|  | 3.5.9 |  | Change AGS Classis SMS endpoint - ARIES | Tibor Obreczan |  |  | 5 mins |  | Not Started |  |  |  |  | 0
|  | 3.5.10 |  | Change LINX endpoint for AGS AGP service. | Shankar/Raja |  |  | 5 mins |  | Not Started |  |  |  |  | 0
|  | 3.5.11 |  | iframe policy to be adjusted on GI3 web servers | Maykon |  |  | 30 mins |  | Not Started |  |  |  |  | 0
|  | 3.5.12 |  | PDF reports endpoints in ARIES | Tibor Obreczan |  |  | 5 mins |  | Not Started | Not needed to be checked with Aries team (Tibor) |  |  |  | 0
|  | 3.5.13 |  | PDF reports endpoints in Concord (validated by Eugene) | Eugene |  |  | 20 mins |  | Not Started | Validate if this server will be migrated to AMsterdan at this time. cbymsrptprd.eu.avonet.net: under discussion - Eugene will check if it can be moved from FTP |  |  |  | 0
|  | 3.5.14 |  | Point ARIES PG interface to new MQ ( EE,FI,LV,LT) | Attila / Tibor |  |  | 10 min |  | Not Started |  |  |  |  | 0
|  | 3.5.15 |  | AWS changes by HCL DevOps | HCL DevOPs (Nirdesh / Rakesh / Kapender) / Zoli |  |  | 30 min | Maintenance page up | Not Started | Deploy master branch of service-registry-for-ipaas-infra-tf to PROD via Jenkins (https://jenkins.devops-prod.aws.avon.com/job/API GW/job/API GW Prod/job/Service Registry for iPaaS/job/Service Registry infra/) Add new entries in Secrets Manager (AWS account #121642321945). Copy serviceReg/WEBECEP with its secret values to serviceReg/WEBEUAP |  |  |  | 0
[10 empty] | Not Started |  |  |  |  | 0
created |  | 3.6 |  | SWITCH TO NEW DATABASES |  | 2021-11-13 07:40 | 2021-11-13 08:50 | 70 mins | 3.4 | Not Started |  |  |  |  | 0
|  | 3.6.1 |  | supportal new db configuration | Michal |  |  | 10 mins |  | Not Started | What are predecessors ? |  |  |  | 0
|  | 3.6.2 |  | ezBrochure change point CE2 markets to new DB (XML config change) | Michal |  |  |  |  | Not Started | What are predecessors ? |  |  |  | 0
|  | 3.6.3 |  | CRM - redirect to new LINX DB - only for( EE,FI,LV,LT,UA) | Citrix team / Tibor |  |  | 70 mins | 3.4.1.5.2 | Not Started | CRM is connected with Aries and Linx |  |  |  | 0
[10 empty] | Not Started |  |  |  |  | 0
|  | 3.7 |  | Setup connectivity between future PROD and satellite applications |  | 2021-11-13 07:50 | 2021-11-13 08:50 | 60 mins | 3.4 | Not Started |  |  |  |  | 0
|  | 3.7.1 |  | Avon Grow - Change Avon Grow AGS service enpoint to new one (details) | Jackson |  |  | 60 mins | 3.5.4; 3.4 | Not Started |  |  |  |  | 0
|  | 3.7.2 |  | MAS - Switch to new AGS URLs (detailed plan by Imre Balla) | Imre Balla / Akos Tamas |  |  | 60 mins |  | Not Started | Completed |  |  |  | 0
|  | 3.7.3 |  | MAO | [5 empty] | Not Started |  |  |  |  | 0
|  | 3.7.3.1 |  | AGS3 domain update : myavon-ws-eu-ams.prod.avon.com | Tamas Szeremy |  |  | 10 mins |  | Not Started | Need URL confirmation from Tamas |  |  |  | 0
|  | 3.7.3.2 |  | Validation of MAO connectivity | Tanaya |  |  | 20 mins |  | Not Started |  |  |  |  | 0
|  | 3.7.4 |  | IMB - Switch to new AGS URLs | alexandru |  |  | 30 mins |  | Not Started | New AGS URL in Amsterdam: https://ags-ws-eu-ams.prod.avon.com/agws/ |  |  |  | 0
|  | 3.7.5 |  | Avon On -Switch to new AGS URLs | Sai |  |  | 45 mins |  | Not Started | New AGS URL in Amsterdam: https://ags-ws-eu-ams.prod.avon.com/agws/ |  |  |  | 0
|  | 3.7.6 |  | IVR - Laszlo will redirect to the production URL for all the 17 CE Aries markets. | Laszlo.Somogyi@maintel.co.uk |  |  | 15 mins |  | Not Started | Need endpoints from Laszlo. |  |  |  | 0
|  | 3.7.7 |  |  | Attila / Tibor |  |  | 5 mins |  | Not Started | New AGS URL in Amsterdam: https://ags-ws-eu-ams.prod.avon.com/agws/ |  |  |  | 0
|  | 3.7.8 |  | FUSE | gwe.service.delivery@avon.com, Kristine Tan Seng-Espiritu |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.7.8.1 |  | local digital team update AGS3 fuse sso in magnolia (MAO) | Digital Team |  |  |  |  | Not Started | to be checked with the markets |  |  |  | 0
|  | 3.7.8.2 |  | local digital team update AGS3 fuse sso in GI3 | Anandhi |  |  | 30 mins |  | Not Started |  |  |  |  | 0
|  | 3.7.8.3 |  | local digital team update AGS3 fuse sso in MAS | Imre Balla / Akos Tamas |  |  | 60 mins |  | Not Started | Covered in 3.8.2 |  |  |  | 0
|  | 3.7.9 |  | Change Data Integration Services to New ODS - can be done after the DB activities, Rain to be informed | rain.zhen@avon.com |  |  | 60 mins |  | Not Started | Independent Task Avon Data Integration <avondataintegration@isoftstone.com> Avon Data Service Team <avondataservicesteam@isoftstone.com> from cbylxwebeeupdbc1.uk.avon.com:1521:webecep to amslxgi3eupdb2.dc.avon.net:1521:webeuap |  |  |  | 0
|  | 3.7.10 |  | Eloqua config needs to be updated to use the proper AGS/AGS3 domain | Dragos Ene |  |  | 30 mins |  | Not Started | Have to confirm with Dragos | myavon-ws-eu-dls.prod.avon.com |  |  | 0
|  | 3.7.11 |  | SMS Gateway - Change AGS classic endpoints | Pavel |  |  | 5 mins |  | Not Started |  |  |  |  | 0
|  | 3.7.12 |  | PRP - CE2 | Doru Dumitrescu/ |  |  | 30 mins |  | Not Started |  |  |  |  | 0
|  | 3.7.13 |  | ARIES/Concord | [5 empty] | Not Started |  |  |  |  | 0
|  | 3.7.13.1 |  | Change dblink/config for Tibi's engine - Nordics | Gabor Pachert |  |  | 5 mins |  | Not Started | also linx and HDS DB Links |  |  |  | 0
|  | 3.7.13.2 |  | Change dblink/config for Tibi's engine - UA | HCL DB team/ Eugene |  |  | 5 mins |  | Not Started | DB link connection will remain intact but TNS name will change. also linx and HDS DB Links |  |  |  | 0
|  | 3.7.14 |  | Teamsite -Change TeamSite config | Anton |  |  | 60 mins |  | Not Started | can be done anytime after cutover starts |  |  |  | 0
|  | 3.7.15 |  | Payment Gateway - ( EE,FI,LV,LT) (Not required In UA) NEW | Priyanka / Raja |  |  | 10 mins |  | Not Started | Card details required for QA env.- Sandra |  |  |  | 0
|  | 3.7.16 |  | Leads application - 3 markets - EE, LA, LT Setup new AGS URL for authenticate users | Imre Balla |  |  | 60 mins |  | Not Started | Need to confirm with Imre Bala |  |  |  | 0
|  | 3.7.17 |  | Point concorde back to new MQ QMGR | Eugene |  |  | 15 mins |  | Not Started |  |  |  |  | 0
|  | 3.7.18 |  | Change OSA application end points | Oleksandr Ovdiy |  |  |  |  | Not Started
[10 empty] | Not Started |  |  |  |  | 0
|  | 3.8 |  | ADDITIONAL CHECKS/CONNECTIVITY |  | 2021-11-13 07:50 | 2021-11-13 08:20 | 30 mins | 3.7 | Not Started |  |  |  |  | 0
ENT-AUTOSYS |  | 3.8.1 |  | DML scripts execution (autojob details) | Michal |  |  | 10 mins |  | Not Started | Duplicate job |  |  |  | 0
|  | 3.8.2 |  | Run selected autosys jobs manually from cmd line and verify they are not failing | Michal |  |  | 20 mins |  | Not Started |  |  |  |  | 0
created |  | 3.9' |  | STARTING APPS |  | 2021-11-13 08:50 | 2021-11-13 09:50 | 60 mins |  | Not Started |  |  |  |  | 0
|  | 3.9.1 |  | Run scripts / start GOMAC | Gergo |  |  | 60 mins | '3.4.4.5 | Not Started | Required for 2 environments |  |  |  | 0
|  | 3.9.2 |  | Start MAO Email sending Boomi process | Tibor Kepecs |  |  | 5 mins |  | Not Started | Start MAO Email sending Boomi process. Add EE,LV,LT,FI,UA to PROD APAC -> env variables -> Dynamic Process Properties -> DPP_MAOEmail_marketList |  |  |  | 0
|  | 3.9.3 |  | start GI3 apps (CE2 markets) (Amst) | MW Team |  |  | 60 mins | '3.7.27 | Not Started | https://amslxgi3pdmgr1.dc.avon.net:14001/ibm/console |  |  |  | 0
|  | 3.9.4 |  | ripple restart AGS3 MyAvon Cluster | MW |  |  |  | '3.7.27 | Not Started | https://amslxags3pdmgr1.dc.avon.net:14001/ibm/console |  |  |  | 0
|  | 3.9.5 |  | ripple restart AGS-AMS Cluster | MW |  |  |  | '3.7.27 | Not Started | https://amslxgi3pdmgr1.dc.avon.net:14001/ibm/console |  |  |  | 0
|  | 3.9.6 |  | Enable Aries jobs | Gabor Pachert |  |  | 5 mins |  | Not Started |  |  |  |  | 0
|  | 3.9.7 |  | Enable Concord jobs | Eugene |  |  | 5 mins |  | Not Started |  |  |  |  | 0
On 28.09 we finished here |  | 3.10 |  | SMOKE TESTS |  | 2021-11-13 09:50 | 2021-11-13 12:50 | 180 mins | 3.9 | Not Started |  |  |  |  | 0
|  | 3.10.1 |  | smoke tests MAO including reports | Tanaya |  |  | 120 mins |  | Not Started |  |  |  |  | 0
|  | 3.10.2 |  | smoke tests GI3 | Anandhi |  |  | 180 mins |  | Not Started |  |  |  |  | 0
|  | 3.10.3 |  | Smoke test AGS3 | Zoli to inform |  |  | 15 mins |  | Not Started |  |  |  |  | 0
|  | 3.10.4 |  | smoke tests AGS classic | Shankar |  |  | 30 mins |  | Not Started |  |  |  |  | 0
|  | 3.10.5 |  | smoke tests LINX connectivity | Gergo |  |  | 30 mins |  | Not Started |  |  |  |  | 0
|  | 3.10.6 |  | RRM connectivity to Linx | Gabor Pachert |  |  | 30 mins | '3.7.3 | Not Started |  |  |  |  | 0
|  | 3.10.7 |  | Smoke test Payment Gateway (partial) | Priyanka G |  |  | 30 mins |  | Not Started |  |  |  |  | 0
|  | 3.10.8 |  | validate this application einvoice.eu.avon.com | Michal |  |  | 30 mins |  | Not Started
created |  | 3.11 |  | Enable autosys jobs |  | 2021-11-13 07:40 | 2021-11-13 08:15 | 35 mins | 3.4 | Not Started | doesn’t need to wait for smoke tests |  |  |  | 0
ENT-AUTOSYS |  | 3.11.1 |  | Put new Dallas/Corby autosys jobs back online. | Miguel |  |  | 15 mins |  | Not Started |  |  |  |  | 0
ENT-AUTOSYS |  | 3.11.2 |  | Check for any job failures - AUTO_JOB_DETL, autsys log files | Michal |  |  | 15 mins |  | Not Started |  |  |  |  | 0
|  | 3.11.3 |  | we need to clear down old archive logs so arch dest does not get full | Ishan |  |  | 5 mins |  | Not Started | Moved to DBA section |  |  |  | 0
|  | 3.12 |  | BUSINESS TESTING (with maintenance pages on) |  | 2021-11-13 12:50 | 2021-11-13 18:50 | 6 hours | 3.11 | Not Started | Business testors can work in shifts if possible |  |  |  | 0
|  | 3.12.1 |  | IVR- Change AGS3 endpoints | Laszlo.Somogyi@maintel.co.uk |  |  | 5 mins |  | Not Started | Independent task
|  | 3.12.2 |  | IVR - Testing | Sandra |  |  | 15 mins |  | Not Started
|  | 3.13. |  | GI3 | [5 empty] | Not Started |  |  |  |  | 0
|  | 3.13.1 |  | Estonia | Janis Gureckis |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.13.1.1 |  | Finland | Renars Paukstello |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.13.1.2 |  | Latvia | Renars Paukstello |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.13.1.3 |  | Lithuania | Janis Gureckis |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.13.1.4 |  | Ukraine | Oksana |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.13.2 |  | MAS | [5 empty] | Not Started |  |  |  |  | 0
|  | 3.13.2.1 |  | Estonia | Janis Gureckis |  |  |  |  | Not Started |  | Yes |  |  | 0
|  | 3.13.2.2 |  | Finland | Renars Paukstello |  |  |  |  | Not Started |  | Yes |  |  | 0
|  | 3.13.2.3 |  | Latvia | Renars Paukstello |  |  |  |  | Not Started |  | Yes |  |  | 0
|  | 3.13.2.4 |  | Lithuania | Janis Gureckis |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.13.2.5 |  | Ukraine | Oksana |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.13.3 |  | MAO | [5 empty] | Not Started |  |  |  |  | 0
|  | 3.13.3.1 |  | Estonia | Janis Gureckis |  |  |  |  | Not Started |  | Yes |  |  | 0
|  | 3.13.3.2 |  | Finland | Renars Paukstello |  |  |  |  | Not Started |  | Yes |  |  | 0
|  | 3.13.3.3 |  | Latvia | Renars Paukstello |  |  |  |  | Not Started |  | Yes |  |  | 0
|  | 3.13.3.4 |  | Lithuania | Janis Gureckis |  |  |  |  | Not Started |  | Yes |  |  | 0
|  | 3.13.3.5 |  | Ukraine | Oksana |  |  |  |  | Not Started |  | Yes |  |  | 0
|  | 3.13.6 |  | IMB NOT UNTIL MAINT PAGE LIFTED | [5 empty] | Not Started |  |  |  |  | 0
|  | 3.13.6.1 |  | Estonia | Janis Gureckis |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.13.6.2 |  | Finland | Renars Paukstello |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.13.6.3 |  | Latvia | Renars Paukstello |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.13.6.4 |  | Lithuania | Janis Gureckis |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.13.6.5 |  | Ukraine | Oksana |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.13.4 |  | Payment Gateway | [5 empty] | Not Started |  |  |  |  | 0
|  | 3.13.4.1 |  | Estonia | Janis Gureckis |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.13.4.2 |  | Finland | Renars Paukstello |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.13.4.3 |  | Latvia | Renars Paukstello |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.13.4.4 |  | Lithuania | Janis Gureckis |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.13.5 |  | FUSE (integration check) - maintenance pages activated | [5 empty] | Not Started |  |  |  |  | 0
|  | 3.13.5.1 |  | Estonia | Janis Gureckis |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.13.5.2 |  | Finland | Renars Paukstello |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.13.5.3 |  | Latvia | Renars Paukstello |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.13.5.4 |  | Lithuania | Janis Gureckis |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.13.5.5 |  | Ukraine | Oksana |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.13.6 |  | SMS ordering | [5 empty] | Not Started |  |  |  |  | 0
|  | 3.13.6.5 |  | Ukraine | Oksana |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.13.7 |  | Personal Recutement Pages - Nordics and UA | Doru Dumitrescu/ |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.13.8 |  | Bill Test Orders - | Markets |  |  | 60 mins |  | Not Started |  |  |  |  | 0
|  | 3.13.8.1 |  | Estonia | Attila Fiel |  |  |  |  | Not Started
|  | 3.13.8.2 |  | Finland | Attila Fiel |  |  |  |  | Not Started
|  | 3.13.8.3 |  | Finland | Attila Fiel |  |  |  |  | Not Started
|  | 3.13.8.4 |  | Lithuania | Attila Fiel |  |  |  |  | Not Started
|  | 3.13.8.5 |  | Ukraine | Albina Kazantseva |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.14 |  | GO / NO GO DECISION |  | 2021-11-13 18:50 | 2021-11-13 19:00 |  |  | Not Started |  |  |  |  | 0
[10 empty] | Not Started |  |  |  |  | 0
|  | 3.15 |  | LIFTING / Removal |  | 2021-11-13 19:00 | 2021-11-13 20:00 | 1 hours |  | Not Started |  |  |  |  | 0
|  |  |  | Remove maintenence pages | [5 empty] | Not Started |  |  |  |  | 0
|  | 3.15.1 |  | GI3 - remove main page | MW team |  |  | 20 mins |  | Not Started |  |  |  |  | 0
|  | 3.15.2 |  | MAO - remove maintenance page | [5 empty] | Not Started |  |  |  |  | 0
|  | 3.15.2.1 |  | MAO - remove maintenance page | MW team |  |  | 30 mins |  | Not Started |  |  |  |  | 0
|  | 3.15.2.2 |  | MAO - remove maintenance page | Terrafom team- Kapender |  |  | 30 mins |  | Not Started |  |  |  |  | 0
|  | 3.15.2.3 |  | Validation of removal of maintenance page | Tanaya |  |  | 5 mins |  | Not Started |  |  |  |  | 0
|  | 3.15.2 |  | MAS - remove maintenance page | Akos Tamas |  |  | 30 mins |  | Not Started |  |  |  |  | 0
|  | 3.15.3 |  | Avon Grow - remove maintenance page | jackson.yan@avon.com |  |  | 15 mins |  | Not Started |  |  |  |  | 0
|  | 3.15.4 |  | IMB - remove maintenance page | Alexandru |  |  | 30 mins |  | Not Started |  |  |  |  | 0
|  | 3.15.5 |  | Enable Avon On | [5 empty] | Not Started |  |  |  |  | 0
|  | 3.15.5.1 |  | Enable single sign on to place orders | Sai |  |  | 45 mins |  | Not Started |  |  |  |  | 0
|  | 3.15.5.2 |  | Enable single sign on to history of orders / returns | Sai |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.15.5.3 |  | Enable signe sign on to cutomer orders | Sai |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.15.5.4 |  | Enable make a payment from dashboard, from my account page, decision landing page, menu | Sai |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.15.5.5 |  | Enable edit phone number and email from my profile page | Sai |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.15.5.6 |  | Enable single sign on to Avon Office | Sai |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.15.5.7 |  | Enable single sign on to Avon Connect | Sai |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.15.5.8 |  | Enable IMB dashboard | Sai |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.15.5.9 |  | Enable IMB ordering | Sai |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.15.5.10 |  | Enable single sign on for Avon Grow | Sai |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.15.5.11 |  | Enable self appointment from login page | Sai |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.15.5.12 |  | Digital recruitment links - enable a from component | Sai |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.15.6 |  | FUSE - Avon Connect | Kristine Tan Seng-Espiritu gwe.service.delivery@avon.com |  |  |  |  | In progress | Ticket and time shared with fuse team |  |  |  | 0
|  | 3.15.7 |  | OSA Recruitmnet Pages - UA | Oksana |  |  | 15 mins |  | Not Started |  |  |  |  | 0
|  | 3.15.8 |  | Start SMS Gateway/SMS Ordering Job | Pavel |  |  | 5 mins |  | Not Started |  |  |  |  | 0
|  | 3.15.9 |  | NOEL -Change NOEL endpoint from Corby to Amsterdam - AGS3 | Laszlo G |  |  | 30 mins |  | Not Started |  |  |  |  | 0
|  | 3.15.10 |  | Disable maintenance page for OSA | Oleksandr Ovdiy |  |  | 20 mins |  | Not Started | Need to confirm about host files 134.65.161.38 ags-ws-eu-ams.prod.avon.com |  |  |  | 0
|  | 3.16 |  | Final Business Checks (after maintenance pages lifted) |  | 2021-11-13 20:00 | 2021-10-14 23:00 | 3 hours |  | Not Started |  |  |  |  | 0
|  | 3.16.1 |  | GI3 | [5 empty] | Not Started |  |  |  |  | 0
|  | 3.16.1.1 |  | Estonia | Janis Gureckis |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.16.1.2 |  | Finland | Renars Paukstello |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.16.1.3 |  | Latvia | Renars Paukstello |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.16.1.4 |  | Lithuania | Janis Gureckis |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.16.1.5 |  | Ukraine | Oksana |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.16.2 |  | MAS | [5 empty] | Not Started |  |  |  |  | 0
|  | 3.16.2.1 |  | Estonia | Janis Gureckis |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.16.2.2 |  | Finland | Renars Paukstello |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.16.2.3 |  | Latvia | Renars Paukstello |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.16.2.4 |  | Lithuania | Janis Gureckis |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.16.2.5 |  | Ukraine | Oksana |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.16.3 |  | MAO | [5 empty] | Not Started |  |  |  |  | 0
|  | 3.16.3.1 |  | Estonia | Janis Gureckis |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.16.3.2 |  | Finland | Renars Paukstello |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.16.3.3 |  | Latvia | Renars Paukstello |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.16.3.4 |  | Lithuania | Janis Gureckis |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.16.3.5 |  | Ukraine | Oksana |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.16.4 |  | AVON GROW -can be tested when maint page is lifted | [5 empty] | Not Started |  |  |  |  | 0
|  | 3.16.4.1 |  | Estonia | Janis Gureckis |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.16.4.2 |  | Finland | Renars Paukstello |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.16.4.3 |  | Latvia | Renars Paukstello |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.16.4.4 |  | Lithuania | Janis Gureckis |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.16.4.5 |  | Ukraine | Oksana |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.16.5 |  | Avon ON -can be tested when maint page is lifted | [5 empty] | Not Started |  |  |  |  | 0
|  | 3.16.5.1 |  | Estonia | Janis Gureckis |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.16.5.2 |  | Finland | Renars Paukstello |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.16.5.3 |  | Latvia | Renars Paukstello |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.16.5.4 |  | Lithuania | Janis Gureckis |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.16.5.5 |  | Ukraine | Oksana |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.16.6 |  | IMB - can be tested when maint page is lifted | [5 empty] | Not Started |  |  |  |  | 0
|  | 3.16.6.1 |  | Estonia | Janis Gureckis |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.16.6.2 |  | Finland | Renars Paukstello |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.16.6.3 |  | Latvia | Renars Paukstello |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.16.6.4 |  | Lithuania | Janis Gureckis |  |  |  |  | Not Started |  |  |  |  | 0
|  | 3.16.6.5 |  | Ukraine | Oksana |  |  |  |  | Not Started |  |  |  |  | 0
|  | 4 |  | END OF THE OUTAGE |  | 2021-11-13 23:00 | 2021-11-13 23:00 |  |  | Not Started |  |  |  |  | 0
|  | 5 |  | Mass Billing enablement | (Nordics)/ Albina Kazantseva(UA) |  |  | 30 mins |  | Not Started | LIT, LAT, EST, FIN |  |  |  | 0
|  | 5.1 |  | Estonia | Attila Fiel | 2021-11-13 23:00 | 2021-11-13 23:00 |  |  | Not Started
|  | 5.1 |  | Finland | Attila Fiel | 2021-11-13 23:00 | 2021-11-13 23:00 |  |  | Not Started
|  | 5.1 |  | Latvia | Attila Fiel | 2021-11-13 23:00 | 2021-11-13 23:00 |  |  | Not Started
|  | 5.1 |  | Lithuania | Attila Fiel | 2021-11-13 23:00 | 2021-11-13 23:00 |  |  | Not Started
|  | 5.1 |  | Ukraine | Albina Kazantseva | 2021-11-15 02:00 | 2021-11-15 02:00 |  |  | Not Started
|  | 6 |  | Post Outage | [5 empty] | Not Started |  |  |  |  | 0
[10 empty] | Not Started |  |  |  |  | 0
[10 empty] | Not Started |  |  |  |  | 0
[10 empty] | Not Started |  |  |  |  | 0
Note on L84: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Gwidon what's the approach for this. Will the list of users for admin-rights to this file will come from Project? If so then we need a task to collect those and HCL to execute it

## CE2 Trial Cutover 08.11
IMPORTANT NOTE for next streams:
| for CRQ we just need to contact TanMoy, no need to join CAB call (applies for DEV and QA) | [9 empty] | DATE : 08/11/2021 09:00 CET
Standard change created: https://avon.service-now.com/nav_to.do?uri=change_request.do?sys_id=68c3ba061be3b054e7253339cc4bcb6a
| 3 | TRIAL CUTOVER | [11 empty] | refresh database and smoke tests
CRQ |  | ID | Task description | Responsible |  | START CEST tz | END CEST tz | Actual Start time | Actual end time | Duration | Predecesor | Status | Comments
CHG0064260 |  | 0 | PREPARATIONS |  | 2021-11-08 | 1 day before trial cutover |  |  |  | (In Hrs.)
|  | 0.1 | CRQ CHG ... for testing and database refresh and application restart | Gurvinder Singh | [7 empty] | Complete
|  | 0.2 | We need to figure out what to do so that new PROD autosys jobs are not failing during the DB restore task. Also, once DB is restored, we need to ensure no jobs are running until data is scrambled. Assuming we are scrambling data actually… | Michal Elias | [7 empty] | Complete
|  | 0.3 | Collect list of jobs that need to be inactive | Michal Elias | [7 empty] | Complete
|  | 0.4 | Put autosys jobs on-hold | Michal Elias/Miguel Poma | [7 empty] | Complete
|  | 0.5 | Backup autosys jobs details and definitions | Michal Elias | [7 empty] | Complete
|  | 0.6 | Production Validation confirmed | Global QA team, UATs
|  | 0.7 | Level 0 Backups and copy - webecep gmcgcep leadsep (Serbia) webepgp (Germany and Slovakia) | Ishan Malik | [7 empty] | Complete |  | To perform on Sunday 7th Nov.
TRIAL CUTOVER START
|  | 3.1 | PREPARATIONS BEFORE APPS STOP
Do we require this ? | Aries Systems | 3.1.1 | Turn off order processing | Attila Fiel |  |  | 30 mins. | [5 empty] | Need to Validate with Attila Gurbi and Team
|  | 3.1.2 | Check whether all the invoices are printed | Attila Fiel
|  | 3.1.3 | Disable jobs in ARIES responsible for data refresh | Attila G |  |  | 15 mins. |  |  |  |  | Waiting for reply
| Concord | 3.1.4 | Turn off order processing | Eugene |  |  | 10 mins
|  | 3.1.5 | Check whether all the invoices are printed | Albina Kazantseva |  |  | 10 mins | [5 empty] | Business Team need to be involved
|  | 3.1.6 | Disable jobs in Ukraine responsible for data refresh | Eugene |  |  | 10 mins
|  | 3.1.7 | Disable Oracle jobs and stop UA Batcher sessions | Eugene |  |  | 15 mins
|  | 3.1.8 | Stop Replication for MAO HDS | Eugene |  |  | 5 mins
|  | 3.1.9 | Change NOEL to dummy URL | Laszlo Gecse/BDP/HU <Laszlo.Gecse@avon.com |  |  | 5 mins | [5 empty] | Need confirmation if Lazlo will support or someone from him team
|  | 3.1.10 | Update NOEL interface control table in CORBY WEBECEP | Michal |  |  | 5 mins
|  | 3.2 | APPLICATIONS STOP |  | 2021-11-08 09:00 | 2021-11-08 10:00 | 30 mins |  |  |  | 3.1, 3.2
|  | 3.2.1 | stop gi3 jvm New ( Estonia, finland, Latvia, Lithuania, ukraine & UA) - | MW team/ Santosh |  |  | 20 mins | 2021-11-08 09:17 | 2021-11-08 09:18 | 0:01 |  | Complete | https://amslxgi3pdmgr1.dc.avon.net:14001/ibm/console/logon.jsp
ESO-OMS-ADMIN |  | 3.2.2 | Stop all GOMAC / Estonia, finland, Latvia, Lithuania, ukraine markets (New) | OMS Admins / Gergo Spielmann |  |  | 10 mins | 2021-11-08 09:20 | 2021-11-08 09:21 | 0:01 |  | Complete
|  | 3.3 | DB ACTIVITIES |  | 2021-11-08 10:00 | 2021-11-08 15:00 | 7 hrs |  | 2021-11-08 10:27 |  | 3.3 | Complete
|  | 3.3.1 | DATABASE REFRESH | Ishan
ENT-ORACLE |  | 3.3.1.1 | Drop DBs - Clear archive filesystem | Ishan Malik |  |  | 10 mins | 2021-11-08 09:21 | 2021-11-08 09:44 | 0:23 |  | Complete
ENT-ORACLE |  | 3.3.1.2 | restore database from level 0 backup ( | Ishan Malik |  |  | 150 mins | 2021-11-08 09:44 | 2021-11-08 11:28 | 1:44 |  | Complete
|  | 3.4.1.2.1 | webeuap | Ishan Malik, Nakul Chopra |  |  | 150 mins | 2021-11-08 09:44 | 2021-11-08 11:28 |  |  | Complete
|  | 3.4.1.2.2 | gmcgfip | Ishan Malik, Nakul Chopra |  |  |  | 2021-11-08 09:44 | 2021-11-08 11:28 |  |  | Complete
|  | 3.4.1.2.3 | gmcguap | Ishan Malik, Nakul Chopra |  |  |  | 2021-11-08 09:44 | 2021-11-08 11:28 |  |  | Complete
ENT-ORACLE |  | 3.4.1.3 | level 1 backup + archive backup + copy | Ishan Malik | 2021-11-08 02:20 | 2021-11-08 03:35 | 75 mins | 2021-11-08 09:44 | 2021-11-08 11:28 |  | 3.3.1.2 | Complete
ENT-ORACLE |  | 3.4.1.3.1 | webecep | Ishan Malik, Nakul Chopra |  |  |  | 2021-11-08 09:44 | 2021-11-08 11:28 |  |  | Complete
ENT-ORACLE |  | 3.4.1.3.2 | gmcgcep - Estonia, finland, Latvia, Lithuania | Ishan Malik, Nakul Chopra |  |  |  | 2021-11-08 09:44 | 2021-11-08 11:28 |  |  | Complete
|  | 3.4.1.3.3 | gmcgeep- Ukraine | Ishan Malik, Nakul Chopra |  |  |  | 2021-11-08 09:44 | 2021-11-08 11:28 |  |  | Complete
ENT-ORACLE |  | 3.4.1.3.3 | Copy backup | Ishan Malik, Nakul Chopra |  |  | 15 mins | 2021-11-08 09:44 | 2021-11-08 11:28 |  |  | Complete
ENT-ORACLE |  | 3.4.1.4 | recover databases | Ishan Malik | 2021-11-08 03:35 | 2021-11-08 04:20 | 50 mins |  |  |  | '3.4.1.3 | In-Progress
ENT-ORACLE |  | 3.4.1.4.1 | webeuap | Ishan Malik, Nakul Chopra |  |  |  | 2021-11-08 11:28 | 2021-11-08 11:47 | 0:19 |  | Complete
ENT-ORACLE |  | 3.4.1.4.2 | gmcgfip - Estonia, finland, Latvia, Lithuania | Ishan Malik, Nakul Chopra |  |  |  | 2021-11-08 11:47 | 2021-11-08 13:05 | 1:18 |  | Complete
|  | 3.4.1.4.3 | gmcguap- Ukraine | Ishan Malik, Nakul Chopra |  |  |  | 2021-11-08 11:28 | 2021-11-08 11:55 | 0:27 |  | complete
|  | 3.4.1.5 | upgrade databases | Ishan Malik, Nakul Chopra | 2021-11-08 04:20 | 2021-11-08 05:35 | 75 mins |  |  |  | 3.4.1.4 | complete
|  | 3.4.1.5.1 | webeuap | Ishan Malik, Nakul Chopra |  |  |  | 2021-11-08 11:47 | 2021-11-08 12:25 | 0:38 |  | complete
|  | 3.4.1.5.2 | Gomac - gmcgfip | Ishan Malik, Nakul Chopra |  |  |  | 2021-11-08 13:04 | 2021-11-08 14:20 | 1:16 |  | complete
|  | 3.4.1.5.3 | Gomac - gmcguap | Ishan Malik, Nakul Chopra |  |  |  | 2021-11-08 12:20 | 2021-11-08 13:00 | 0:40 |  | complete
|  | 3.4.1.6 | Drop Partitions | Ishan Malik, Nakul Chopra | 2021-11-08 05:35 | 2021-11-08 06:20 | 45 mins |  |  |  | '3.4.1.5 | complete
|  | 3.4.1.6.1 | webeuap ( all except Estonia, finland, Latvia, Lithuania,Ukraine) | Ishan Malik, Nakul Chopra |  |  |  | 2021-11-08 13:25 | 2021-11-08 14:05 | 0:40 |  | complete
|  | 3.4.1.6.2 | Run scripts / create DB links - sent via email by Gergo | Ishan Malik, Nakul Chopra |  |  |  | 2022-01-08 14:09 | 2022-01-08 14:19 | 0:10 |  |  |  | Need to check with Gergo for scripts.
|  | 3.3 | DDL install db objects (external tables and directory changes) - webeuap | Nakul | 08/11/2021 :15:00 | 15:10 | 10 mins
|  | 3.3.1 | directory changes | Ishan Malik |  |  | 5 mins | 2022-01-08 14:19 | 2022-01-08 14:25 | 0:06 |  | complete
|  | 3.3.2 | Verify the partitions and data counts | Pavel |  |  | 10 mins | 2021-11-08 14:05 | 2021-11-08 14:15 | 0:10 |  | Complete
|  | 3.3.3 | truncate table monitor.session_login; webeuap | Ishan Malik |  |  | 2 mins | 2022-01-08 14:19 | 2022-01-08 14:25 | 0:06 |  | complete
|  | 3.4.2 | SANITY CHECK - each db owner should check if db is accessible | db owners | 2021-11-08 15:10 | 2021-11-08 15:40 | 30 mins |  |  |  | 3.4.1
|  | 3.4.2.1 | webeuap | Ivan Ferrer/ Pavel |  |  | 5 mins | 2022-01-08 14:25 | 2022-01-08 14:30 | 0:05 |  | complete
|  | 3.4.2.2 | chrptcep (EE,FI,LV,LT,UA) | Tatiana Darkshevich |  |  | 5 mins | 2021-11-08 14:40 | 2021-11-08 14:41 | 0:01 |  | complete
|  | 3.4.2.3 | Gomac - gmcgfip | Gergo Spielmann |  |  | 30 mins | 2022-01-08 14:25 | 2022-01-08 14:55 | 0:30 |  | complete
|  | 3.4.2.4 | Gomac - gmcguap | Gergo Spielmann |  |  |  | 2022-01-08 14:25 | 2022-01-08 14:55 | 0:30 |  | complete
|  | 3.4.3 | DML scripts execution (autojob details) - restoring backuped autosys jobs | Michal | 2021-11-08 15:40 | 2021-11-08 16:40 | 60 mins
|  | 3.4.3.1 | we need to clear down old archive logs so arch dest does not get full | Ishan Malik |  |  | 5 mins | 2021-11-08 14:41 | 2021-11-08 14:51 | 0:10 |  | complete | To be moved to DBA section
|  | 3.4.3.2 | Test websphere data sources in Amsterdam in EE,FI,LV,LT,UA | MW team/Santosh |  |  | 15 mins | 2021-11-08 14:48 | 2021-11-08 14:58 | 0:10 |  | complete | https://amslxgi3pdmgr1.dc.avon.net:14001/ibm/console
|  | 3.4.3.3 | Run jobs to recalculate statistics - webeuap | Ishan Malik |  |  | 60 mins | 2021-11-08 14:50 | 2021-11-08 15:45 | 0:55 |  | complete | Independent parallel task
|  | 3.6 | CONTENT REFRESH |  | 2021-11-08 12:30 | 2021-11-08 15:00 | 2.5 hrs
|  | 3.6.1 | Needs to send a notification by email to Anton that all future deployment after nov8 needs to be done on old and new Gi3 (Oct 8-9) | Gurvinder Singh |  |  | 5 mins |  |  | 0:00 |  | Complete
|  | 3.6.2 | Refresh NAS Folders (GI3 all EE,FI,LV,LT,UA markets) | Maykon Salvi |  |  | 120 mins | 2021-11-08 11:40 | 2021-11-08 13:40 | 2:00 |  | Complete
|  | 3.6.3 | Update property files (GI3 all EE,FI,LV,LT,UA markets) | Anandhi/Praveena |  |  | 30 mins | 2021-11-08 13:40 | 2021-11-08 14:52 | 1:12 |  | Complete
|  | 3.7 | Restart Applications |  | 2021-11-08 16:40 | 9/11/2021 17:25 CET | 45 mins
|  | 3.7.1 | Applications to be started (Amst pre-prod): GI3 clusters CE2 markets and UA | Ankur |  |  | 30 mins | 2021-11-08 15:00 | 2021-11-08 15:20 | 0:20 |  | complete
|  | 3.7.2 | Applications to be started (Amst pre-prod): GOMAC | Gergo Spielmann |  |  | 30 mins | 2021-11-08 15:00 | 2021-11-08 16:30 | 1:30 |  | complete
|  | 3.7.3 | Test websphere data sources in Amsterdam in EE,FI,LV,LT,UA | MW team |  |  | 15 mins | 2021-11-08 15:20 | 2021-11-08 15:30 | 0:10 |  | complete
|  | 3.10 | IT-smoke testing (application level) - DATA IS NOT SCRAMBLED! |  | 2021-11-09 17:25 | 00/01/1900 18:55:00 | CET
|  | 3.10.1 | GI3 smoke tests with hostfile entry | Anandhi/Praveena |  |  | 90 mins | 2021-11-08 14:20 | 2021-11-08 15:50 | 1:30 |  | complete
|  | 3.10.2 | AGS classic webservices | Raja / Shankar |  |  | 60 mins | 2021-11-08 16:10 | 2021-11-08 16:45 | 0:35 |  | complete
|  | 3.10.3 | AGS3 | Zoltan Kovacs |  |  | 5 mins |  |  | 0:00 |  | complete

## Sheet2 (hidden)
CRQ |  | No | Task description | Responsible | START CEST tz | END CEST tz | Duration In (Mins) | Predecesor | Status | Comments |  | Real start | Real end | duration
GOLIVE: 12th of November, start downtime: 2100 CET
Estimates
|  |  | Database backup and recovery estimations from Ishan | DB's |  | Restore | Estimated by
|  |  |  | Old | New
|  |  | ODS DB | webecep | webeuap
|  |  | ODS DB Ukraine | webecep | webeuap
|  |  | LINX DB | gmcgcep | gmcgfip
|  |  | LINX DB Ukraine | gmcgeep | gmcguap
|  |  | chrptcep | chrptcep
|  |  | leadsep(EE,LA,LT) | leadsep
|  |  | PG(EE,FI,LT, LV) | PG
In scope DB's: ODS, GOMAC, HDS
Out of scope DB: Leads?
|  | 1 | Pre-cutover checks / activities |  | 29th Oct | 12th Nov | 0:00
|  | 1.1 | Maintanance page (content to be confirmed and who prepare, when) | Gurvinder Singh
|  | 1.2 | Agree prompt on IVR/CTI
|  | 1.3 | GO/NOGO for cutover with Business | Gurvinder Singh
|  | 1.4 | CRQ for Outage (CHG0062968) | Gurvinder Singh
|  | 1.5 | QAP signoff | Attilla Domokos
|  | 1.6 | UAT signoff (new PROD) | Mihaly / Attila
|  | 1.7 | outage + communication | Gurvinder Singh
|  | 1.8 | Global Privacy approval | Anastacia Izmaylova
|  | 1.9 | Project Risks approval | Michał Ziółkowski
|  | 1.10 | SOX approval | Karolina Przybysz
|  | 1.11 | Service Team approval (communication) | Jarosław Żurawski
|  |  | Firewall port communication from celerity to MQ in Amsterdam/Corby for concorde applictaion | Gwidon |  |  |  |  | Complete | Need to check with Gwidon if all ports are opened Source: Concorde Database(172.26.180.80) target amslxgi3pmq1.dc.avon.net ( 10.160.140.20) port 1414 cbylxwebepmq1.uk.avon.com (172.20.29.99 ) port 1414
|  | 2 | PREPARATIONS / CHECKS / SCRIPTING
|  | 2.1 | Preparation activities
|  | 2.1.1 | Check all dblinks in webeuap, gmcgfip, gmcguap and confirm if they need to undergo any changes. | Ivan (webe) (chrptcep), Gergo (gmc) | [5 empty] | Gergo completed his part;
|  | 2.1.2 | Check whether we have got any changes in DDLs we would need to run during cutover (check with Michal for EXT) | Ivan Ferror | [5 empty] | Michal to provide script ot Ivan Ferror
|  | 2.2 | Maintenence pages / prompts / communication
|  | 2.5 | Scripts preparation
|  | 2.5.1 | Level 0 backup scripts | Ishan
|  | 2.5.2 | WEBECEP (ODS db) clone and upgrade from production | Ishan
|  | 2.5.3 | gmcgcep | Ishan
|  | 2.5.4 | scripts to install db objects (external tables for ETL users) | Ivan Ferror |  |  |  |  | In progress
|  | 2.5.5 | review prod deployment process GI3, AGS classic | Maykon | [5 empty] | Maykon will Validate
|  | 2.7 | AGS3 / MAO verification
|  | 2.7.1 | AGS3 - deploy of newest version on prod (on QA already deployed) | Andras/Ivan Ferror
|  | 2.8 | Another preparations
|  | 2.8.1 | hostfiles | Maykon |  |  |  |  | Complete
|  | 2.8.2 | prepare new AKAMAI for AGS classic & AGS3 | Maykon |  |  |  |  | Complete
|  | 2.8.3 | create new NetScalers for AGS classic and AGS3 | HCL Network Team
|  | 2.8.4 | validate new servers backup - all prod non-data servers | Vineet / backup team
|  | 2.8.5 | Open connectivity from MAS PROD env (AWS) to AGS classic endpoint! | Imre Sz
|  | 2.8.6 | Check connectivity from MAS PROD env (AWS) to AGS classic endpoint! | Imre Balla |  |  | 15 mins
|  | 2.8.7 | resync NAS folders GI3 | Maykon | [5 empty] | Will be completed by 8th November Need to talk to Anton he needs to deploy contents in both env.s
|  | 2.8.8 | Deploy GI3 property files | Anandhi
|  | 2.8.9 | Reduce DNS TTL 5 mins | Amit
|  | 2.8.10 | Validate DNS TTL | Amit
|  | 2.8.11 | SMTP servers to be installed to batch and app servers - Check if it was done | Maykon |  |  |  |  | Completed
|  | 2.8.12 | level 0 backup - 2 dbs Friday - webecep and gmcgcep | Ishan
|  | 2.8.13 | we need to clear down old archive logs so arch dest does not get full | Ishan
|  | 2.8.14 | hostfiles - provide for new users (same as for testing) | Gurvinder Singh
|  | 2.8.15 | Constantino, will raise ticket to update ags3 url on fuse end | Constantino
|  | 2.8.16 | Setup Gi3 maint page (AMST) | Martket Content Team / manish / MW team | 2021-10-22 | 2021-10-22
|  | 2.8.17 | ODS - CDW | Michal | [5 empty] | Need to check with Satyam
|  | 2.8.17.1 | MAS eligability feed change
|  | 3 | CUTOVER
|  | 3.1 | Initial activities
|  | 3.1.1 | Maintenance Pages set up |  | 2021-10-12 21:00
|  | 3.1.1.1 | GI3 Maintenance pages set up | MW Team
|  | 3.1.1.1.1 | Setup Gi3 maint page (AMST) | MW Team |  |  | 30 mins
|  | 3.1.1.1.2 | Making the DNS changes - all CE2 & UA markets | Amit |  |  | 30 mins
|  | 3.1.1.1.3 | Akmai changes - all CE2 & UA markets | Maykon |  |  | 30mins
|  | 3.1.1.1.4 | Validate Gi3 maint page | Anandhi |  |  | 15 mins
|  | 3.1.1.2 | MAO Maintenance pages set up
ENT-MIDDLEWARE WAS |  | 3.1.1.2.1 | MAO - Setup the maint page EE,FI,LV,LT Markets | MW Team |  |  | 30 mins
ENT-MIDDLEWARE WAS |  | 3.1.1.2.2 | MAO - Setup the maint page (for few markets)-Ukraine Markets | Terraform Team - Kapender / Nirdesh - to be confirmed from Vineet |  |  | 30mins
|  | 3.1.1.2.3 | MAO - validate MAO connectivity | Tatiana Darkshevich | [5 empty] | To confirm with Carol
|  | 3.1.1.3 | Avon On - disable connections 5 markets | Sai |  |  | 60 mins
|  | 3.1.1.3.1 | Disable single sign on to place orders | Sai
|  | 3.1.1.3.2 | Disable single sign on to history of orders / returns | Sai
|  | 3.1.1.3.3 | Disable signe sign on to cutomer orders | Sai
|  | 3.1.1.3.4 | Disable make a payment from dashboard, from my account page, decision landing page, menu | Sai
|  | 3.1.1.3.5 | Disable edit phone number and email from my profile page | Sai
|  | 3.1.1.3.6 | Disable single sign on to Avon Office | Sai
|  | 3.1.1.3.7 | Disable single sign on to Avon Connect | Sai
|  | 3.1.1.3.8 | Disable IMB dashboard | Sai
i |  | 3.1.1.3.9 | Disable IMB ordering | Sai
|  | 3.1.1.3.10 | Disable single sign on for Avon Grow | Sai
|  | 3.1.1.3.11 | Disable self appointment from login page | Sai
|  | 3.1.1.3.12 | Potentially include task related to digital | Sai
|  | 3.1.1.4 | MAS Maintenance pages set up - five markets | Imre Balla |  |  | 15 mins
|  | 3.1.1.5 | Avon Grow Maintenance pages set up - 4 markets | Jackson |  |  | 10 mins
|  | 3.1.1.6 | IVR Maintenance pages set up 4 markets or 5 Markets | Laszlo.Somogyi@maintel.co.uk | [5 empty] | Need to check with SME from IVR about steps and time required for change. Need to check if we can keep it up for CE2 markets - Need to reconfirm for Gwidon eugene
|  | 3.1.1.6.1 | IVR - activate prompt () | Laszlo.Somogyi@maintel.co.uk | [5 empty] | Need to change voice message mentioning maintenance
|  | 3.1.1.7 | FUSE - 5 markets | kristine.tansengespiritu@avon.com, gwe.service.delivery@avon.com | [5 empty] | Need to confirm
|  | 3.1.1.8 | IMB Maintenance pages set up - 5 Markets | Alexandru |  |  | 30 mins
|  | 3.1.1.9 | Leads Maintenance pages set up - 3 markets - EE, LA, LT | Imre Balla | [5 empty] | Need to confirm from Imre Bala
|  | 3.2 | PREPARATIONS BEFORE APPS STOP
| Aries Systems | 3.2.1 | Turn off order processing | Attila Fiel |  |  | 30 mins. |  |  | Need to Validate with Attila Gurbi and Team
|  | 3.2.2 | Check whether all the invoices are printed | Attila Fiel
|  | 3.2.3 | Disable jobs in ARIES responsible for data refresh | Attila G |  |  | 15 mins. |  | Waiting for reply
| Ukraine | 3.2.4 | Turn off order processing | Eugene |  |  | 10 mins
|  | 3.2.5 | Check whether all the invoices are printed | Albina Kazantseva |  |  | 10 mins |  |  | Business Team need to be involved
|  | 3.2.6 | Disable jobs in Ukraine responsible for data refresh | Eugene |  |  | 10 mins
|  | 3.2.7 | Disable Oracle jobs and stop UA Batcher sessions | Eugene |  |  | 15 mins
|  | 3.2.8 | Stop Replication for MAO HDS | Eugene |  |  | 5 mins
|  | 3.2.9 | Change NOEL to dummy URL | Laszlo Gecse/BDP/HU <Laszlo.Gecse@avon.com | [5 empty] | Need confirmation if Lazlo will support or someone from him team
|  | 3.2.10 | Update NOEL interface control table in CORBY WEBECEP | Michal |  |  | 5 mins
| c | 3.3 | APPLICATIONS STOP |  | 2021-11-12 22:40 | 2021-10-22 23:40 | 60 mins | 3.1, 3.2
|  | 3.3.3 | stop old gi3 jvm (all Estonia, finland, Latvia, Lithuania, ukraine & UA) | MW |  |  | 20 mins |  |  | Nordics and UA https://cbylxwebewdm1.uk.avon.com:14001/ibm/console
ESO-OMS-ADMIN |  | 3.3.4 | Stop all GOMAC / Estonia, finland, Latvia, Lithuania, ukraine markets | OMS Admins / Gergo |  |  | 10 mins | 4.1
|  | 3.4 | DB ACTIVITIES |  | 2021-10-22 23:40 | 2021-10-23 06:40 | 420 mins (7 hours) | 3.3 |  | 3.4.6.4 is not in duration, could be done independently
|  | 3.4.1 | DATABASE REFRESH | Ishan |  |  | 7 hours
ENT-ORACLE |  | 3.4.1.1 | Drop DBs? Clear archive filesystem | Ishan | 2021-10-22 23:40 | 2021-10-22 23:50 | 10 mins
ENT-ORACLE |  | 3.4.1.2 | restore database from level 0 backup ( | Ishan | 2021-10-22 23:50 | 2021-10-23 02:20 | 150 mins | 3.4.1.1
|  | 3.4.1.2.2 | webeuap | Ishan, Nakul |  |  | 150 mins |  |  | Ishan to provide time
|  | 3.4.1.2.3 | gmcgfip | Ishan, Nakul
|  |  | gmcguap | Ishan, Nakul
ENT-ORACLE |  | 3.4.1.3 | level 1 backup + archive backup + copy | Ishan | 2021-10-23 02:20 | 2021-10-23 03:35 | 75 mins | 3.4.1.2 |  | Can be done in parallel with others
ENT-ORACLE |  | 3.4.1.3.1 | webecep | Ishan, Nakul | [5 empty] | Duration of longest recover (recovery done in parallel)
ENT-ORACLE |  | 3.4.1.3.2 | gmcgcep - Estonia, finland, Latvia, Lithuania | Ishan, Nakul
|  | 3.4.1.3.3 | gmcgeep- Ukraine | Ishan, Nakul, | [5 empty] | Ishan to provide time
ENT-ORACLE |  | 3.4.1.3.3 | Copy backup | Ishan, Nakul |  |  | 15 mins
ENT-ORACLE |  | 3.4.1.4 | recover databases | Ishan | 2021-10-23 03:35 | 2021-10-23 04:20 | 50 mins | 3.4.1.3
ENT-ORACLE |  | 3.4.1.4.1 | webeuap | Ishan, Nakul
ENT-ORACLE |  | 3.4.1.4.2 | gmcgfip - Estonia, finland, Latvia, Lithuania | Ishan, Nakul
|  |  | gmcguap- Ukraine | Ishan, Nakul
|  | 3.4.1.5 | upgrade databases | Ishan, Nakul | 2021-10-23 04:20 | 2021-10-23 05:35 | 75 mins | 3.4.1.4
|  | 3.4.1.5.1 | webeuap | Ishan, Nakul
|  | 3.4.1.5.2 | Gomac - gmcgfip | Ishan, Nakul
|  |  | Gomac - gmcguap | Ishan, Nakul
|  | 3.4.1.7 | Drop Partitions | Ishan, Nakul | 2021-10-23 05:35 | 2021-10-23 06:20 | 45 mins | '3.4.1.5
|  | 3.4.1.7.1 | webeuap ( all except Estonia, finland, Latvia, Lithuania,Ukraine) | Ishan, Nakul
|  | 3.4.1.7.2 | Run scripts / create DB links - sent via email by Gergo | Ishan, Nakul
|  | 3.3 | DDL install db objects (external tables and directory changes) - weberop | Nakul
|  | 3.4.1 | directory changes | Ishan |  |  | 5 mins
|  | 3.4.1.8 | Verify the partitions and data counts | Ivan Ferror | 2021-10-23 06:20 | 2021-10-23 06:30 | 10 mins
|  | 3.4.1.8.1 | truncate table monitor.session_login; webeuap | Ishan |  |  | 2 mins
|  | 3.4.2 | SANITY CHECK - each db owner should check if db is accessible | db owners | 2021-10-23 06:30 | 2021-10-23 06:35 | 5 mins | 3.4.1
|  | 3.4.2.1 | webeuap | Ivan Ferror |  |  | 5 mins
|  | 3.4.2.2 | chrptcep (EE,FI,LV,LT,UA) | Tatiana Darkshevich |  |  | 5 mins
|  | 3.4.2.3 | Gomac - gmcgfip | Gergo |  |  | 60mins
|  | 3.4.2.4 | Gomac - gmcguap | Gergo
|  | 3.4.3 | DML scripts execution (autojob details) - restoring backuped autosys jobs | Michal | 2021-10-23 06:35 | 2021-10-23 06:40 | 5 mins
|  | 3.4.3.1 | we need to clear down old archive logs so arch dest does not get full | Ishan |  |  | 5 mins |  |  | To be moved to DBA section
|  | 3.4.3.2 | Test websphere data sources in Amsterdam in EE,FI,LV,LT,UA | MW team |  |  | 15 mins |  |  | https://amslxgi3pdmgr1.dc.avon.net:14001/ibm/console
|  | 3.4.3.3 | Run jobs to recalculate statistics - webeuap | Ishan |  |  | 60 mins |  |  | Independent parallel task
|  | 3.6 | CONTENT REFRESH |  |  | 18.10.2021 | 18.10.2021
|  |  | needs to send a notification by email to Anton that all future deployment after nov8 needs to be don on old and new Gi3 (Oct 8-9) |  | Gurvinder
|  | 3.6.1 | Refresh NAS Folders (GI3 all EE,FI,LV,LT,UA markets)(Oct 8-9) |  | Maykon | 18.10.2021 14:00 CET | 150 mins |  |  | Anton to implemention on both locations (New, and old)
|  | 3.6.2 | Update property files (GI3 all EE,FI,LV,LT,UA markets)(Oct 8-9) |  | Anandhi/Keerthana |  | 120 mins
|  | 3.7 | Restart Applications |  |  | 13.10.2021 16:00 CET | 13.10.2021 16:45 CET | 60 mins
|  | 3.7.1 | Applications to be started (Amst pre-prod): GI3 clusters CE2 markets |  | Pradeep Arya/ Rahul Sud |  | 50 mins
|  | 3.7.8 | Applications to be started (Amst pre-prod): GOMAC |  | Gergo |  | 60 mins
|  | 3.10 | IT-smoke testing (application level) - DATA IS NOT SCRAMBLED! |  |  | 13.10.2021 16:45 CET | 13.10.2021 17:45 CET | 180 mins
|  | 3.10.1 | GI3 smoke tests with hostfile entry |  | Anandhi/Keerthana |  | 180 mins
|  | 3.10.2 | AGS classic webservices |  | Raja / Shankar |  | 60 mins
|  | 3.10.3 | AGS3 |  | Zoli |  | 5 mins
created |  | 3.7 | SWITCH TO NEW DATABASES |  | 2021-10-23 06:40 | 2021-11-13 | 10 mins | 3.4
|  | 3.7.1 | supportal new db configuration | Michal |  |  | 10 mins
|  | 3.7.2 | ezBrochure change point CE2 markets to new DB (XML config change) | Michal
|  | 3.7.3 | CRM - redirect to new LINX DB - only for( EE,FI,LV,LT,UA) | Citrix team / Tibor | 2021-10-23 05:35 | 2021-11-13 | 70 mins | 3.4.1.5.2 |  | Will be performed after 3.4.1.5.2 Need to confirm - need input from aries team to citrix team
|  | 3.8 | Setup connectivity between future PROD and satellite applications |  | 2021-11-13 | 2021-11-13 | 120 mins | 3.7
|  | 3.8.1 | Avon Grow - Change Avon Grow AGS service enpoint to new one (details) | Jackson |  |  | 60 mins | 3.5.4;3.4
|  | 3.8.2 | MAS - Switch to new AGS URLs (detailed plan by Imre Balla) | Imre Balla / Akos Tamas |  |  | 60 mins |  |  | need confirmation from Imre
|  | 3.8.3 | MAO
|  | 3.8.3.1 | AGS3 domain update : myavon-ws-eu-ams.prod.avon.com | Tamas Szeremy |  |  | 10 mins |  |  | Need URL confirmation from Tamas
|  | 3.8.3.2 | Validation of MAO connectivity | Tanaya |  |  | 20 mins
|  | 3.8.4 | IMB - Switch to new AGS URLs | alexandru |  |  | 30 mins |  |  | New AGS URL in Amsterdam: https://ags-ws-eu-ams.prod.avon.com/agws/
|  | 3.8.5 | Avon On | Sai
|  | 3.8.5.1 | Switch to new AGS URLs | Sai |  |  | 30 mins |  |  | New AGS URL in Amsterdam: https://ags-ws-eu-ams.prod.avon.com/agws/
|  | 3.8.6 | IVR - NA | Laszlo.Somogyi@maintel.co.uk | [5 empty] | Need endpoints from Laszlo.
|  | 3.8.7 |  | Attila / Tibor |  |  | 5 mins |  |  | New AGS URL in Amsterdam: https://ags-ws-eu-ams.prod.avon.com/agws/
|  | 3.8.8 | FUSE | gwe.service.delivery@avon.com, Kristine Tan Seng-Espiritu/MNL/PH <kristine.tansengespiritu@avon.com>
|  | 3.8.8.1 | local digital team update AGS3 fuse sso in magnolia (MAO) | Digital Team | [5 empty] | to be checked with the markets
|  | 3.8.8.2 | local digital team update AGS3 fuse sso in GI3 | Anandhi |  |  | 30 mins
|  | 3.8.8.3 | local digital team update AGS3 fuse sso in MAS | Imre Balla / Akos Tamas |  |  | 60 mins |  |  | Covered in 3.8.2
|  | 3.8.9 | Change Data Integration Services to New ODS - can be done after the DB activities, Rain to be informed | rain.zhen@avon.com |  |  | 30 mins |  |  | Avon Data Integration <avondataintegration@isoftstone.com> Avon Data Service Team <avondataservicesteam@isoftstone.com> from cbylxwebeeupdbc1.uk.avon.com:1521:webecep to amslxgi3eupdb2.dc.avon.net:1521:webeuap
|  | 3.8.10 | Eloqua config needs to be updated to use the proper AGS/AGS3 domain | Dragos Ene | 2021-10-26 | 2021-10-26 | TBC |  |  |  | myavon-ws-eu-dls.prod.avon.com
|  | 3.8.11 | SMS Gateway
|  | 3.8.11.1 | Change AGS classic endpoints | Pavel |  |  | 5 mins
|  | 3.8.12 | PRP - CE2 | Doru |  |  | 5 mins
|  | 3.8.13 | ARIES/Concord
|  | 3.8.13.1 | Change dblink/config for Tibi's engine - Nordics | Gabor Pachert |  |  | 5 mins |  |  | also linx and HDS DB Links
|  | 3.8.13.2 | Change dblink/config for Tibi's engine - UA | HCL DB team/ Eugene |  |  | 5 mins |  |  | DB link connection will remain intact but TNS name will change. also linx and HDS DB Links
|  | 3.8.14 | Teamsite
|  | 3.8.14.1 | Change TeamSite config | Anton |  |  | 120 mins
|  |  | Payment Gateway - ( EE,FI,LV,LT) (Not required In UA) NEW | Priyanka / Raja | [5 empty] | Card details required for QA env.- Sandra
|  |  | Leads application - 3 markets - EE, LA, LT | Imre Balla | [5 empty] | Need to confirm with Imre Bala
|  | 3.9 | ADDITIONAL CHECKS/CONNECTIVITY |  | 2021-10-23 06:50 | 2021-10-23 07:20 | 30 mins | 3.7
ENT-AUTOSYS |  | 3.9.1 | DML scripts execution (autojob details) | Michal |  |  | 10 mins |  |  | Duplicate job
|  | 3.9.2 | Run selected autosys jobs manually from cmd line and verify they are not failing | Michal |  |  | 15 mins
created |  | 3.10' | STARTING APPS |  | 2021-10-23 08:50 | 2021-10-23 09:50 | 60 mins | 3.7, 3.8, 3.9
|  | 3.10.3 | Run scripts / start GOMAC | Gergo |  |  | 120 mins |  |  | Required for 2 environments
|  | 3.10.4 | Start MAO Email sending Boomi process | Tibor Kepecs |  |  | 5 mins |  |  | Start MAO Email sending Boomi process. Add EE,LV,LT,FI,UA to PROD APAC -> env variables -> Dynamic Process Properties -> DPP_MAOEmail_marketList
|  | 3.10.5 |  |  |  |  | 5 mins |  |  | a
|  | 3.10.6 | start GI3 apps (CE2 markets) (Amst) | MW Team |  |  | 60 mins |  |  | https://amslxgi3pdmgr1.dc.avon.net:14001/ibm/console
|  | 3.10.7 | ripple restart AGS3 MyAvon Cluster | MW | [5 empty] | https://amslxags3pdmgr1.dc.avon.net:14001/ibm/console
|  | 3.10.8 | ripple restart AGS-AMS Cluster | MW | [5 empty] | https://amslxgi3pdmgr1.dc.avon.net:14001/ibm/console
|  | 3.10.9 | Ripple restart CPC PG Armsterdam (WAS9) | MW | [5 empty] | https://amslxgi3pdmgr1.dc.avon.net:14001/ibm/console
|  | 3.10.10' | Enable Aries jobs | Gabor Pachert |  |  | 5 mins
|  |  | Enable Concord jobs | Eugene |  |  | 5 mins
On 28.09 we finished here |  | 3.11 | SMOKE TESTS |  | 2021-10-23 09:50 | 2021-10-23 12:50 | 180 mins | 3.10'
|  | 3.11.1 | smoke tests MAO including reports | Tanaya |  |  | 120 mins
|  | 3.11.2 | smoke tests GI3 | Anandhi |  |  | 180 mins
|  | 3.11.3 | Smoke test AGS3 | Lorand |  |  | 15 mins
|  | 3.11.4 | smoke tests AGS classic | Shankar |  |  | 30 mins
|  | 3.11.5 | smoke tests LINX connectivity | Gergo |  |  | 30 mins
|  | 3.11.6 | RRM connectivity to Linx | Gabor Pachert |  |  | 30 mins | '3.7.3
|  | 3.11.7 | Smoke test Payment Gateway (partial) | Priyanka G |  |  | 30 mins
created |  | 3.12 | Enable autosys jobs |  | 2021-10-23 08:50 | 2021-10-23 09:25 | 35 mins | 3.8
ENT-AUTOSYS |  | 3.12.1 | Put new Dallas/Corby autosys jobs back online. | Miguel |  |  | 15 mins
ENT-AUTOSYS |  | 3.12.2 | Check for any job failures - AUTO_JOB_DETL, autsys log files | Michal |  |  | 15 mins
|  | 3.12.3 | we need to clear down old archive logs so arch dest does not get full | Ishan |  |  | 5 mins |  |  | Moved to DBA section
|  | 3.13 | BUSINESS TESTING (with maintenance pages on) |  | 2021-10-23 12:50 | 2021-10-23 18:50 | 6 hours | 3.11 |  | Business testors can work in shifts if possible
|  | 3.13.1 | GI3
|  | 3.13.1.1 | Estonia | Janis Gureckis
|  | 3.13.1.2 | Finland | Renars Paukstello
|  | 3.13.1.3 | Latvia | Renars Paukstello
|  | 3.13.1.4 | Lithuania | Janis Gureckis
|  | 3.13.1.5 | Ukraine | Oksana
|  | 3.13.2 | MAS
|  | 3.13.2.1 | Estonia | Janis Gureckis | [6 empty] | Yes
|  | 3.13.2.2 | Finland | Renars Paukstello | [6 empty] | Yes
|  | 3.13.2.3 | Latvia | Renars Paukstello | [6 empty] | Yes
|  |  | Lithuania | Janis Gureckis
|  |  | Ukraine | Oksana
|  | 3.13.3 | MAO
|  | 3.13.3.1 | Estonia | Janis Gureckis | [6 empty] | Yes
|  | 3.13.3.2 | Finland | Renars Paukstello | [6 empty] | Yes
|  | 3.13.3.3 | Latvia | Renars Paukstello | [6 empty] | Yes
|  | 3.13.3.4 | Lithuania | Janis Gureckis | [6 empty] | Yes
|  | 3.13.3.5 | Ukraine | Oksana | [6 empty] | Yes
|  | 3.13.4 | GROW -can be tested when maint page is lifted
|  | 3.13.4.1 | Estonia | Janis Gureckis
|  | 3.13.4.2 | Finland | Renars Paukstello
|  | 3.13.4.3 | Latvia | Renars Paukstello
|  | 3.13.4.4 | Lithuania | Janis Gureckis
|  | 3.13.4.5 | Ukraine | Oksana
|  | 3.13.5 | Avon ON -can be tested when maint page is lifted
|  | 3.13.5.1 | Estonia | Janis Gureckis
|  | 3.13.5.2 | Finland | Renars Paukstello
|  | 3.13.5.3 | Latvia | Renars Paukstello
|  | 3.13.5.4 | Lithuania | Janis Gureckis
|  | 3.13.5.5 | Ukraine | Oksana
|  | 3.13.6 | IMB NOT UNTIL MAINT PAGE LIFTED
|  | 3.13.6.1 | Estonia | Janis Gureckis
|  | 3.13.6.2 | Finland | Renars Paukstello
|  | 3.13.6.3 | Latvia | Renars Paukstello
|  | 3.13.6.4 | Lithuania | Janis Gureckis
|  | 3.13.6.5 | Ukraine | Oksana
|  | 3.13.9 | Payment Gateway
|  | 3.13.9.1 | Estonia | Janis Gureckis
|  | 3.13.9.2 | Finland | Renars Paukstello
|  | 3.13.9.3 | Latvia | Renars Paukstello
|  | 3.13.9.4 | Lithuania | Janis Gureckis
|  | 3.13.10' | NOEL - will be performed after 3.15.1.12.1
|  | 3.13.10.1 | Estonia | Janis Gureckis
|  | 3.13.10.2 | Finland | Renars Paukstello
|  | 3.13.10.3 | Latvia | Renars Paukstello
|  | 3.13.10.4 | Lithuania | Janis Gureckis
|  | 3.13.10.5 | Ukraine | Oksana
|  | 3.13.11 | FUSE (integration check) - maintenance pages activated
|  | 3.13.11.1 | Estonia | Janis Gureckis
|  | 3.13.11.2 | Finland | Renars Paukstello
|  | 3.13.11.3 | Latvia | Renars Paukstello
|  | 3.13.11.4 | Lithuania | Janis Gureckis
|  | 3.13.11.5 | Ukraine | Oksana
|  | 3.13.12 | SMS ordering
|  | 3.13.12.1 | Estonia | Janis Gureckis
|  | 3.13.12.2 | Finland | Renars Paukstello
|  | 3.13.12.3 | Latvia | Renars Paukstello
|  | 3.13.12.4 | Lithuania | Janis Gureckis
|  | 3.13.12.5 | Ukraine | Oksana
|  | 3.13.13 | PRP - Germany | Tobias Rauscher
|  | 3.15.1.10 | Bill Test Orders | Markets |  |  | 60 mins
|  | 3.14 | GO / NO GO DECISION |  | 2021-10-23 18:50 | 2021-10-23 19:20
|  | 3.15 | LIFTING / Removal |  | 2021-10-23 19:20 | 2021-10-23 20:20 | 1 hours
|  | 3.15.1 | Remove maintenence pages
|  | 3.15.1.1 | GI3 - remove main page | MW team |  |  | 20 mins
|  | 3.15.1.1 | MAO - remove maintenance page
|  | 3.15.1.1.1 | MAO - remove maintenance page | MW team |  |  | 30 mins
|  | 3.15.1.1.2 | MAO - remove maintenance page | Terrafom team- Kapender |  |  | 30 mins
|  | 3.15.1.1.3 | Validation of removal of maintenance page | Tanaya |  |  | 5 mins
|  | 3.15.1.2 | MAS - remove maintenance page | Akos Tamas |  |  | 30 mins
|  | 3.15.1.3 | Avon Grow - remove maintenance page | jackson.yan@avon.com |  |  | 15 mins
|  | 3.15.1.4 | IMB - remove maintenance page | Alexandru |  |  | 30 mins
|  | 3.15.1.5 | Enable Avon On
|  | 3.15.1.5.1 | Enable single sign on to place orders | Sai |  |  | 45 mins
|  | 3.15.1.5.2 | Enable single sign on to history of orders / returns | Sai
|  | 3.15.1.5.3 | Enable signe sign on to cutomer orders | Sai
|  | 3.15.1.5.4 | Enable make a payment from dashboard, from my account page, decision landing page, menu | Sai
|  | 3.15.1.5.5 | Enable edit phone number and email from my profile page | Sai
|  | 3.15.1.5.6 | Enable single sign on to Avon Office | Sai
|  | 3.15.1.5.7 | Enable single sign on to Avon Connect | Sai
|  | 3.15.1.5.8 | Enable IMB dashboard | Sai
|  | 3.15.1.5.9 | Enable IMB ordering | Sai
|  | 3.15.1.5.10 | Enable single sign on for Avon Grow | Sai
|  | 3.15.1.5.11 | Enable self appointment from login page | Sai
|  | 3.15.1.5.12 | Digital recruitment links - enable a from component | Sai
|  | 3.15.1.6 | FUSE - Avon Connect | Kristine Tan Seng-Espiritu/MNL/PH <kristine.tansengespiritu@avon.com>, gwe.service.delivery@avon.com | [5 empty] | Kristine to open ticket with Fuse of 5 markets
|  | 3.15.1.8 | OSA Recruitmnet Pages - NA | Oksana
|  |  | Start SMS Gateway/SMS Ordering Job | Pavel |  |  | 5 mins
|  | 3.15.1.12 | NOEL
|  | 3.15.1.12.1 | Change NOEL endpoint from Corby to Amsterdam - AGS3 | Laszlo G |  |  | 30 mins
|  | 3.16 | Final Business Checks (after maintenance pages lifted) |  | 2021-10-23 20:50 | 2021-10-23 23:50 | 3 hours
|  | 3.16.1 | GI3
|  | 3.16.1.1 | Estonia | Janis Gureckis
|  | 3.16.1.2 | Finland | Renars Paukstello
|  | 3.16.1.3 | Latvia | Renars Paukstello
|  | 3.16.1.4 | Lithuania | Janis Gureckis
|  | 3.16.1.5 | Ukraine | Oksana
|  | 3.16.2 | MAS
|  | 3.16.2.1 | Estonia | Janis Gureckis
|  | 3.16.2.2 | Finland | Renars Paukstello
|  | 3.16.2.3 | Latvia | Renars Paukstello
|  | 3.16.2.4 | Lithuania | Janis Gureckis
|  | 3.16.2.5 | Ukraine | Oksana
|  | 3.16.3 | MAO
|  | 3.16.3.1 | Estonia | Janis Gureckis
|  | 3.16.3.2 | Finland | Renars Paukstello
|  | 3.16.3.3 | Latvia | Renars Paukstello
|  | 3.16.3.4 | Lithuania | Janis Gureckis
|  | 3.16.3.5 | Ukraine | Oksana
|  | 3.16.4 | GROW -can be tested when maint page is lifted
|  | 3.16.4.1 | Estonia | Janis Gureckis
|  | 3.16.4.2 | Finland | Renars Paukstello
|  | 3.16.4.3 | Latvia | Renars Paukstello
|  | 3.16.4.4 | Lithuania | Janis Gureckis
|  | 3.16.4.5 | Ukraine | Oksana
|  | 3.16.5 | Avon ON -can be tested when maint page is lifted
|  | 3.16.5.1 | Estonia | Janis Gureckis
|  | 3.16.5.2 | Finland | Renars Paukstello
|  | 3.16.5.3 | Latvia | Renars Paukstello
|  | 3.16.5.4 | Lithuania | Janis Gureckis
|  | 3.16.5.5 | Ukraine | Oksana
|  | 3.16.6 | IMB - After MAINT PAGE LIFTED
|  | 3.16.6.1 | Estonia | Janis Gureckis
|  | 3.16.6.2 | Finland | Renars Paukstello
|  | 3.16.6.3 | Latvia | Renars Paukstello
|  | 3.16.6.4 | Lithuania | Janis Gureckis
|  | 3.16.6.5 | Ukraine | Oksana
|  | 4 | END OF THE OUTAGE |  | 2021-10-23 23:50 | 2021-10-23 23:50
|  | 5 | Mass Billing enablement | Attila Fiel (Nordics)/ Albina Kazantseva(UA) |  |  | 30 mins |  |  | LIT, LAT, EST, FIN
|  | 6 | Post Outage
Note on K65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Gwidon what's the approach for this. Will the list of users for admin-rights to this file will come from Project? If so then we need a task to collect those and HCL to execute it

## Sheet1 (hidden)
| Jarosław Żurawski | +48789223300
| System | Name | Mail | Group | Mobile | Comments
| PM | Gurvinder Singh | gurvinder.loh@avon.com |  | +91 9988883360
| PM | Monika Zajączkowska | monika.zajaczkowska@avon.com | IPC-PMO-PRJMGMT | +48789222555
| PM HCL | Vineet Khare | vineet.khare@avon.com | n/a | +919650010594
| PM HCL | Manish Mittal | manish.mittal@avon.com |  | +91-9811151377
| GI3 | Pavel Gas | pavel.gas@avon.com | n/a | +420602655005 | Michal and Ivan are substitutions for Pavel
| GI3 | Ivan Ferrer | ivan.ferrer@avon.cpm | n/a | +52 5538769324
| GI3 DEV | Anandhi | anandhi.chinnarasu@avon.com | GWE-PRJ-MGMT | +91 9176033289
| HCL Middleware Team | Sweta Sinha | sweta-s@hcl.com | ENT-MIDDLEWARE WAS
| MW Team | Manish Kumar Gudral Pradeep Arya Sunday Ananya Sunday | AVON_MIDDLEWARE <AvonMiddleware@hcl.com> pradeep.arya@avon.com ananya.garg@avon.com | ENT-MIDDLEWARE WAS | +91 8860376884 +91 9899924522 +91 7500860667
| Server Build | Maykon Salvi | maykon.salvi@avon.com | DCO-SPO-SERVER-SUPT-BR | +55 (19) 9 8818-4532 +55 11 5546-8694
| LINX / GOMAC | Gergo Spielmann | gergo.spielmann@avon.com | ESO-OMS-ADMIN | +36308842023 | backup: Sławek
| LINX / GOMAC | Haziq Khalil | haziq.khalil@avon.com | ESO-OMS-ADMIN | +60 147209257 | not during NAME/PT/GR
| LINX / GOMAC | Jaya Gash | jaya.gash@avon.com | ESO-OMS-ADMIN | +60 1110 935650 | not during NAME/PT/GR
| LINX / GOMAC | Sławomir Świątkowski | slawomir.swiatkowski@avon.com | ESO-OMS-ADMIN | +48789209020 | in case Gergo need any support
| DB activities | Nakul Chopra | nakul.chopra@avon.com nakul.chopra@hcl.com | ENT-ORACLE | +8588897842
| DB activities | Ishan Malik | ishan.malik@hcl.com | ENT-ORACLE | +9896510152
| DB activities | Imre Szabo | imre.szabo@avon.com | ENT-ORACLE | +36307482028
| AGS3 | Zoltan Kovacs | zoltan.kovacs@avon.com | n/a | +36 30 34 34 311
| HCL Network Team | Amit Kumar | amitkum-ka@hcl.com | ENT-Networkdata | mobile no/ Whatsapp is +918809562513
| MAS | Levente Kiraly | levente.kiraly@avon.com | MY-AVON-STORE-APSUPT-GLOBAL | +36 20 9587884
| IMB | Alexandru Darabam | alexandru.daraban@interactively.eu | n/a | 0040761342301
| Magnolia PR | Uvaraj Murugesan | uvaraj.murugesan@avon.com | GWE-APP-SPT
| Avon Grow | Jackson Yan | jackson.yan@avon.com | n/a | +86 15997427627
| Avon Grow | Owen Wan | owen.wan@avon.com | n/a | +86 15207109989 | Pls keep our delivery lead (Owne) in cc
| Avon On | Sai Chadalapaka | Sai.Chadalapaka@avon.com | GWE-DEVELOPERS | +91 9500286426
| MAIMS all countries | Paulo Jorge | paulo.jorge@avon.com | n/a | +351 219226205 | onboard during all cutover
| MAIMS EG | Marko Nasef | marko.nasef@avon.com | n/a | +2 01014498765
| MAIMS SA | Hassan Alsadig | hassan.Alsadiq@avon.com | n/a | +966556922214
| MAIMS GR | Giouli Fanouraki | giouli.fanouraki@avon.com | n/a | +30 6977049226
| MAIMS PT, MA and all countries | Manuel João | manuel.joao@avon.com | n/a | +351913356658 | onboard during all cutover
| MAIMS GR | George Thanos | george.thanos@avon.com | n/a | +30210 6605500
| Billing operator for Linx EG | Mohamed Thabit | mohamed.thabit@avon.com | n/a | +201060059119
| Billing operator for Linx MA | Hanaa Amzi | hanaa.azmi@avon.com | n/a | +212 522 679 696 | Nadia Sadif - to advice if Hanaa is back or who can replace her during cutover
| Billing operator for Linx SA | Hassan Alsadig | hassan.Alsadiq@avon.com | n/a | +966556922214
| Billing operator for Linx PT | Ivan Criado | ivan.criado@avon.com | n/a | +34661416521 | Francisco Edesa as he is my backup only on my absences.
| Billing operator for Linx GR | Giouli Fanouraki | giouli.fanouraki@avon.com | n/a | +30 6977049226 | greece.billing@avon.com
| AWS DevOps | Rakesh Kumar |  |  | +919971200149
| Autosys jobs | Michal Elias | michal.elias@avon.com | ENT-AUTOSYS | +42 0732543355
| Autosys jobs | Miguel Poma | miguel.poma@avon.com | ENT-AUTOSYS
| AS-400 | Suresh Rajagopal | sureshraj@hcl.com | ENT-AS400
| AS-400 | Ravi Verma | ravi_v@hcl.com | ENT-AS400
| Teamsite | Anoton Koptelov | anton.koptelov@avon.com | n/a | +79161722706
| AGS | Shankar Chandranswayamprabha | shankar.chandranswayamprabha@avon.com | n/a | +44 7943 189148 | Shankar is available today: +447760281932
| NOEL | Laszlo Gecse | Laszlo.Gecse@avon.com | ENT-INTEGRATION-SERVICES | +36702186389
| FUSE | Constantino Pooja Upadhyay | constantino.vazquez@avon.com pooja.upadhyay@fuseuniversal.com | n/a | +34 639 77 22 39
Standby
| HCL DBA | DBA on duty 24/7
| Network | Vitaliy Krikun | vitaliy.krikun@avon.com |  | +44-773-330-2710 | in case of real emergency with network as Vitaliy is on holidays 1 week since Sat
| Linux |  |  | ENT-LINUX |  | in case we need support from your team we will reach you
| Security |  |  | ENT-NETWORK SECURITY |  | in case we need support from your team we will reach you
| LINX / GOMAC BA | Szabolcs Hodossy | szabolcs.hodossy@avon.com |  | +36 30 657 0350
| LINX / GOMAC Arch | Tamas Csiba | tamas.csiba@avon.com |  | +36305526287
Business team
| ePayment | Sergio Miguel Pestana Abreu | sergio.pestana@avon.com
| ePayment | Vana Politopoulou | vana.politopoulou@avon.com
| ePayment | Agisilaos Koulopoulos | agisilaos.koulopoulos@avon.com
|  | Imane Ettaki |  |  | +'212672280709
| Greece | Nina Markozannes | nina.markozanes@avon.com |  | +306983391356
| Greece | Ioanna Tsoukala | ioanna.tsoukala@avon.com |  | +306932346892
| Portugal | Rui Gaspar | rui.gaspar@avon.com
| Egypt | Marian Nasr | Marian.Nasr@avon.com
|  | Mohamed Thabit | Mohamed.Thabit@avon.com
|  | Mohamed Hassan | mohamed.hassan@avon.com
|  | Marko Nasef | marko.nasef@avon.com
| Saudi Arabia | Hassan Alsadiq | hassan.alsadiq@avon.com;
|  | Rewaa Mirza | rewaa.mirza@avon.com
|  | Noura AlShuaibi | Noura.AlShuaibi@avon.com
| Morocco | Imane Ettaki | Imane.Ettaki@avon.com
|  | Hanaa Azmi | hanaa.azmi@avon.com
|  | Youssef Houdna | Youssef.Houdna@avon.com

## Draft_Copy (hidden)
CRQ |  | No | ID | Task description | Responsible | START CEST tz | END CEST tz | Duration | Predecesor | Status | Comments |  | Real start | Real end | duration
GOLIVE: 12th of November, start downtime: 2100 CET
Estimates
|  |  |  | Database backup and recovery estimations from Ishan | DB's |  | Restore | Estimated by
[5 empty] | Old | New
|  |  |  | ODS DB | webecep | webeuap
|  |  |  | ODS DB Ukraine | webecep | webeuap
|  |  |  | LINX DB | gmcgcep | gmcgfip
|  |  |  | LINX DB Ukraine | gmcgeep | gmcguap
|  |  |  | chrptcep | chrptcep
|  |  |  | leadsep(EE,LA,LT) | leadsep
|  |  |  | PG(EE,FI,LT, LV) | PG
In scope DB's: ODS, GOMAC, HDS
Out of scope DB: Leads?
|  | 1 |  | Pre-cutover checks / activities |  | 29th Oct | 12th Nov
|  | 1.1 |  | Maintanance page (content to be confirmed and who prepare, when) | Gurvinder Singh
|  | 1.2 |  | Agree prompt on IVR/CTI
|  | 1.3 |  | GO/NOGO for cutover with Business | Gurvinder Singh
|  | 1.4 |  | CRQ for Outage (CHG0062968) | Gurvinder Singh
|  | 1.5 |  | QAP signoff | Attilla Domokos
|  | 1.6 |  | UAT signoff (new PROD) | Mihaly / Attila
|  | 1.7 |  | outage + communication | Gurvinder Singh
|  | 1.8 |  | Global Privacy approval | Anastacia Izmaylova
|  | 1.9 |  | Project Risks approval | Michał Ziółkowski
|  | 1.10 |  | SOX approval | Karolina Przybysz
|  | 1.11 |  | Service Team approval (communication) | Jarosław Żurawski
|  |  |  | Firewall port communication from celerity to MQ in Amsterdam/Corby for concorde applictaion | Gwidon |  |  | Completed |  |  | Need to check with Gwidon if all ports are opened Source: Concorde Database(172.26.180.80) target amslxgi3pmq1.dc.avon.net ( 10.160.140.20) port 1414 cbylxwebepmq1.uk.avon.com (172.20.29.99 ) port 1414
|  | 2 |  | PREPARATIONS / CHECKS / SCRIPTING |  | 2021-10-29 | 2021-10-22
|  | 2.1 |  | Preparation activities
|  | 2.1.1 |  | Check all dblinks inwebeuap, webeuap, gmcgfip, gmcguap and confirm if they need to undergo any changes. | Ivan (webe) (chrptcep), Slawek and Gergo (gmc) Raja (payment gateway)
|  | 2.1.2 |  | Check whether we have got any changes in DDLs we would need to run during cutover (check with Michal for EXT) | Ivan
|  | 2.2 |  | Maintenence pages / prompts / communication
|  | 2.2.1 |  | Check / prepare maintenance page for MAS | Imre Balla --- No Such task
|  | 2.2.2 |  | Check / prepare maintenance page for MAO | Carol
|  | 2.2.3 |  | Check / prepare maintenance page for Avon Grow (EE,FI,) | Jackson / Owen |  |  | 10 mins
|  | 2.2.4 |  | Check / prepare maintenance page for IMB (for all CE2 & UA markets) | Alexandru |  |  | 45 mins
|  | 2.3 |  | Prepare communication for business | Gurvinder Singh
|  | 2.4 |  | Create new release of service-registry-for-ipaas-infra-tf | Zoltan
|  | 2.5 |  | Scripts preparation
|  | 2.5.1 |  | Level 0 backup scripts | Ishan
|  | 2.5.2 |  | WEBECEP (ODS db) clone and upgrade from production | Ishan
|  | 2.5.3 |  | gmcgcep | Gergo
|  | 2.5.4 |  | scripts to install db objects (external tables for ETL users) | Ivan F
|  | 2.5.5 |  | review prod deployment process GI3, AGS classic | Maykon
|  | 2.5.6 |  | setup new deployment script on new env - AGS, GI3 | Maykon / Eduardo
|  | 2.6 |  | new PROD - Environment readiness (incl. Smoke tests) | Vineet
|  | 2.6.1 |  | autosys jobs checked, confirmed, turned on in controlled way | Michal
|  | 2.6.2 |  | Put webe jobs on HOLD before trial cutover | Michal / Miguel
|  | 2.6.3 |  | NAS mounts / NAS folders | Maykon
|  | 2.6.4 |  | webserver config (httpd) | Maykon
|  | 2.6.5 |  | websphere preparations | Maykon
|  | 2.6.6 |  | application deployment | Maykon
|  | 2.6.7 |  | symbolic links creation | Maykon
|  | 2.6.8 |  | teamsite preparation | Anton
|  | 2.6.9 |  | enable config for new prod deployment | Anton
|  | 2.6.10 |  | Check CCA properties in AGS during the login | Anandhi
|  | 2.6.11 |  | content refresh scripts (just for CCA) | Michal
|  | 2.6.12 |  | perl modules instalation | Maykon
|  | 2.6.13 |  | perl scripts validation | Michal
|  | 2.6.14 |  | shell scripts validation | Michal
|  | 2.6.15 |  | autosys setup to new batch servers | Miguel
|  | 2.6.16 |  | import GI3 & AGS3 & AGS classic new certificates to the applications that invokes it | Maykon
|  | 2.6.17 |  | MAO - AGS3 cert | Maykon
|  | 2.6.18 |  | import external weservice certificates to the new AGS and AGS3 env | Maykon
|  | 2.6.19 |  | import external weservice certificates to the new Gi3 | Maykon
|  | 2.6.20 |  | provide the list of all external URLs (otherwise we have P1) - GI3, AGS, AGS3 | Zoli, Pavel, Michal…. All team
|  | 2.6.21 |  | submit the request for external URLs to be added to FireWall | Maykon
|  | 2.7 |  | AGS3 / MAO verification
|  | 2.7.1 |  | AGS3 - deploy of newest version on prod (on QA already deployed) | Andras/Ivan
|  | 2.7.2 |  | Check whether any additonal deployment is required | Zoli
|  | 2.8 |  | Another preparations
|  | 2.8.1 |  | hostfiles | Maykon
|  | 2.8.2 |  | prepare new AKAMAI for AGS classic & AGS3 | Maykon
|  | 2.8.3 |  | create new NetScalers for AGS classic and AGS3 | HCL Network Team
|  | 2.8.4 |  | validate new servers backup - all prod non-data servers | Vineet / backup team
|  | 2.8.5 |  | Open connectivity from MAS PROD env (AWS) to AGS classic endpoint! | Imre Sz
|  | 2.8.6 |  | Check connectivity from MAS PROD env (AWS) to AGS classic endpoint! | Imre Balla |  |  | 15 mins
|  | 2.8.7 |  | resync NAS folders GI3 | Maykon/ imre / Linux team
|  | 2.8.8 |  | Deploy GI3 property files | Anandhi
|  | 2.8.9 |  | Reduce DNS TTL 5 mins | Amit
|  | 2.8.10 |  | Validate DNS TTL | Amit
|  | 2.8.11 |  | SMTP servers to be installed to batch and app servers - Check if it was done | Maykon
|  | 2.8.12 |  | level 0 backup - 2 dbs Friday - webecep and gmcgcep | Ishan
|  | 2.8.13 |  | we need to clear down old archive logs so arch dest does not get full | Ishan
|  | 2.8.14 |  | hostfiles - provide for new users (same as for testing) | Gurvinder Singh
|  | 2.8.15 |  | Constantino, will raise ticket to update ags3 url on fuse end | Constantino
|  | 2.9 |  | Setup Gi3 maint page (AMST) | Martket Content Team / manish / MW team | 2021-10-22 | 2021-10-22
|  | 2.10' |  | ODS - CDW | Michal
MAS eligability feed change
CUTOVER - make sure AMIT is here + Vitaly on call at least
|  | 3 |  | CUTOVER
|  | 3.1 |  | Initial activities
|  | 3.1.1 |  | Maintenance Pages set up |  | 2021-10-12 21:00
|  | 3.1.1.1 |  | GI3 Maintenance pages set up | MW Team
|  | 3.1.1.1.1 |  | Setup Gi3 maint page (AMST) | MW Team |  |  | 30 mins
|  | 3.1.1.1.2 |  | Making the DNS changes - all CE2 & UA markets | Amit |  |  | 30 mins
|  |  |  | Akmai changes - all CE2 & UA markets | Maykon |  |  | 30mins
|  | 3.1.1.1.3 |  | Validate Gi3 maint page | Anandhi |  |  | 15 mins
|  | 3.1.1.2 |  | MAO Maintenance pages set up
ENT-MIDDLEWARE WAS |  | 3.1.1.2.1 |  | MAO - Setup the maint page (for few markets)-Nordics Markets | MW Team
ENT-MIDDLEWARE WAS |  | 3.1.1.2.2 |  | MAO - Setup the maint page (for few markets)-Ukraine Markets | Terraform Team - Kapender / Nirdesh - to be confirmed from Vineet |  |  | 30mins
|  | 3.1.1.2.3 |  | MAO - validate MAO connectivity | tatiana.darkshevich@avon.com
|  | 3.1.1.3 |  | Avon On - disable connections | Sai |  |  | 60 mins
|  | 3.1.1.3.1 |  | Disable single sign on to place orders | Sai
|  | 3.1.1.3.2 |  | Disable single sign on to history of orders / returns | Sai
|  | 3.1.1.3.3 |  | Disable signe sign on to cutomer orders | Sai
|  | 3.1.1.3.4 |  | Disable make a payment from dashboard, from my account page, decision landing page, menu | Sai
|  | 3.1.1.3.5 |  | Disable edit phone number and email from my profile page | Sai
|  | 3.1.1.3.6 |  | Disable single sign on to Avon Office | Sai
|  | 3.1.1.3.7 |  | Disable single sign on to Avon Connect | Sai
|  | 3.1.1.3.8 |  | Disable IMB dashboard | Sai
i |  | 3.1.1.3.9 |  | Disable IMB ordering | Sai
|  | 3.1.1.3.10 |  | Disable single sign on for Avon Grow | Sai
|  | 3.1.1.3.11 |  | Disable self appointment from login page | Sai
|  | 3.1.1.3.12 |  | Potentially include task related to digital | Sai
|  | 3.1.1.4 |  | MAS Maintenance pages set up | Imre Balla | 15 mins
|  | 3.1.1.5 |  | Avon Grow Maintenance pages set up |  |  |  | 10 mins
|  | 3.1.1.5.1 |  | Enable maintenance page | Jackson |  |  | 15 mins
|  | 3.1.1.6 |  | IVR Maintenance pages set up | Laszlo.Somogyi@maintel.co.uk | [5 empty] | Need to check with SME from IVR about steps and time required for change. Need to check if we can keep it up for CE2 markets
|  | 3.1.1.6.1 |  | IVR - activate prompt () | Laszlo.Somogyi@maintel.co.uk | [5 empty] | Need to change voice message mentioning maintenance
|  | 3.1.1.7 |  | FUSE - Not required | kristine.tansengespiritu@avon.com, gwe.service.delivery@avon.com | [5 empty] | Need to confirm
|  | 3.1.1.8 |  | IMB Maintenance pages set up | Alexandru |  |  | 30 mins
|  | 3.1.1.9 |  | SMS Gateway (All 5 CE2 & UA markets) Maintenance pages set up | Pavel Gas |  |  | 5 mins
|  | 3.1.1.10' |  | Payment Gateway - Nordics (Not required In UA) | Priyanka / Raja | [5 empty] | Pavel will confirm the markets on payment gateway
|  | 3.2 |  | PREPARATIONS BEFORE APPS STOP
| Aries Systems | 3.2.1 |  | Turn off order processing | gabor.greba@avon.com |  |  | 30 mins. |  |  | Need to Validate with Attila Gurbi and Team
|  | 3.2.2 |  | Check whether all the invoices are printed | gabor.greba@avon.com
|  | 3.2.3 |  | Disable jobs in ARIES responsible for data refresh | Attila G |  |  | 15 mins. |  | Waiting for reply
| Ukraine | 3.2.1 |  | Turn off order processing | Eugene
|  | 3.2.2 |  | Check whether all the invoices are printed | Albina Kazantseva | [5 empty] | Business Team need to be involved
|  | 3.2.3 |  | Disable jobs in Ukraine responsible for data refresh | Eugene
|  | 3.2.4 |  | Disable Oracle jobs and stop UA Batcher sessions | Eugene
|  | 3.2.5 |  | Stop Replication for MAO HDS | Eugene
|  | 3.2.6 |  | Change NOEL to dummy URL | Laszlo Gecse/BDP/HU <Laszlo.Gecse@avon.com | [5 empty] | Need confirmation if Lazlo will support or someone from him team
|  | 3.2.7 |  | Update NOEL interface control table in CORBY WEBECEP | Michal
|  | 3.3 |  | APPLICATIONS STOP
|  | 3.3.1 |  | stop old gi3 dmgr (all CE2 & UA markets)-Estonia, finland, Latvia, Lithuania, ukraine | MW |  |  | 20mins |  |  | https://cbylxwebewdm1.uk.avon.com:14001/ibm/console/
ESO-OMS-ADMIN |  | 3.3.2 |  | Stop all GOMAC / CE2 & UA markets-Estonia, finland, Latvia, Lithuania, ukraine | OMS Admins |  |  | 10mins |  |  | Gergo will confirm the Admin who will perform the activity
|  | 3.3.3 |  | Stop MAO Email sending Boomi process. Remove EE,LV,LT,FI,UA from PROD APAC -> env variables -> Dynamic Process Properties -> DPP_MAOEmail_marketList | Zoltan |  |  | 5mins
|  | 3.3.4 |  | Stop ARIES SMS sending | Attila G
|  | 3.3.5 |  | Stop Ukrainian sms and email sending (Concorde App server Crontab) | Eugene |  |  | 15mins
|  | 3.3.6 |  | Stop SMS Gateway/SMS Ordering Job | Pavel
|  | 3.4 |  | DB ACTIVITIES
|  | 3.4.1 |  | DATABASE REFRESH | Ishan
ENT-ORACLE |  | 3.4.1.1 |  | Drop DBs? Clear archive filesystem | Ishan
ENT-ORACLE |  | 3.4.1.2 |  | restore database from level 0 backup | Ishan
ENT-ORACLE |  | 3.4.1.2.1 |  | webecep | Ishan, Nakul
|  | 3.4.1.2.2 |  | gmcgcep | Ishan, Nakul
ENT-ORACLE |  | 3.4.1.3 |  | level 1 backup + archive backup + copy | Ishan
ENT-ORACLE |  | 3.4.1.3.1 |  | webecep | Ishan, Nakul
ENT-ORACLE |  | 3.4.1.3.2 |  | gmcgcep | Ishan, Nakul
ENT-ORACLE |  | 3.4.1.3.3 |  | Copy backup | Ishan, Nakul
ENT-ORACLE |  | 3.4.1.4 |  | recover databases | Ishan
ENT-ORACLE |  | 3.4.1.4.1 |  | webecep | Ishan, Nakul
ENT-ORACLE |  | 3.4.1.4.2 |  | gmcgcep | Ishan, Nakul
|  | 3.4.1.5 |  | upgrade databases | Ishan, Nakul
|  | 3.4.1.5.1 |  | webecep | Ishan, Nakul
|  | 3.4.1.5.2 |  | gmcgcep | Ishan, Nakul
|  | 3.4.1.6 |  | Resfresh Data | Ishan, Nakul
|  | 3.4.1.6.1 |  | chrptcep (SK, RS, DE, BA, HR, SI, ME) - NA | Ishan, Nakul
|  | 3.4.1.6.2 |  | Count DB objects - NA | Ivan
|  | 3.4.1.7 |  | Drop Partitions | Ishan, Nakul
|  | 3.4.1.7.1 |  | webecep ( all except CE2 & UA markets) | Ishan, Nakul
|  | 3.4.1.7.2 |  | Run scripts / create DB links - sent via email by Gergo | Ishan, Nakul
|  | 3.4.1.8 |  | Verify the number of data counts - NA | Ivan
|  | 3.4.1.8.1 |  | truncate table monitor.session_login; webecep | Ishan
|  | 3.4.2 |  | SANITY CHECK - each db owner should check if db is accessible | db owners |  |  | 60 min
|  | 3.4.2.1 |  | webecep | Pavel
|  | 3.4.2.3 |  | chrptcep (SK, RS, DE, BA, HR, SI, ME) - NA | tatiana.darkshevich@avon.com
|  | 3.4.3 |  | DDL install db objects (external tables and directory changes) - weberop | Nakul
|  | 3.4 |  | directory changes | Ishan
|  | 3.4.4 |  | DML scripts execution (autojob details) - restoring backuped autosys jobs | Michal
|  | 3.5 |  | CHECK/ENABLE CONNECTIVITY |  | 2021-10-22 00:10
|  | 3.5.1 |  | Setup connections (dblinks) - collect links and recreate
|  | 3.5.1.1 |  | ARIES | Tibor / Atila G
|  | 3.5.1.2 |  | Ukraine Concorde Application | Ishan, Nakul
|  | 3.5.1.2 |  | webe | Ishan, Nakul
|  | 3.5.1.3 |  | HDS | Ishan, Nakul
|  | 3.5.1.5 |  | CBC PG | Ishan, Nakul | [5 empty] | Need to check with Pavel Gas
|  | 3.6 |  | APPLICATION ACTIVITIES TO BE DONE DURING DB ACTIVITIES |  | 2021-10-22 00:10 | [6 empty] | 700 | 11.6667
DCO-SPO-SERVER-SUPT-BR |  | 3.6.1 |  | change all CE2 & UA markets to the new ip on /etc/hosts on dlslxpsmsgwap1 | Maykon |  |  | 10mins
|  | 3.6.2 |  | Adjust MQ channels | Maykon / Middleware team | [5 empty] | Need to check if any MQ channel is available
|  | 3.6.3 | 3.5.2.2 | MQ host name changes ARIES | Attila / Tibor | [5 empty] | " ""server"": ""amslxgi3pmq1.dc.avon.net(1414)"", ""channel"": ""GOMAC.SERVER.01"", ""queuemanager"": ""CBYPWEBE"""
|  | 3.6.4 |  | MQ host name changes to Ukraine Concorde Application | Eugene |  |  | 10mins |  |  | " ""server"": ""amslxgi3pmq1.dc.avon.net(1414)"", ""channel"": ""GOMAC.SERVER.01"", ""queuemanager"": ""CBYPWEBE"""
|  | 3.6.5 |  | Point old CBC PG to new MQ | Maykon/Raja | [5 empty] | Need to check if any MQ channel is available
|  | 3.6.6 |  | Point ARIES PG interface to new MQ | Eugene | [5 empty] | Need to check if any MQ channel is available for Payment Gateway
|  | 3.6.7 |  | AWS changes by HCL DevOps | HCL DevOPs (Nirdesh / Rakesh / Kapender) / Zoli |  |  | 30mins |  |  | Deploy master branch of service-registry-for-ipaas-infra-tf to PROD via Jenkins (https://jenkins.devops-prod.aws.avon.com/job/API GW/job/API GW Prod/job/Service Registry for iPaaS/job/Service Registry infra/) Add new entries in Secrets Manager (AWS account #121642321945). Copy serviceReg/WEBECEP with its secret values to serviceReg/WEBEUAP
created |  | 3.7 |  | SWITCH TO NEW DATABASES |  | 2021-10-22 05:40 | 2021-10-22 05:40 |  | 3.4
|  | 3.7.1 |  | supportal new db configuration | Michal
|  | 3.7.2 |  | ezBrochure change point CE markets to new DB (XML config change) | Michal
|  | 3.7.3 |  | CRM - redirect to new LINX DB | Citrix team | [5 empty] | Need to check with Attila Gurbi /Tibor
|  | 3.7.4 |  | Redirect Concord's SOAP Linx connections | Eugene |  |  | 10mins |  |  | Gergo will send details to Eugene over email
|  |  |  | Redirect the new DB link for Ukraine from concorde to Linx | DBA Team | [5 empty] | Need to check firewall ports for setting up redirection; need to add in pre-requisites section
|  |  |  | fix Report users in Dallas batch servers | Maykon | [5 empty] | The Report users was not well created in the linux side and we need a CRQ to have them fixed to avoid a major issue in the next releases. The users have diferente uuid/gid in the servers below. dlslxgi3pbt1.dc.avon.net dlslxgi3pbt2.dc.avon.net
|  | 3.8 |  | Setup connectivity between future PROD and satellite applications |  | 2021-10-23 05:55 | 2021-10-23 06:55 |  | 3.6
|  | 3.8.1 |  | Avon Grow - Change Avon Grow AGS service endpoint to new one (details) | Jackson |  |  | 15 mins | 3.5.4;3.4
|  | 3.8.2 |  | MAS - Switch to new AGS URLs (detailed plan by Imre Balla) | Imre Balla |  |  | 50 mins
|  | 3.8.3 |  | MAO
|  | 3.8.3.1 |  | AGS3 domain update : myavon-ws-eu-ams.prod.avon.com | Tamas Szeremy
|  | 3.8.3.2 |  | Validation of MAO connectivity | Tanaya
|  | 3.8.4 |  | IMB - Switch to new AGS URLs | alexandru |  |  | 30 mins
|  | 3.8.5 |  | Avon On | Sai
|  | 3.8.5.1 |  | Switch to new AGS URLs
|  | 3.8.6 |  | IVR | Laszlo.Somogyi@maintel.co.uk
|  | 3.8.6.1 |  | Switch all endpoints for CE2 & UA markets - switch endpoints | Laszlo.Somogyi@maintel.co.uk
|  | 3.8.7 |  | Change AGS Classis SMS endpoint - ARIES | Attila
|  | 3.8.8 |  | FUSE | gwe.service.delivery@avon.com, Kristine Tan Seng-Espiritu/MNL/PH <kristine.tansengespiritu@avon.com>
|  | 3.8.8.1 |  | local digital team update AGS3 fuse sso in magnolia (MAO) | Digital Team
|  | 3.8.8.2 |  | local digital team update AGS3 fuse sso in GI3 | Anandhi
|  | 3.8.8.3 |  | local digital team update AGS3 fuse sso in MAS | Imre Balla - By Imre's team |  |  | 10 mins
|  | 3.8.9 |  | Change Data Integration Services to New ODS | rain.zhen@avon.com
|  | 3.8.10 |  | Eloqua config needs to be updated to use the proper AGS/AGS3 domain | Dragos Ene | [6 empty] | myavon-ws-eu-dls.prod.avon.com
|  | 3.8.11 |  | SMS Gateway
|  | 3.8.11.1 |  | Change AGS classic endpoints
|  | 3.8.12 |  | PRP - CE2 & UA | Doru
|  | 3.8.13 |  | ARIES
|  | 3.8.13.1 |  | Change dblink/config for Tibi's engine | Attila/Tibor
|  | 3.8.14 |  | Teamsite
|  | 3.8.14.1 |  | Change TS config | Anton
|  | 3.9 |  | ADDITIONAL CHECKS/CONNECTIVITY |  | 2021-11-12 | 2021-11-12 |  | 3.7
ENT-AUTOSYS |  | 3.9.1 |  | DML scripts execution (autojob details) | Michal
|  | 3.9.2 |  | Run selected autosys jobs manually from cmd line and verify they are not failing | Michal
created |  | 3.10' |  | STARTING APPS |  | 2021-11-12 | 2021-11-12 |  | 3.4, 3.5
|  | 3.10.1 |  | Run scripts / start GOMAC | Slawek's team
|  | 3.10.2 |  | start GI3 apps (CE2 & UA markets) (Amst) | MW Team
|  | 3.10.3 |  | Start MAO Email sending Boomi process | Zoltan
|  | 3.10.4 |  | Start SMS Gateway/SMS Ordering Job | Pavel
|  | 3.10.5 |  | ripple restart AGS3 MyAvon Cluster | MW
|  | 3.10.6 |  | ripple restart AGS-AMS Cluster | MW
|  | 3.10.7 |  | Ripple restart CPC PG Corby (WAS8, WAS8.5) | MW
On 28.09 we finished here |  | 3.11 |  | SMOKE TESTS |  | 2021-11-12 | 2021-11-12 |  | 3.6,3.7
|  | 3.11.1 |  | smoke tests MAO including reports | Tanaya
|  | 3.11.2 |  | smoke tests GI3/CCA | Anandhi
|  | 3.11.3 |  | Smoke test AGS3 | Lorand
|  | 3.11.4 |  | smoke tests AGS classic | Shankar
|  | 3.11.5 |  | smoke tests LINX | LINX Team
|  | 3.11.6 |  | ARIES? | Attila
|  | 3.11.7 |  | Smoke test Payment Gateway (partial) | Priyanka G
|  | 3.11.8 |  | NOEL - Noel: AGS3 domain update : myavon-ws-eu-ams.prod.avon.com | Laszlo G
created |  | 3.12 |  | Enable autosys jobs |  |  |  |  | 3.8
ENT-AUTOSYS |  | 3.12.1 |  | Put new Dallas/Corby autosys jobs back online. | Miguel
ENT-AUTOSYS |  | 3.12.2 |  | Check for any job failures - AUTO_JOB_DETL, autsys log files | Michal
|  | 3.12.3 |  | we need to clear down old archive logs so arch dest does not get full | Ishan
|  | 3.13 |  | BUSINESS TESTING (with maintenance pages on) |  |  |  |  | 3.10
|  | 3.13.1 |  | GI3
|  | 3.13.1.1 |  | Estonia
|  | 3.13.1.2 |  | Finland
|  | 3.13.1.3 |  | Latvia
|  | 3.13.1.4 |  | Lithuania
|  | 3.13.1.5 |  | Ukraine
|  | 3.13.2 |  | MAS
|  | 3.13.2.1 |  | Serbia (SER)
|  | 3.13.2.2 |  | Slovakia
|  | 3.13.3 |  | MAO
|  | 3.13.3.1 |  | Estonia
|  | 3.13.3.2 |  | Finland
|  | 3.13.3.3 |  | Latvia
|  | 3.13.3.4 |  | Lithuania
|  | 3.13.3.5 |  | Ukraine
|  | 3.13.4 |  | GROW -can be tested when maint page is lifted
|  | 3.13.4.1 |  | Estonia
|  | 3.13.4.2 |  | Finland
|  | 3.13.4.3 |  | Latvia
|  | 3.13.4.4 |  | Lithuania
|  | 3.13.4.5 |  | Ukraine
|  | 3.13.5 |  | Avon ON -can be tested when maint page is lifted
|  | 3.13.5.1 |  | Estonia
|  | 3.13.5.2 |  | Finland
|  | 3.13.5.3 |  | Latvia
|  | 3.13.5.4 |  | Lithuania
|  | 3.13.5.5 |  | Ukraine
|  | 3.13.6 |  | IMB NOT UNTIL MAINT PAGE LIFTED
|  | 3.13.6.1 |  | Estonia
|  | 3.13.6.2 |  | Finland
|  | 3.13.6.3 |  | Latvia
|  | 3.13.6.4 |  | Lithuania
|  | 3.13.6.5 |  | Ukraine
|  | 3.13.7 |  | IVR
|  | 3.13.7.1 |  | Estonia
|  | 3.13.7.2 |  | Finland
|  | 3.13.7.3 |  | Latvia
|  | 3.13.7.4 |  | Lithuania
|  | 3.13.8 |  | Leads -
|  | 3.13.9 |  | Old Payment Gateway
|  | 3.13.9.1 |  | Germany (DE)
|  | 3.13.9.2 |  | Slovakia
|  | 3.13.10' |  | NOEL
|  | 3.13.10.1 |  | Estonia
|  | 3.13.10.2 |  | Finland
|  | 3.13.10.3 |  | Latvia
|  | 3.13.10.4 |  | Lithuania
|  | 3.13.10.5 |  | Ukraine
|  | 3.13.11 |  | FUSE (integration check)
|  | 3.13.11.1 |  | Estonia
|  | 3.13.11.2 |  | Finland
|  | 3.13.11.3 |  | Latvia
|  | 3.13.11.4 |  | Lithuania
|  | 3.13.11.5 |  | Ukraine
|  | 3.13.12 |  | SMS gateway
|  | 3.13.12.1 |  | Estonia
|  | 3.13.12.2 |  | Finland
|  | 3.13.12.3 |  | Latvia
|  | 3.13.12.4 |  | Lithuania
|  | 3.13.12.5 |  | Ukraine
|  | 3.13.13 |  | PRP
|  | 3.14 |  | GO / NO GO DECISION |  | 2021-11-13 | 2021-11-13
|  | 3.14.1 |  | Patch Deployment for CBC PG in Corby (WAS8) | MW
|  | 3.15 |  | LIFTING / ENABLING
|  | 3.15.1 |  | Remove maintenence pages
|  | 3.15.1.1 |  | MAO - remove maintenance page
|  | 3.15.1.1.1 |  | MAO - remove maintenance page | MW team
|  | 3.15.1.1.2 |  | MAO - remove maintenance page | Terrafom team
|  | 3.15.1.1.3 |  | Validation of removal of maintenance page | Tanaya
|  | 3.15.1.2 |  | MAS - remove maintenance page | Imre Balla |  |  | 15 mins
|  | 3.15.1.3 |  | Avon Grow - remove maintenance page | jackson.yan@avon.com |  |  | 10 mins
|  | 3.15.1.4 |  | IMB - remove maintenance page | Alexandru |  |  | 45 mins
|  | 3.15.1.5 |  | Enable Avon On |  |  |  | 45 mins
|  | 3.15.1.5.1 |  | Enable single sign on to place orders | Sai
|  | 3.15.1.5.2 |  | Enable single sign on to history of orders / returns | Sai
|  | 3.15.1.5.3 |  | Enable signe sign on to cutomer orders | Sai
|  | 3.15.1.5.4 |  | Enable make a payment from dashboard, from my account page, decision landing page, menu | Sai
|  | 3.15.1.5.5 |  | Enable edit phone number and email from my profile page | Sai
|  | 3.15.1.5.6 |  | Enable single sign on to Avon Office | Sai
|  | 3.15.1.5.7 |  | Enable single sign on to Avon Connect | Sai
|  | 3.15.1.5.8 |  | Enable IMB dashboard | Sai
|  | 3.15.1.5.9 |  | Enable IMB ordering | Sai
|  | 3.15.1.5.10 |  | Enable single sign on for Avon Grow | Sai
|  | 3.15.1.5.11 |  | Enable self appointment from login page | Sai
|  | 3.15.1.5.12 |  | Digital recruitment links - enable a from component | Sai
|  | 3.15.1.6 |  | FUSE - Avon Connect | Kristine Tan Seng-Espiritu/MNL/PH <kristine.tansengespiritu@avon.com>, gwe.service.delivery@avon.com
|  | 3.15.1.7 |  | PRP | Doru
|  | 3.15.1.8 |  | OSA Recruitmnet Pages
|  | 3.15.1.9 |  | Start ARIES SMS process | Attila Gurbi
|  | 3.15.1.10 |  | Bill Test Orders | Markets
|  | 3.15.1.11 |  | Change DB links for Germany in PL Axapta to new LINX | Marek
|  | 3.15.1.12 |  | NOEL
|  | 3.15.1.12.1 |  | Change NOEL endpoint from Corby to Amsterdam - AGS3 | Laszlo G
|  | 3.16 |  | Smoke Tests - Final Business Checks (after maintenance pages lifted) |  | 2021-10-23 16:00 | 2021-10-23 16:00
|  | 3.16.1 |  | GI3
|  | 3.16.1.1 |  | Estonia | Adrian Vlad/Natalia Slavova
|  | 3.16.1.2 |  | Finland | Gordan Vargovic/Nikola Kljajic
|  | 3.16.1.3 |  | Latvia | Gordan Vargovic/Nikola Kljajic
|  | 3.16.1.4 |  | Lithuania | Tobias Rauscher
|  | 3.16.1.5 |  | Ukraine | Adrian Vlad/Natalia Slavova
|  | 3.16.2 |  | MAS
|  | 3.16.2.1 |  | Estonia | LazarVeljanovic/Gordan Vargovic/Nikola Kljajic
|  | 3.16.2.2 |  | Finland | Veronika Matika/Jan Šťástka
|  | 3.16.2.3 |  | Latvia
|  | 3.16.2.4 |  | Lithuania
|  | 3.16.2.5 |  | Ukraine
|  | 3.16.3 |  | MAO
|  | 3.16.3.1 |  | Estonia | Gordan Vargovic/Nikola Kljajic
|  | 3.16.3.2 |  | Finland | Gordan Vargovic/Nikola Kljajic
|  | 3.16.3.3 |  | Latvia | Tobias Rauscher
|  | 3.16.3.4 |  | Lithuania | Gordan Vargovic / Darko Pupovac
|  | 3.16.3.5 |  | Ukraine | LazarVeljanovic/Gordan Vargovic/Nikola Kljajic
|  | 3.16.4 |  | GROW -can be tested when maint page is lifted
|  | 3.16.4.1 |  | Estonia | Gordan Vargovic/Nikola Kljajic
|  | 3.16.4.2 |  | Finland | Gordan Vargovic/Nikola Kljajic
|  | 3.16.4.3 |  | Latvia | Adrian Vlad/Natalia Slavova
|  | 3.16.4.4 |  | Lithuania | Adrian Vlad/Vladislav Ivancenco
|  | 3.16.4.5 |  | Ukraine | LazarVeljanovic/Gordan Vargovic/Nikola Kljajic
|  | 3.16.5 |  | Avon ON -can be tested when maint page is lifted
|  | 3.16.5.1 |  | Estonia | Adrian Vlad/Natalia Slavova
|  | 3.16.5.2 |  | Finland | Gordan Vargovic/Nikola Kljajic
|  | 3.16.5.3 |  | Latvia | Gordan Vargovic/Nikola Kljajic
|  | 3.16.5.4 |  | Lithuania | Tobias Rauscher
|  | 3.16.5.5 |  | Ukraine | Adrian Vlad/Natalia Slavova
|  | 3.16.6 |  | IMB NOT UNTIL MAINT PAGE LIFTED
|  | 3.16.6.1 |  | Estonia | Adrian Vlad/Natalia Slavova
|  | 3.16.6.2 |  | Finland | Gordan Vargovic/Nikola Kljajic
|  | 3.16.6.3 |  | Latvia | Gordan Vargovic/Nikola Kljajic
|  | 3.16.6.4 |  | Lithuania | Tobias Rauscher
|  | 3.16.6.5 |  | Ukraine | Adrian Vlad/Natalia Slavova
|  | 3.16.7 |  | IVR
|  | 3.16.7.1 |  | Estonia | Adrian Vlad/Natalia Slavova
|  | 3.16.7.2 |  | Finland | Gordan Vargovic/Nikola Kljajic
|  | 3.16.7.3 |  | Latvia | Gordan Vargovic/Nikola Kljajic
|  | 3.16.7.4 |  | Lithuania | Tobias Rauscher
|  | 3.16.7.5 |  | Ukraine | Adrian Vlad/Natalia Slavova
|  | 3.16.8 |  | Leads - Serbia | LazarVeljanovic/Gordan Vargovic/Nikola Kljajic
|  | 3.16.9 |  | Old Payment Gateway
|  | 3.16.9.1 |  | Estonia
|  | 3.16.9.2 |  | Finland
|  | 3.16.9.3 |  | Latvia
|  | 3.16.9.4 |  | Lithuania | Tobias Rauscher
|  | 3.16.9.5 |  | Ukraine | Veronika Matika/Jan Šťástka
|  | 3.16.10' |  | NOEL
|  | 3.16.10.1 |  | Estonia | Adrian Vlad/Natalia Slavova
|  | 3.16.10.2 |  | Finland | Gordan Vargovic/Nikola Kljajic
|  | 3.16.10.3 |  | Latvia | Gordan Vargovic/Nikola Kljajic
|  | 3.16.10.4 |  | Lithuania | Tobias Rauscher
|  | 3.16.10.5 |  | Ukraine | Adrian Vlad/Natalia Slavova
|  | 3.16.11 |  | FUSE (integration check)
|  | 3.16.11.1 |  | Estonia | Adrian Vlad/Natalia Slavova
|  | 3.16.11.2 |  | Finland | Gordan Vargovic/Nikola Kljajic
|  | 3.16.11.3 |  | Latvia | Gordan Vargovic/Nikola Kljajic
|  | 3.16.11.4 |  | Lithuania | Tobias Rauscher
|  | 3.16.11.5 |  | Ukraine | Adrian Vlad/Natalia Slavova
|  | 3.16.12 |  | SMS gateway
|  | 3.16.12.1 |  | Estonia | Adrian Vlad/Natalia Slavova
|  | 3.16.12.2 |  | Finland | Gordan Vargovic/Nikola Kljajic
|  | 3.16.12.3 |  | Latvia | Gordan Vargovic/Nikola Kljajic
|  | 3.16.12.4 |  | Lithuania | Tobias Rauscher
|  | 3.16.12.5 |  | Ukraine | Adrian Vlad/Natalia Slavova
|  | 4 |  | END OF THE OUTAGE
|  | 5 |  | Mass Billing?
|  | 6 |  | Post Outage
|  | 6.1 |  | Disable Kafka feed, send only to AMST | Rain
Note on L95: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Gwidon what's the approach for this. Will the list of users for admin-rights to this file will come from Project? If so then we need a task to collect those and HCL to execute it

## Contacts
System | Name | Mail | Group | Mobile | Comments
PM | Gurvinder Singh Loh | gurvinder.loh@avon.com | n/a | +91 9988883360
PM | Monika Zajączkowska | monika.zajaczkowska@avon.com | n/a | +48789222555
GI3 | Pavel Gas | pavel.gas@avon.com | n/a | +420602655005
GI3 | Ivan Ferrer | ivan.ferrer@avon.cpm | n/a | +52 5538769324
GI3 | Michal Elias | michal.elias@avon.com |  | +420 732 543 355 | +420 257 089 277
GI3 DEV | Anandhi C | anandhi.chinnarasu@avon.com | GWE-PRJ-MGMT | +91 9176033289
LINX / GOMAC | Gergo Spielmann | gergo.spielmann@avon.com | ESO-OMS-ADMIN | +36308842023
LINX / GOMAC | Haziq Khalil | haziq.khalil@avon.com | ESO-OMS-ADMIN | +60 147209257
AGS3 | Zoltan Kovacs | zoltan.kovacs@avon.com | n/a | +36 30 34 34 311 | ping on mobile before task
Tibor for Boomi changes
Lorand Fazekas for AGS3
AGS | Raja | raja.subramaniam@avon.com |  | +91 9361101135 | +91 9943544357
ODS | Rain Zhen | rain.zhen@avon.com |  | 86 13720226848
Teamsite | Anoton Koptelov | anton.koptelov@avon.com |  | +79161722706 | not needed task
MAS | Akos Tamas Imre Balla/ Kinga Lovasz | levente.kiraly@avon.com imre.balla@avon.com | MY-AVON-STORE-APSUPT-GLOBAL | +36 20 9587884
IMB | Alexandru Darabam | alexandru.daraban@interactively.eu |  | 0040761342301
Avon On | Sai Chadalapaka | Sai.Chadalapaka@avon.com | GWE-DEVELOPERS | +44 7448291222 | Not available in signature
NOEL | Jozsef Bodnar | jozsef.bodnar@avon.com | ENT-INTEGRATION-SERVICES | 36309313731
Autosys jobs | Miguel Poma | miguel.poma@avon.com | ENT-AUTOSYS | 914-935-2512
DB activities | Imre Szabo Ishan Malik Nakul Chopra | imre.szabo@avon.com ishan.malik@hcl.com; ishan.malik@avon.com nakul.chopra@avon.com | ENT-ORACLE | +36 28 530 000/2130 +91 9896510152 +91 8588897842
HCL Middleware Team | Sweta Sinha | sweta-s@hcl.com | ENT-MIDDLEWARE WAS | +91 C78527826949
HCL Network Team | Amit Kumar | amitkum-ka@hcl.com | ENT-Networkdata | mobile no/ Whatsapp is +918809562513
Maykon | Maykon Salvi | maykon.salvi@avon.com | DCO-SPO-SERVER-SUPT-BR | +55 (19) 9 8818-4532 +55 11 5546-8694
MAO | Ying Kan | ying.kan@avon,com | n/a | +36-70-3103123
GROW | Owen Wan Jackson | owen.wan@avon.com jackson.yan@avon.com | GWE-APP-SPT | +86 15997427627 +86 15207109989
PRP | Doru
MAB
FUSE | Arvind - +447448569167 (primary oncall) Zack - +60172380019 (secondary oncall) Kristine - +639175831057 | Arvind Kumar Eswaran/Infosys/Consultant <arvindkumar.eswaran@avon.com>; Zack Lee/Other/Consultant <zack.lee@avon.com>; Kristine Tan Seng-Espiritu/MNL/PH; GWE Service Delivery <gwe.service.delivery@avon.com> | n/a | +34 639 77 22 39
IVR Other | Laszlo Somogyi | Laszlo.Somogyi@maintel.co.uk
LINX / GOMAC Arch | Tamas Csiba | tamas.csiba@avon.com |  | 36305526287
HCL DBA | DBA on duty 24/7
Network | Vitaliy Krikun | vitaliy.krikun@avon.com |  | 34902540
Linuxv- Siddarth Verma |  |  | ENT-LINUX |  | in case we need support from your team we will reach you
Security |  |  | ENT-NETWORK SECURITY |  | in case we need support from your team we will reach you
FUSE (Backup) | Constantino |  | n/a | +34 639 77 22 39
Eduardo
| Dragos Ene | dragos.ene@avon.com |  | +40755260638
Business testers
Svitlana Melnyk | svitlana.melnyk@avon.com | -
Janis Gureckis | janis.gureckis@avon.com | -
Renars Paukstello | renars.paukstello@avon.com
Attilla Domokos | attila.domokos@avon.com
Mihaly Teleki | mihaly.teleki@avon.com
Attila Fiel | attila.fiel@avon.com | +36306172850
Anastacia Izmaylova | anastacia.izmaylova@avon.com
Michał Ziółkowski | michal.ziolkowski@avon.com
Karolina Przybysz | karolina.okrojek@avon.com | 789200080
Jarosław Żurawski | jaroslaw.zurawski@avon.com
Oleksandr Ovdiy
Oksana Shulga | oksana.shulga@avon.com
Oksana Davydova | oksana.davydova@avon.com; | +380999269902
Oksana Antonuk Promotion | oksana.antonuk.promotion@avon.com
| eduardo.cervetto@avon.com | +54 (9 11) 4416-2250

## TimeZone
CET | UA | EE | LT | LA | FI | IST
21:00 | 22:00 | 22:00 | 22:00 | 22:00 | 22:00 | 25:30
22:00 | 23:00 | 23:00 | 23:00 | 23:00 | 23:00 | 26:30
23:00 | 24:00 | 24:00 | 24:00 | 24:00 | 24:00 | 27:30
24:00 | 25:00 | 25:00 | 25:00 | 25:00 | 25:00 | 28:30
25:00 | 26:00 | 26:00 | 26:00 | 26:00 | 26:00 | 29:30
26:00 | 27:00 | 27:00 | 27:00 | 27:00 | 27:00 | 30:30
27:00 | 28:00 | 28:00 | 28:00 | 28:00 | 28:00 | 31:30
28:00 | 29:00 | 29:00 | 29:00 | 29:00 | 29:00 | 32:30
29:00 | 30:00 | 30:00 | 30:00 | 30:00 | 30:00 | 33:30
30:00 | 31:00 | 31:00 | 31:00 | 31:00 | 31:00 | 34:30
31:00 | 32:00 | 32:00 | 32:00 | 32:00 | 32:00 | 35:30
32:00 | 33:00 | 33:00 | 33:00 | 33:00 | 33:00 | 36:30
33:00 | 34:00 | 34:00 | 34:00 | 34:00 | 34:00 | 37:30
34:00 | 35:00 | 35:00 | 35:00 | 35:00 | 35:00 | 38:30
35:00 | 36:00 | 36:00 | 36:00 | 36:00 | 36:00 | 39:30
36:00 | 37:00 | 37:00 | 37:00 | 37:00 | 37:00 | 40:30
37:00 | 38:00 | 38:00 | 38:00 | 38:00 | 38:00 | 41:30
38:00 | 39:00 | 39:00 | 39:00 | 39:00 | 39:00 | 42:30
39:00 | 40:00 | 40:00 | 40:00 | 40:00 | 40:00 | 43:30
40:00 | 41:00 | 41:00 | 41:00 | 41:00 | 41:00 | 44:30
41:00 | 42:00 | 42:00 | 42:00 | 42:00 | 42:00 | 45:30
42:00 | 43:00 | 43:00 | 43:00 | 43:00 | 43:00 | 46:30
43:00 | 44:00 | 44:00 | 44:00 | 44:00 | 44:00 | 47:30
44:00 | 45:00 | 45:00 | 45:00 | 45:00 | 45:00 | 48:30
45:00 | 46:00 | 46:00 | 46:00 | 46:00 | 46:00 | 49:30
46:00 | 47:00 | 47:00 | 47:00 | 47:00 | 47:00 | 50:30
47:00 | 48:00 | 48:00 | 48:00 | 48:00 | 48:00 | 51:30
48:00 | 49:00 | 49:00 | 49:00 | 49:00 | 49:00 | 52:30

## Hostfiles
10.160.0.37 rep.avon.fi | Databases used
10.160.0.37 www.avon.ee | Markets | MAB | ODS DB | LINX DB | chrptcep | leadsep | PG | webeen2p
10.160.0.37 www.avon.com.ua | Estonia |  | webecep | gmcgcep | Yes | Yes | webepgp
10.160.0.37 www.avon.lv | Finland |  | webecep | gmcgcep | Yes |  | webepgp
10.160.0.37 rep.avon.lt | Latvia |  | webecep | gmcgcep | Yes | Yes | webepgp
10.240.26.106 avon.fi # web3 | Lithuania |  | webecep | gmcgcep | Yes | Yes | webepgp
10.240.26.106 www.avon.fi # web3 | Ukraine |  | webecep | gmcgeep | Yes
10.240.26.106 avon.lt # web3
10.240.26.106 www.avon.lt # web3 | [8 empty] | Old one: cbylxwebeeupdbc2.uk.avon.com/1526 CHRPTCEP
10.240.26.106 avon.lv # web3 | [8 empty] | New one: amslxgi3eupdb1.dc.avon.net/ 1521 chrptcep
10.240.26.106 my.avon.lv # web3
10.240.26.106 avon.ee # web3
10.240.26.106 my.avon.ee # web3
10.240.26.106 avon.ua # web3
10.240.26.106 my.avon.ua # web3
134.65.41.151 office.avon.lt
134.65.41.151 office.avon.lv
134.65.41.151 office.avon.ee
134.65.41.151 office.avon.fi

## Server Backup
Sr. No | List of servers
1 | amslxgi3pdmgr1.dc.avon.net
2 | amslxags3pdmgr1.dc.avon.net
3 | amslxgi3pw1.dc.avon.net
4 | amslxgi3pw2.dc.avon.net
5 | amslxgi3pap1.dc.avon.net
6 | amslxgi3pap2.dc.avon.net
7 | amslxgi3pap3.dc.avon.net
8 | amslxgi3pbt1.dc.avon.net
9 | amslxgi3ptsr1.dc.avon.net
10 | amslxags3pap1.dc.avon.net
11 | amslxags3pap2.dc.avon.net
12 | amslxags3pap3.dc.avon.net
13 | amslxags3pap4.dc.avon.net
14 | amslxpagssolr1.dc.avon.net
15 | amslxpagssolr2.dc.avon.net
16 | amslxpagssolr3.dc.avon.net
17 | amslxags3pw1.dc.avon.net
18 | amslxags3pw2.dc.avon.net

## Rollback Plan
No | Task description | Responsible | START CET timezone | End CET TZ | Duration | Predecesor | Status | Comments
BACKOUT PLAN
5 | Backout plan |  | 2021-10-23 19:20 | 2021-10-24 07:20
5.1 | Preps before we stop apps on new |  | 16.10.2021 16:30:00 | 16.10.2021 17:00:00 | 30 mins
5.1.1 | Get data counts on AMS db | Ivan | 16.10.2021 16:30:00 | 16.10.2021 17:00:00 | 30 mins
5.1.2 | Get data counts on AMS db (including custtable) |  | 16.10.2021 16:30:00 | 16.10.2021 17:00:00 | 30 mins
5.1.3 | If data counts shows differences than |  | 16.10.2021 16:30:00 | 16.10.2021 17:00:00 | 30 mins
5.1.4 | Recovery orders to old database (CBY) |  | 16.10.2021 16:30:00 | 16.10.2021 17:00:00 | 30 mins
5.1 | Stopping applications |  | 2021-10-23 19:20 | 2021-10-23 20:05 | 45 mins | 5.1
5.1.1 | Stop all new GOMAC servers + LINX | Gergo |  |  | 45 mins
5.1.2 | Stop MAO Email sending Boomi process | Tibor Kepecs |  |  | 5mins |  |  | Stop MAO Email sending Boomi process. Remove EE,LV,LT,FI,UA from PROD APAC -> env variables -> Dynamic Process Properties -> DPP_MAOEmail_marketList
5.1.3 | Remove DB's from restricted mode (only for DBA's) | Ishan
5.1.4 | webecep | Ishan |  |  | 10 mins
5.1.5 | gmcgcep - CE2 | Ishan
5.1.6 | gmcgeep- Ukraine | Ishan
5.1.7 | Put DB's in restricted mode (only for DBA's)
5.1.8 | webeuap | Ishan
5.1.9 | gmcgfip | Ishan
5.1.10 | gmcguap | Ishan
5.2 | Tasks before we switch apps to old db and endpoints |  | 2021-10-23 20:05 | 2021-10-23 21:05 | 1 h | 5.2
5.2.1 | webecep | Ivan Ferrer |  |  | 10 mins
5.2.1.1 | gmcgcep | Gabor Pabert
5.2.1.2 | gmcgeep | Oksana
5.2.1.3 | chrptcep | Tanya |  |  | 5 mins
5.2.1.4 | leadsep
5.2.1.5 | PG | Priyanka Chopra
5.2.2 | Drop the DB link (WEBE_CE.WORLD) - NA | Ishan |  |  | 5 mins |  |  | Pending DB link name from Ishan
5.2.3 | Change CE to the old ip on /etc/hosts on dlslxpsmsgwap1 | Maykon |  |  | 10 mins
5.2.4 | point concorde back to old MQ QMGR in CBY | Eugene |  |  | 30 mins
5.2.5 | Turn on order processing | Eugene
5.2.6 | Enable jobs in Ukraine responsible for data refresh | Eugene
5.2.7 | Enable Oracle jobs and stop UA Batcher sessions | Eugene
5.2.8 | Start Replication for MAO HDS | Eugene
5.2.9 | MQ host name changes Concord | Eugene
5.2.10 | PDF reports endpoints in Concord (validated by Eugene) | Eugene
5.2.11 | Change dblink/config for Tibi's engine - UA | Eugene
5.2.12 | Enable Concord jobs | Eugene
5.3 | Avon Grow
5.3.1 | Change Avon Grow front end to old AGS classic end point | Owen |  |  | 1 h
5.3.2 | Change AGS3 endpoint for Fuse / Avon Connect | Owen
5.3.3 | Change AGS3 endpoint for Avon Office (MAO) | Owen
5.3.2 | MAS - Switch to old AGS URLs (detailed plan by Imre Balla) | Imre/Akos Tamas |  |  | 1 h
5.3.2.1 | local digital team update AGS3 fuse sso in MAS | Imre Balla
5.3.3 | MAO
5.3.3.1 | Switch to the old AGS3 endpoint | Tamas Szeremy |  |  | 1 h |  |  | To confirm the resource
5.3.3.2 | Validation of MAO connectivity with AGS3 | tatiana.darkshevich@avon.com |  |  | 30 mins
5.3.4 | NOEL - Noel: AGS3 domain update : old URL | Laszlo Gecse |  |  | 30 mins
5.3.5 | IMB - Switch to old AGS URLs (change endpoints) | Alexandru |  |  | 30 mins |  |  | Need old URLs here
5.3.6 | AWS changed by HCL DevOps | DevOps Team / Nirdesh / Kapender |  |  | 1 h |  |  | To be confirmed from Zoltan to share the info Talk to Tamas for implemention plan
5.3.7 | Avon On - Switch to old URLs | Sai |  |  | 1 h
5.3.8 | FUSE - change URL to enable access |  |  |  | 1 h |  |  | Michal to suggest
5.3.8.1 | local digital team update AGS3 fuse sso in UA (MAO) | Oksana | [5 empty] | markets
5.3.8.2 | local digital team update AGS3 fuse sso in CE2 (MAO) | [6 empty] | Local business team
5.3.9 | ARIES -
5.3.9.1 | MQ host name changes Concord | Tibor |  |  | 5 mins
5.3.9.2 | AGS Endpoint | Tibor |  |  | 5 mins
5.3.9.3 | DB Links verification | Tibor |  |  | 5 mins
Need to discuss with testers
5.3.10 | SMS Gateway- Change AGS classic endpoints to the old ones | Pavel |  |  | 5 mins
5.3.11 | Teamsite -Change TeamSite config | Anton |  |  | 60 mins
5.3.12 | IVR to change back
5.3.13 | Personal Recruitment Pages CE2 & Ukraine | Doru |  |  | 40 mins
5.3.14 | Change Data Integration Services to old ODS - can be done after the DB activities, Rain to be informed | rain.zhen@avon.com |  |  | 90 mins |  |  | Avon Data Integration <avondataintegration@isoftstone.com> Avon Data Service Team <avondataservicesteam@isoftstone.com> from cbylxwebeeupdbc1.uk.avon.com:1521:webecep to amslxgi3eupdb3.dc.avon.net:1521:webecep
5.4 | Starting apps in Corby |  | 2021-10-23 21:05 | 2021-10-23 22:05 | 60 mins | 5.4
5.4.1 | start GOMAC | Gergo |  |  | 30 mins
5.4.2 | Connect to th dmgr in CBY and modify the datasource to a valid hosts and ripple restart AGS3 JVMs | MW / Santosh |  |  | 45 mins
5.4.3 | Start Gi3 environment in CBY | Santosh / Maykon / MW |  |  | 60 mins
5.4.4 | Re-create DB links in ARIES to ODS and Linx | Gabor Pachert |  |  | 5 mins
5.4.5 | Start MAO Email sending Boomi process | Tibor Kepecs |  |  | 5 mins |  |  | Start MAO Email sending Boomi process. Add EE,LV,LT,FI,UA to PROD APAC -> env variables -> Dynamic Process Properties -> DPP_MAOEmail_marketList
5.4.6 | Start SMS Gateway/SMS Ordering Job | Pavel |  |  | 5 mins
5.4.7 | Enable Aries jobs | Gabor Pachert |  |  | 5 mins
5.5 | Smoke tests |  | 2021-10-23 22:05 | 2021-10-23 23:05 | 1 h | 5.5
5.5.1 | Update hosts files with CBY settings for testers (check MAS only) | Market |  |  | 1 h |  |  | need hostfiles for Corby
5.5.2 | smoke tests MAO including reports | Tanya |  |  | 1 h
5.5.3 | smoke tests GI3/CCA | Anandhi/Keerthana |  |  | 1 h
5.5.4 | smoke tests LINX connectivity | Gergo |  |  | 10 mins
5.5.5 | smoke tests MAS | Akos Tamas |  |  | 1 h
5.5.6 | Smoke test AGS3 | Lorand Fazekas |  |  | 15 mins
5.5.7 | smoke tests AGS classic | Shankar |  |  | 30 mins
5.5.8 | RRM connectivity to Linx | Gabor Pachert |  |  | 30 mins
5.5.9 | Smoke test Payment Gateway (partial) | Priyanka G |  |  | 30 mins
5.5.10 | NOEL - Noel: AGS3 domain update : myavon-ws-eu-ams.prod.avon.com | Laszlo G |  |  | 30 mins
5.5.11 | smoke tests Fuse | Kristine Tan Seng-Espiritu |  |  | 1 h
5.6 | Start old autosys jobs |  | 2021-10-23 23:05 | 2021-10-23 23:35 | 30 mins | 5.6
5.6.1 | DML script tasks activation | Michal |  |  | 10 mins
5.6.2 | Put old autosys jobs online. See tab "Jobs to be put offline" | Miguel |  |  | 30 mins |  |  | Miguel to get the list of jobs from Michal
5.7 | Business tests on old env |  | 2021-10-23 23:35 | 2021-10-24 02:35 | 1 h | 5.7
5.7.1 | Support Business testing | Gabor |  |  | 30 mins |  |  | Gabor / Mihai / Daniel will organize
5.7.2 | Change NOEL endpoint from AMS to CBY URL | Laszlo Gecse |  |  | 30 mins |  |  | NA
5.7.3 | Update tester's host files to point to GI3 CBY | Business Testers
5.7.4 | GI3 | [6 empty] | Business testors
5.7.5 | MAS | [6 empty] | Business testors
5.7.6 | MAO | [6 empty] | Business testors
5.7.7 | Payment Gateway | [6 empty] | Business testors
5.7.8 | SMS ordering | [6 empty] | Business testors
5.7.9 | PRP - Nordics and UA | [6 empty] | Business testors
5.8 | Maintenance pages removal |  | 2021-10-24 02:35 | 2021-10-24 03:35 | 60 mins | 5.8
5.8.1 | migrate DNS to CBY | Amit Kumar LB |  |  | 30 mins
5.8.2 | Remove maintenence pages
5.8.2.1 | MAO - remove maintenance page
| MAO - remove maintenance page | MW team |  |  | 30 mins
5.9.1.4 | MAO - remove maintenance page | Terraform (HCL Devops) Team - Nirdesh |  |  | 30 mins
5.9.1.6 | Validation of removal of maintenance page | tatiana.darkshevich@avon.com |  |  | 5 mins
5.9.2 | MAS - remove maintenance page | Akos Tamas |  |  | 30 mins |  |  | Imre confirmed
5.9.2.1 | Avon Grow - remove maintenance page | jackson.yan@avon.com |  |  | 15 mins |  |  | Owen confirmed
5.9.2.2 | IMB - remove maintenance page | Alexandru |  |  | 30 mins |  |  | Alex confirmed
5.9.2.3 | Enable Avon On
5.9.2.4 | Enable single sign on to place orders | Sai |  |  | 45 mins |  |  | Sai confirmed
5.9.2.5 | Enable single sign on to history of orders / returns | Sai
5.9.2.6 | Enable signe sign on to cutomer orders | Sai
5.9.2.7 | Enable make a payment from dashboard, from my account page, decision landing page, menu | Sai
5.9.2.8 | Enable edit phone number and email from my profile page | Sai
5.9.2.9 | Enable single sign on to Avon Office | Sai
5.9.2.10 | Enable single sign on to Avon Connect | Sai
| Enable IMB dashboard | Sai
| Enable IMB ordering | Sai
| Enable single sign on for Avon Grow | Sai
| Enable self appointment from login page | Sai
| Digital recruitment links - enable a from component | Sai
OSA Recruitmnet Pages - NA
6 | END OF THE OUTAGE |  | 2021-11-14 |  |  | 5.9
6.5 | Mass billing | Billing Operator / Gabor

## Backout Plan (hidden)
5.1 | stop new autosys jobs | Miguel | 30 mins
5.2 | Preps before we stop apps on new prod |  | 30 mins
| Put new Dallas/Corby autosys jobs back online. | Miguel
| Check for any job failures - AUTO_JOB_DETL, autsys log files | Michal
5.3 | APPS STOP |  | 30 mins
Run scripts / start GOMAC
Stop MAO Email sending Boomi process
Stop GI3 apps (CE2 markets) (Amst)
disable Aries jobs
Disable Concord jobs
5.4 | Tasks before we switch apps to old db and endpoints for sat apps |  | 60 mins
| change CE2 to the old ip on /etc/hosts on dlslxpsmsgwap1 | Maykon
| modify GI3 urls to the old IPs | Amit |  | maykon to prepare URLs and Ips
5.5 | Switch to old databases |  | 30 mins
| start old databases | Ishan
| ezBrochure change point CE markets to new DB (XML config change) | Michal
| Connect to the dmgr in CBY and modify the data source to a valid hosts and ripple restart AGS3 JVMs | Maykon
5.6 | Starting apps |  | 30 mins
| start GI3 | HCL MW
5.7 | Smoke tests |  | 90 mins
| smoke tests MAO including reports | Tanaya
| smoke tests GI3/CCA | Anandhi | 30 mins
| Smoke test AGS3 | Andras
| smoke tests MAB | Amritha / Jozsef
| smoke tests AGS classic | Shankar | 30 mins
| smoke tests LINX | Gergo
| ARIES? | Attila
| Smoke test Payment Gateway (partial) | Priyanka G
5.8 | Start old autosys jobs |  | 60 mins
| Put new Dallas autosys jobs back online. See tab "Jobs to be put online" | Miguel
| Logfiles, tabels for jobs to be checked | Michal
5.9 | satellite apps endpoints to be changed back to old env & smoke tested (tests when we have jobs done) |  | 120 mins | can be started anytime
Avon Grow - Change Avon Grow front end to old one (details)
MAS - Switch to old AGS URLs (detailed plan by Imre Balla)
MAO
AGS3 domain update : OLD URL
Validation of MAO connectivity
NOEL - Noel: AGS3 domain update : OLD URL
IMB - Switch to old AGS URLs
Avon On - to be discussed with Sai
Switch to old AGS URLs
IVR
Hungary - switch endpoints?
RO/BG/CZ - Switch endpoints
Cognito
Change AGS Classis SMS endpoint - ARIES
FUSE
local digital team update AGS3 fuse sso in magnolia (mab, mao)
Constantino, will raise ticket to update ags3 url on fuse end
Change Data Integration Services to New ODS
Eloqua config needs to be updated to use the proper AGS/AGS3 domain
SMS Gateway
Change AGS classic endpoints
PRP
OSA Recruitmnet Pages
Dynatrace
Transfer lincenses from AMST To CBY
ARIES
Change dblink/config for Tibi's engine
5.1 | Business Testing
MAB
Estonia
Finland
Latvia
Lithuania
Ukraine
GI3 CCA
Estonia
Finland
Latvia
Lithuania
Ukraine
MAO
Estonia
Finland
Latvia
Lithuania
Ukraine
MAS
Estonia
Finland
Latvia
Lithuania
Ukraine
Avon ON
Estonia
Finland
Latvia
Lithuania
Ukraine
Avon Grow
Estonia
Finland
Latvia
Lithuania
Ukraine
IVR
Estonia
Finland
Latvia
Lithuania
Ukraine
NOEL
Estonia
Finland
Latvia
Lithuania
Ukraine
Cognito
Estonia
Finland
Latvia
Lithuania
Ukraine
IMB
Estonia
Finland
Latvia
Lithuania
Ukraine
Payment Gateway
Estonia
Finland
Latvia
Lithuania
Ukraine
5.1 | Lift Maitenance Pages
Remove maintenence pages
MAB
MAB CE AMS- remove maint page
MAB Corby - remove maint page
MAO - remove maintenance page
MAS - remove maintenance page
Avon Grow - remove maintenance page
IVR
IVR HU - remove prompt
IVR CZ/BG/RO - remove prompt
IMB
Enable Avon On
Enable single sign on to place orders
Enable single sign on to history of orders / returns
Enable signe sign on to cutomer orders
Enable make a payment from dashboard, from my account page, decision landing page, menu
Enable edit phone number and email from my profile page
Enable single sign on to Avon Office
Enable single sign on to Avon Connect
Enable IMB dashboard
Enable IMB ordering
Enable single sign on for Avon Grow
Enable self appointment from login page
Digital recruitment links - enable a from component
FUSE - Avon Connect
PRP
OSA Recruitmnet Pages
| Start ARIES SMS process | Attila
Bill Test Orders
NOEL
| Change NOEL endpoint from Corby to Amsterdam - AGS3 | Laszlo G

## Progress Tracker
| Actual Time | Milestone | Status
CE2 and UA Cutover 12-14/11/21 (CET time zone) |  |  |  | PMS | UAT Team | GI3 | Other IT
12/11/21 - 21.00 CET – Start cutover |  | Maintenance Pages Go Up |  | Monika Zajaczkowska | Zoe Youel | Pavel Gas | Maykon Salvi/SPO/BR <maykon.salvi@avon.com>
- 18.00 – 20.00 (2h) End day processing |  | Application Server Shutdown |  | Irena Pstragowska |  | Anandhi Chinnarasu | Miguel Poma/RYE/US <miguel.poma@avon.com>
- 21.00 – 23.40 (2h 40 mins) Stop applications & setup maintenance page for Avon Office, Avon Store, (GI3 outage) |  | Database Refresh Processes |  | Vineet Khare; |  | Michal Elias/PRG/CS <michal.elias@avon.com> | Slawomir Swiatkowski/WAW/PL <slawomir.swiatkowski@avon.com>
12-13/11/21 - 23.40 – 7:50 (8hrs 10 min) Database activities, including restore from PROD and migration to Amsterdam |  |  |  | Gurvinder Singh Loh |  |  | Gergo Spielmann/BDP/HU <gergo.spielmann@avon.com>
13/11/21 - 06:50 – 07.50 (1h) Setting up connectivity between databases, applications, and starting applications |  | Connecting And Smoke Testing Satellite Applications
- 07.50 – 10.50 (3h) Smoke testing |  | Applications Servers Start
13/11/21 - 10.50 – 16.50 (6h) Production validation testing (by the Business) & bug fixing |  | Application Smoke Testing |  | Ashwani Tripathi; | Business Testers |  | Imre Szabo/BDP/HU <imre.szabo@avon.com>
-16:50 – GO / NO GO Decision |  | Business Testing |  | Manish Mittal; | Cristina Corcho |  | Jozsef Bodnar/BDP/HU <jozsef.bodnar@avon.com>
- 17.15 – 18.15 (1h) Maintenance page removal + enabling Avon On, Avon Store |  | Go-No Go Decision (Pending Completion Of Testing) |  | Gwidon | María Muñoz
- 18.15– 21.15 (3h) Remaining UATs (Payment Gateway) |  | Lift Maintenance Pages |  | Amit G | Angelica Meriel
- 21.15 – 23.15 (2h) Contingency |  | Business Validation/Checkout |  |  | Miriam Carrascosa
- 23.15 End of Outage |  | End
- 23.15 – 01.15(2h) Post cutover activities / starting mass billing |  |  |  | Comms | Serena Binda | App Teams
|  |  |  | Karen Turnham/NHT/GB <karen.turnham@avon.com> | Adriana Batticani | Imre Balla
|  |  |  | Allison Darling/NHT/GB <Allison.Darling@avon.com> |  | Lorand Fazekas/BDP/HU <lorand.fazekas@avon.com>
|  |  |  | Kate Donovan/NHT/GB <kate.donovan@avon.com> | Shalina Fatania | Raja Subramaniam/Infosys/Consultant <raja.subramaniam@avon.com>
[5 empty] | David Keown | Levente Kiraly/BDP/HU <levente.kiraly@avon.com>
|  |  |  | ITBPS | Amy Dunababin | Jackson Yan/Other/Consultant <jackson.yan@avon.com>
|  |  |  | Radek | Jason Earnshaw | Alexandru DARABAN <alexandru.daraban@interactively.eu>
|  |  |  | Volodia | Gemma Stanhope | Constantino Vazquez/ALC/ES <constantino.vazquez@avon.com>
[5 empty] | Simon Parkinson | Shankar Chandranswayamprabha/Infosys/Consultant <shankar.chandranswayamprabha@avon.com>
Sai Chadalapaka/Infosys/Consultant <Sai.Chadalapaka@avon.com>
Zoltan Kovacs/RYE/US <zoltan.kovacs@avon.com>
|  |  |  | UK Business |  | Doru Dumitrescu/TUN/RO <doru.dumitrescu@avon.com>
|  |  |  | Thomas Esward | HCL | Oliver Neczpal/BDP/HU <oliver.neczpal@avon.com>
|  |  |  | Anthony Lewis | Ankur | Tamas Szeremy/BDP/HU <tamas.szeremy@avon.com>
[5 empty] | Ishan Malik <ishan.malik@hcl.com> | Dragos Ene/TUN/RO <dragos.ene@avon.com>
[5 empty] | Nakul | Owen Wan/GZH/CN <Owen.Wan@avon.com>
|  |  |  | UK IT | Rakesh Kumar | Gyongyver Nagy/BDP/HU <gyongyver.nagy@avon.com>;
|  |  |  | lynda.lawrie@avon.com | Onkur | Jaroslava Kmetova/PRG/CS <jaroslava.kmetova@avon.com>
|  |  |  | Jean Wesson/NHT/GB <jean.wesson@avon.com> | Kapendra Singh/HCL/Consultant <kapendra.singh@avon.com> | haziq.khalil@avon.com
jaya.gash@avon.com
Italy IT
Tania Taffoni/CMO/IT <tania.taffoni@avon.com>
Michael Penati/CMO/IT <michael.penati@avon.com>
Andrea Tomizza/CMO/IT <andrea.tomizza@avon.com>
Ivan Criado/ALC/ES <Ivan.Criado@avon.com>

## Checklist
| Checklist | Status | Comments
| Create CRQ, for Trial cutover | Done | CHG0064260
| Create CRQ for final cutover, go to CAB and get approval | Done | CHG0064107
| QA and Integration sign off | In Progress | Pending for open defects in Code Recon
| UAT Business sign off | Done
| Performance testing sign off | Done | Link to Sign-off
| Trial cutover | Done
| Sponsor sign off to run cutover | Not started | Craig - Pending for approval
| Application owner sign off to run a cutover Laszlo and Maks | Not started | Received fro GOMAC
| Prepare a cutover plan | In Progress
NEW!! | Prepare Downtime Announcement | In Progress
| Outage business approval | Not started | To check with Manish
| Prepare Go /no Go deck | In Progress
| Schedule a Go/no Go call | Done | ITBPs, Craig, Market leads, Monika and Vineet
| Setup a chat with CIMT and leaders | Not started | Monika will schedule it
| Setup hyperCare daily 30min calls with team | Not started | Market leads, Dev team, Gi3 team, GOMAC team, PM's, Who raised and to whom Assigned
CUTOVER PREPARATION
NEW!! | Hostfiles | Done | Host File MAO, MAS and GI3 Admin rights | Imre bala, Carol, Anandhi,
| RITM for admin rights to testers to be raised | In Progress | dropped a mail to user with link - to re-check
| Prepare a cutover plan | Done
NEW!! | Prepare a backout plan | Done
| Schedule a daily 1h cutover calls 6 weeks before a cutover | Done
| Ensure that all required people are invited | Done
| Ensure that all required people join calls | Done
| Confirm that every task has assigned name resource | Done
| Confirm IT resources for a cutover | Done
| Confirm Business resources for a cutover | Done
NEW!! | Confirm server patching will not be happening during cutover | done | Link to communication
NEW!! | Confirm Security resources to approve a whitelist (if required) | Done | open a task for security and Unix
| Prepare IT smoke testing plan | Done | Anandhi MAS MAO
| Prepare Business production checkout plan and tests cases | Done | Business testers
| Prepare a contact list with mobile phone numbers and mails | Done
| Send invitation for cutover chat | Not started | 1 cut-over and 2 testing
| Upload a cutover plan into teams and show in a menu | Done
| Upload a test plan into teams and show in a menu | Done
| Create and upload a cutover & Hyper Care file | Done
CUTOVER
| Start a cutover chat | Not started
| Call out task doer to start his task sharing a task #, description on a cutover chat | Not started
| Update a cutover plan about completed tasks | Not started
| Mark tasks in progress | Not started
| Send update mails to all team and leaders | Not started
| Send texts to comms team and test team | Not started
HYPERCARE
| Lead daily HC calls | Not started
| Update a HC defects list | Not started
| Send a HC report wth a status of defects daily | Not started

## LL
STATUS