## NAME PT GR Trial cutover
| from Ishan | level1 backup- 30 minutes
level1 backup copy from corby to amsterdam- 20 minutes
level 0 restore- 2.5 hours for gmcgptp and 1.5 hours for webeptp upgrade database -- 60 minutes directory changes : 5 minutes and partition clean up : 25 mins
| 3 | TRIAL CUTOVER | planned 16th Sept, during daytime - as we agree (ODS and GOMAC -> full backup and restore) | [5 empty] | refresh database and smoke tests
CRQ | No | Task description | Responsible | Start CET time | End | Duration | Predecesor | Status | Comments
NO | 0 | PREPARATIONS |  | 1 day before trial cutover
| 0.1 | CRQ CHG0062375 for testing and database refresh and application restart | Irena | 2021-09-07 | 2021-09-13 |  |  | DONE | at least 7 days before planned trial cutover you need to have change in SNOW promoted from Draft status
| 0.2 | We need to figure out what to do so that new PROD autosys jobs are not failing during the DB restore task. Also, once DB is restored, we need to ensure no jobs are running until data is scrambled. Assuming we are scrambling data actually… | Michal |  |  |  |  | N/A | we are not scrambling data autosys jobs will be on-hold till cutover, released after testing (downtime)
| 0.3 | Collect list of jobs that need to be inactive | Michal |  | 2021-08-25 |  |  | DONE | during cutover we just need to make sure they are inactive
| 0.4 | Put autosys jobs on-hold | Miguel |  | 2021-09-10 |  |  | DONE
| 0.5 | Backup autosys jobs details and definitions | Michal |  | 2021-08-25 |  |  | DONE
| 0.6 | Production Validation confirmed | Global QA team, UATs |  | 2021-09-15 |  |  | DONE | with few defects
| 0.7 | Full backup (lvl 0) and copy from CBY to AMS | Ishan |  | 2021-09-15 |  |  | DONE
| 0.8 | Cleanup scripts for GI3 | Ivan |  | 2021-09-15 |  |  | DONE
| 0.9 | Cleanup scripts for Linx | Tamas Csiba/Andrea Gazdag |  | 2021-09-07 |  |  | DONE
| 0.10 | Change DB parameters on Prod DB which was done on QAP | Imre |  | TBC if needed |  |  | N/A
| 0.11 | Validate timezone configuration on new servers as we are moving from Corby to AMS (GI3 and AGS3 servers web, app, db, batch) | Rakesh Kumar (HCL Linux) |  | 2021-09-16 08:30 |  |  | DONE | to be done/confirmed before trial cutover for all streams migrated from Corby to AMS we need same timezone as in Corby (UK)
TRIAL CUTOVER START
CRQ | No | Task description | Responsible | Start CET time | End | Duration | Predecesor | Status | Comments | real start | real stop
| 3.0 | STOP APPS new prod |  | 2021-09-16 09:30 | 2021-09-16 09:50 |  |  |  | to be started when UAT are finished
YES | 3.0.1 | Applications to be stoped: GI3 PT, GR, SA, EG, MO + stop AGS ams | MW Team |  |  | 20 mins |  | DONE | https://amslxgi3pdmgr1.dc.avon.net:14001/ibm/console stopping AGS but for another streams in AMS we do not as we will stop another markets | 9:30 | 9:45
YES | 3.0.2 | Applications to be stopped: AGS3 JVM: myavon-ams-cluster | MW Team |  |  |  |  | DONE | https://amslxags3pdmgr1.dc.avon.net:14001/ibm/console | 9:30 | 9:45
| 3.1 | DATABASE REFRESH | Ishan | 2021-09-16 09:50 | 2021-09-16 15:20 | 330 mins (5,5h)
| 3.1.1 | restore database from level 0 backup | Ishan | 2021-09-16 09:50 | 2021-09-16 11:50 | 120 mins |  | DONE | should take around 90 mins - estimation (we planned 120 mins)
| 3.1.1.1 | webeptp (ODS db) clone and upgrade from production | Ishan, Nakul |  |  |  |  | DONE | cbylxwebeeupdbc2.uk.avon.com/webepl2p -> clone to Amsterdam as: amslxgi3eupdb2.dc.avon.net/webeptp | 9:50 | 11:45
| 3.1.1.2 | gmcgptp (full backup / restore) | Ishan, Nakul |  |  |  |  | DONE | cbylxwebeeupdbc2.uk.avon.com/gmcgeep -> clone to Amsterdam as: amslxgi3eupdb2.dc.avon.net/gmcgptp | 9:50 | 11:45
| 3.1.2 | level 1 backup + archive backup | Ishan | 2021-09-16 11:50 | 2021-09-16 13:20 | 90 mins |  | DONE | during cutover here we put maint page
| 3.1.2.1 | webeptp (ODS db) | Ishan |  |  |  |  | DONE |  |  | 11:45
| 3.1.1.2 | gmcgptp | Ishan |  |  |  |  | DONE |  |  | 11:45
| 3.1.2.4 | recover databases | Ishan |  |  |  |  | DONE | autosys jobs will be on-hold |  | 11:45
| 3.1.3 | upgrade databases | Ishan, Nakul | 2021-09-16 13:20 | 2021-09-16 14:20 | 60 mins |  | DONE | 60 mins / db - in pararell or more DBAs; Ishan can do 2 dbs in parallel, Nakul to help | 11:45
| 3.1.4.1 | webeptp (ODS db) | Ishan, Nakul |  |  |  |  | DONE | upgraded to 12: 11:55, next step upgrade to 19C - 12:45 | 11:45 | 12:45
| 3.1.4.2 | gmcgptp | Ishan, Nakul |  |  |  |  | DONE | upgraded to 12, next step upgrade to 19C | 11:45 | 17:51 (issues during upgrade)
| 3.1.4.3 | Get data counts | Ivan/Ishan |  |  |  |  | DONE |  | 12:45 | 13:00
| 3.1.4.4 | cleanup - remove PL data partitions GI3 ODS | Ishan, Nakul | 2021-09-16 14:20 | 2021-09-16 15:20 | 60 mins | 3.1.4.1 | DONE | Poland, Montenegro, Israel - scripts to be updated | 13:00 | 13:35
| 3.1.4.5 | cleanup - remove UA, KZ, KG data partitions LINX | Gergo | 2021-09-16 14:20 | 2021-09-16 15:20 | 60 mins | 3.1.4.2 | DONE | real duration: 40 mins | 40 mins real duration
| 3.1.4.6 | Get data counts | Ivan/Ishan |  |  |  |  | DONE
| 3.2 | SANITY CHECK - if db is accessible | db owners | 2021-09-16 15:20 | 2021-09-16 16:00 | 40 mins | 3.1
| 3.2.1 | webeptp (ODS db) | Ivan/Micha/Pavel |  |  | 15 mins |  | DONE | and partition check (Ivan) | 14:30 | 15:30
| 3.2.2 | gmcgptp | Gergo |  |  | 40 mins |  | DONE |  | 17:55 | 18:15
| 3.2.5 | Data scrambling - make sure possible testers are aware we are NOT SCRAMBLING | Ivan F |  |  |  |  | N/A | not applicable for NAME/PT/GR cluster
| 3.3 | DDL install db objects (external tables and directory changes) - webearp | Ishan | 2021-09-16 15:20 | 2021-09-16 15:25 | 5 mins | 3.1 | DONE | Extra package to be added to real cutover | 14:45 | 14:50
| 3.4 | DML scripts execution (autojob details) - restoring backuped autosys jobs | Michal | 2021-09-16 15:20 | 2021-09-16 15:25 | 5 mins | 3.1 | DONE
| 3.5 | CONTENT REFRESH |  | 2021-09-16 13:00 | 2021-09-16 15:00 | 120 mins | anytime when Maykon is at work | DONE
NO | 3.5.1 | pdf reports (DELTA) | Maykon |  | 2021-09-28 03:02 | 60 mins |  | DONE | /mounts/gi3_prod_ftp/reports/PT /mounts/gi3_prod_ftp/reports/GR /mounts/gi3_prod_ftp/reports/SA /mounts/gi3_prod_ftp/reports/MA /mounts/gi3_prod_ftp/reports/EG
| 3.5.2 | Refresh content: /mounts/gi3_prod/prod/portugal /mounts/gi3_prod/prod/greece /mounts/gi3_prod/prod/egypt /mounts/gi3_prod/prod/morocco /mounts/gi3_prod/prod/saudiarabia | Maykon |  | 2021-09-28 03:02 |  |  | DONE | we need to make sure markets push changes to both locations
| 3.5.3 | Deploy latest version of local settings file and vendorlinks file - all markets | Anandhi |  |  | 60 mins |  | DONE |  | 14:55 | 15:30
| 3.6 | APPLICATIONS START |  | 2021-09-16 16:00 | 2021-09-16 16:50 | 50 mins | 3.2, 3.3, 3.4, 3.5
YES | 3.6.1 | Start applications: GI3 PT, GR, SA, EG, MA, AGS ams | MW Team |  |  |  |  | DONE | https://amslxgi3pdmgr1.dc.avon.net:14001/ibm/console | 15:55 | 16:20
YES | 3.6.2 | Start applications: AGS3 JVM: myavon-ams-cluster | MW Team |  |  |  |  | DONE | https://amslxags3pdmgr1.dc.avon.net:14001/ibm/console | 15:55 | 16:20
| 3.7 | IT-smoke testing (application level) - DATA IS NOT SCRAMBLED! |  | 2021-09-16 16:50 | 2021-09-16 17:50 | 60 mins | 3.6
NO | 3.7.1 | GI3 smoke tests with hostfile entry (confirm if GI3 is communicating with GOMAC - today it is pointing to GOMAC QAP, GOMAC needs to point to new MQ - CUTOVER) | Anandhi |  |  | 60 mins |  | DONE | 10.160.0.36 www.eg.avon.com www-o.avon.com.eg 10.160.0.36 www.ma.avon.com www-o.avon.co.ma 10.160.0.36 www.sa.avon.com www-o.avon.com.sa 10.160.0.36 rep.avon.com.pt 10.160.0.36 rep.avoncosmetics.gr | 18:21 | 20:10 (Egypt subtotal and PT pdf reports issues)
| 3.7.2 | AGS classic webservices | Shankar |  |  | 30 mins |  | DONE |  | 16:25 | 16:40
| 3.7.3 | AGS3 | Zoltan |  |  | 15 mins |  | DONE
| 3.8 | AFTER TRIAL CUTOVER |  | 2021-09-16 16:50 | 2021-09-16 17:50 | 60 mins | 3.6
| 3.8.1 | Check all dblinks in WEBEPTP and confirm if they need to undergo any changes. | Ivan |  | after trial cutover |  |  | N/A | important for next streams esp NAME/PT/GR to be confirmed by Ivan 17/09 if needed

## NAME PT GR cutover plan 25t Sep
CRQ | No | Task description |  | Responsible | START CET timezone | End CET TZ | Duration | Predecesor | Status | Comments | Real start | Real end | duration
|  | GOLIVE: 25th Sept start downtime: 23:30 CET | [7 empty] | 11:30 pm - all billings done & REPs to process orders by midnight
content freeze: stop all setup, offers, changes stopped - not pushed to new database, can do, not visible
|  | Database backup and recovery estimations from Ishan - for SMG |  | DB's |  | Backup Time | Recover Time
|  |  |  | webearp |  | 2 hours | 90 mins
|  |  |  | leadslap |  | 1 hour | 1 hour
|  |  |  | chrptlap |  | 2 hours | 90 mins
|  |  |  | gomacarp |  | 45 mins | 40 mins
|  |  |  | wassolap |  | 40 mins for creating the database.
|  |  |  | agslap |  | 45 mins | 40 mins
| 0 | TO BE CONFIRMED WITH MARKETS
| 0.1 | GOMAC content freeze |  | ITBP |  |  |  |  | N/A | real time billing, not applicable with freeze
| 0.2 | GI3 freeze (teamside) - outage confirmed |  | ITBP |  |  |  |  | N/A | deployment to new and old environment
| 0.3 | GOMAC db upgrade start date/hour |  | ITBP |  |  |  |  | N/A | to be done with all implementation
| 0.4 | GI3 downtime |  | ITBP | 2021-09-25 23:30 | 2021-09-26 23:30 |  |  |  | ~24 hours
| 0.5 | maintanance page (content to be confirmed and who prepare, when) |  | ITBP | 2021-09-22 | 2021-09-22 |  |  |  | to be confirmed with IT BP who and when
| 0.6 | GO/NOGO for cutover with Business |  | ITBP, Business | 2021-09-22 | 2021-09-24 |  |  |  | meeting
approach to be confirmed - deployment on old and new env
| 1 | FORMAL PREPARATIONS
| 1.1 | CRQ for any database to be shutdown / decom if needed |  | Irena
| 1.1.1 | confirm with IT BP before sending request to shutdown |  | IT BP
| 1.1.2 | when shutdown - remove from new server |  | Maykon/Imre
| 1.2 | CRQ for trial cutover CHG0062375 |  | Irena | 2021-09-07 | 2021-09-10 |  |  | IN PROGRESS | CHG0062375
| 1.3 | CRQ for GoLive CHG0062735 |  | Irena | 2021-09-17 | 2021-09-21 |  |  |  | CHG0061046 - for SMG as egzample
| 1.3.1 | cutover plan ready |  | Irena |  | 2021-09-10
| 1.3.2 | plan confirmed with NAME/PT/GR markets |  | Irena |  | 2021-09-10
| 1.3.3 | contacts confirmed |  | Irena |  | 2021-09-10
| 1.3.4 | groups for CRQ confirmed (assignement) |  | Irena |  | 2021-09-10
| 1.4 | QAP signoff |  | Pavel/Attila D |  | 2021-09-13
| 1.5 | UAT signoff (new PROD) |  | IT BP |  | 2021-09-15
| 1.6 | outage + communication |  | IT BP |  | 2021-09-10
| 1.7 | Global Privacy approval |  | Anastacia Izmaylova | 2021-07-01 |  |  |  | DONE | done for all GI3 streams
| 1.8 | Project Risks approval |  | Michał Ziółkowski | 2021-07-01 |  |  |  | DONE | done for all GI3 streams
| 1.0 | SOX approval |  | Karolina Przybysz | 2021-07-09 |  |  |  | DONE | done for all GI3 streams
| 1.10 | Service Team approval (communication) |  | Jarosław Żurawski | 2021-09-09 | 2021-09-13 |  |  | IN PROGRESS
| 2 | TECHNICAL PREPARATION
| 2.0 | N/A for SMG markets, need to be revied by another streams | [6 empty] | DONE
| 2.0.1 | Approach to be confirmed - deployment to old and new env OR red line and GI3 content freeze |  | TEAM + ITBPs |  | 2021-09-10 |  |  | DONE | RECOM: deployment to old and new env OR red line and GI3 content freeze
| 2.0.1.1 | Content freeze for GI3 - teamsite will block it (RED LINE) |  | Anton | 2-3 days before GoLive (depends on approach decided) |  |  |  | N/A | SMG has been synch, and deployment could be done to both envs - new and old; we need decision on the approach
n/a | 2.0.1.2 | Content controllers to be infomed (production, migrate) and engaged |  | Anton |  | 2021-09-15 |  |  | DONE | decided to deploy to old and new environments
| 2.0.2 | Check all dblinks in WEBEPTP and confirm if they need to undergo any changes. |  | Ivan | after trial cutover | 2021-09-17 |  |  | N/A | duplicated with trial cutover task 3.8.1
| 2.0.3 | Validate timezone configuration on new servers as we are moving from Corby to AMS (GI3 and AGS3 servers web, app, db, batch) |  | Rakesh (HCL Linux) |  | 2021-09-16 |  |  | DONE | important for next streams esp NAME/PT/GR we need same timezone as in Corby (UK)
| 2.1 | SCRIPTS PREPARATION
| 2.1.1 | level 0 backup scripts for |  | HCL DBA (Ishan) |  |  |  |  | DONE
| 2.1.1.1 | webeptp (ODS db) clone and upgrade from production - scripts preparation | [6 empty] | DONE | cbylxwebeeupdbc2.uk.avon.com/webepl2p -> clone to Amsterdam as: amslxgi3eupdb2.dc.avon.net/webeptp
| 2.1.1.2 | gmcgptp (full backup / restore) - scripts preparation | [6 empty] | DONE | cbylxwebeeupdbc2.uk.avon.com/gmcgeep -> clone to Amsterdam as: amslxgi3eupdb2.dc.avon.net/gmcgptp
| 2.1.1.3 | webwas2p (leave intact) | [7 empty] | Create session DB based on QAF webwasqf scripts: amslxgi3eupdb2.dc.avon.net/webwas2p
| 2.1.1.4 | agscep - (leave intact) |  |  |  | 2021-08-13 |  |  |  | No change is needed for the db side (confirmed by Shankar)
| 2.1.2 | scripts to install db objects (external tables for ETL users) - readiness |  | Michal |  | 2021-08-11 |  |  | DONE | need to create external tables and views
| 2.1.3 | update deployment scripts (AGS3) for NAME/PT/GR |  | MW Team | tbc by Ankur, Ivan U and Andras G | 2021-09-22 |  |  | IN PROGRESS | scripts handed over to MW Team 29.07.2021, need to confirm if they are prepared for NAME/PT/GR
| 2.1.3.1 | details need to be provided by application team |  | Anandhi |  |  |  |  | if needed
| 2.1.4 | review prod deployment process GI3, AGS classic |  | Maykon |  | 2021-07-26 |  |  | DONE | has been done for SMG, do we need it to be done for NAME/PT/GR?
| 2.1.4.1 | setup new GI3, AGS classic deployment script on new env |  | Maykon / Eduardo |  | 2021-09-20
| 2.2 | new PROD - Environment readiness (incl. Smoke tests) |  | Vineet | [5 empty] | to be updated with Programme Plan (environments)
| 2.2.1 | data scrambled before new PROD readiness |  | Ivan F |  |  |  |  | DONE
| 2.2.2 | autosys jobs checked, confirmed, turned on in controlled way |  | Michal | 2021-08-13 |  |  |  | DONE | enabling jobs during cutover
| 2.2.3 | NAS mounts / NAS folders (to be confirmed if needed - Michal) |  | Michal |  |  |  |  | DONE | /mounts/gi3_prod /mounts/gi3_prod_ftp
| 2.2.4 | webserver config (httpd) |  | Maykon |  |  |  |  | DONE
| 2.2.5 | websphere NAME/PT/GR preparations |  | Maykon |  |  |  |  | DONE
| 2.2.6 | application deployment |  | Maykon |  |  |  |  | DONE
| 2.2.7 | symbolic links creation |  | Maykon |  |  |  |  | DONE
| 2.2.8 | teamsite preparation |  | Anton |  |  |  |  | DONE | it is called 'migrate' new target linked to new prod once we go live, i'll remove old one and rename new one to just 'prod'
| 2.2.9 | enable config for new prod deployment |  | Anton |  |  |  |  | DONE
| 2.2.10 | application property files in the NAS |  | GI3 dev team (Jey) |  |  |  |  | DONE | need to deploy when we are done with resynch
| 2.2.11 | content refresh scripts |  | Michal |  |  |  |  | DONE
| 2.2.12 | perl modules instalation |  | Maykon |  |  |  |  | DONE
| 2.2.12.1 | perl scripts validation |  | Michal |  |  |  |  | DONE
| 2.2.13 | shell scripts validation |  | Michal |  |  |  |  | DONE
| 2.2.13.1 | Python modules installation |  | Michal/Maykon |  |  |  |  | N/A
| 2.2.14 | autosys setup to new batch servers |  | Miguel |  |  |  |  | DONE
| 2.2.15 | install dynatrace |  | Maykon |  |  |  |  | DONE
| 2.2.16 | import GI3 & AGS3 & AGS classic new certificates to the applications that invokes it |  | Maykon |  |  |  |  | DONE
| 2.2.16.1 | Google cert to be checked (CAPTCHA issue) |  | Maykon |  | 2021-09-17 |  |  |  | Maykon needs URL we are invoking
| 2.2.17 | QAF and new prod Magnolia external cert submitted |  | Anandhi |  | 2021-09-17 |  |  | DONE | to be checked if calling https not http
| 2.2.17.1 | to be checked if QAF Magnolia sites are running on correct certs | [6 empty] | DONE
| 2.2.18 | import external weservice certificates to the new AGS and AGS3 env |  | Maykon |  |  |  |  | DONE | to be checked by Anandhi
| 2.2.19 | import external weservice certificates to the new Gi3 |  | Maykon |  |  |  |  | DONE | for GI3 done in another way (too many urls)
| 2.2.19.1 | provide the list of all external URLs (otherwise we have P1) - GI3, AGS, AGS3, LEADS |  | Zoli, Pavel, Michal…. All team |  |  |  |  | DONE | for AGS and AGS3 opened
| 2.2.20 | submit the request for external URLs to be added to FireWall |  | Maykon |  |  |  |  | DONE | 1 week before GoLive, predesesor: url delivered
| 2.3 | AGS3 | [6 empty] | DONE
| 2.3.1 | AGS3 - deploy of newest version on prod (on QA already deployed) |  | Andras/Ivan Ukolov |  |  |  |  | DONE
| 2.3.2 | login, readonly services to be tested webservices (safe way) |  | Andras |  |  |  |  | DONE
| 2.3.3 | credentials to be shared with Andras (test accounts) |  | Zoli |  |  |  |  | DONE
| 2.4 | MAS preparations before NAME/PT/GR cutover |  | Imre Balla
| 2.4.1 | Impacted MAS markets to be confirmed |  | Imre Balla |  | 2021-08-05 |  |  | DONE | Portugal and Greece only
| 2.4.2 | Details for "comment section" in cutover plan to be shared |  | Imre Balla |  | 2021-08-16 |  |  | DONE | when we have urls etc
| 2.4.3 | Confirmation who will be appointed to support NAME/PT/GR Tech debt implementation |  | Imre Balla |  | 2021-09-17 |  |  | DONE | Levente Kiraly appointed
| 2.4.4 | MAS hostfiles to be shared |  | Imre Balla / Gabor Hodi |  | 2021-09-21
| 2.4.5 | Impacted MAS markets to be confirmed |  | Imre Balla |  | 2021-08-05 |  |  | DONE | Portugal and Greece only
| 2.4.6 | Question from Imre: New AGS classic URL will be ags-ws-eu-dls.prod.avon.com ? | [6 empty] | DONE | New AGS PROD URL (https://ags-ws-eu-ams.prod.avon.com/agws/)
| 2.4.7 | Question from Imre: Will Gi3 URL also change, like rep login, forgot rep password, etc? For example https://rep.avoncosmetics.gr/REPSuite/registration.page or http://rep.avon.com.pt/REPSuite/registrationTerms.page ? |  | Pavel |  |  |  |  | DONE | nothing changes, only https not http (first link is correct). Second one switch to https
| 2.5 | MAIMS preparations before NAME/PT/GR cutover |  | Irena/Paulo/Sureshaj |  |  |  |  | DONE
| 2.5.1 | To be confirmed when all billing processes end on FRI 24th September | [6 empty] | DONE | Details in timezone sheet, start of downtime: 23:30 CET 24th September with last billing (PT)
| 2.5.2 | Confirm if MAIMS jobs related with GI3 are covered by Michal's list |  | Michal Elias / Paulo |  | 2021-09-15 |  |  | N/A | they should not be covered by Michal, should be stopped on MAIMS side
| 2.6 | Another preparations |  | Irena
| 2.6.1 | passwds to be shared (ftp app paswd to be shared with NAME/PT/GR team) |  | Paulo, George, Michal |  |  |  |  | DONE | what can be needed? Passwds, users, …?
| 2.6.2 | content freeze for GOMAC - minimum backup for database will start for GOMAC | [6 empty] | N/A | not applicable for NAME/PT/GR, we upgrade GOMAC during cutover
| 2.6.3 | QA only - New IMT image upload - Anton to confirm if change was done for all NAME/PT/GR markets from /mounts/webe_cont/qaf/market/ALLSuite to /mounts/gi3_qaf/qaf/../ |  | Anton/Michal |  | 2021-09-16 |  |  | DONE | done for PT, rest of markets not using IMT
| 2.6.4 | PROD New IMT image upload - Anton to confirm if change was done for all NAME/PT/GR markets from /mounts/webe_prod/production/market/ALLSuite to /mounts/gi3_prod/prod/../ |  | Anton/Michal |  | 2021-09-16 |  |  | DONE | done for PT, rest of markets not using IMT
| 2.6.5 | New IMT - Point TS to new DB (what need to be changed to what - Michal to help / details) - should point to content env |  | Anton/Michal |  | 2021-09-16 |  |  | DONE |  | 6:45 | 8:11
| 2.6.6 | smoke tests if GI3 is communicating with GOMAC |  | Gergo/Maykon |  |  |  |  | DONE | to be confirmed during trial cutover - if it is communicating with GOMAC properly: pre-prod/prod GOMAC: "server": "amslxgi3pmq1.dc.avon.net(1414)", "channel": "GOMAC.SERVER.01", "queuemanager": "CBYPWEBE"
| 2.6.7 | prepare new AKAMAI for AGS classic & AGS3 |  | Maykon |  |  |  |  | DONE
| 2.6.8 | create new NetScalers for AGS classic and AGS3 |  | HCL Network Team |  |  |  |  | DONE
| 2.6.9 | validate new servers backup - all prod non-data servers |  | Vineet / backup team |  | 2021-09-17 |  |  | IN PROGRESS
| 2.6.10 | Change ETL OS passwords on new Batch servers: pt_etl, gr_etl, eg_etl, sa_etl, ma_etl, webe_etl |  | Pavel |  | 2021-09-13 |  |  | DONE | do we need it for NAME/PT/GR? passwd change can be invoked from command for each user individually
| 2.6.11 | Test PDF reports download for all 5 markets in preprod env |  | Pavel, Michal |  | 2021-09-16 |  |  | IN PROGRESS | just to prove it
| 2.6.12 | Open connectivity from MAS PT/GR PROD env (AWS) to AGS classic and AGS 3 endpoints |  | Imre Sz |  |  |  |  | DONE
| 2.6.14 | Install autosys agent on the database VMs - DBA team can confirm |  | Miguel |  | 2021-09-16 |  |  |  | Imre Szabo to confirm if we need it really
| 2.6.15 | Reduce GI3 DNS TTL 5 mins |  | Amit | 2021-09-21 | 2021-09-21 |  |  | DONE | www.ar.avon.com www.cl.avon.com www.uy.avon.com www-o.avon.com.ar www-o.avon.com.uy www-o.avon.cl
| 2.6.16 | point websphere for NAME/PT/GR to the production MQ (after trial cutover and UAT, when we have checked that GI3 communicates with GOMAC properly) - Preimplementation task! |  | Maykon |  |  | 10 mins |  | N/A | new MQ for cutover (splitting)
| 2.6.17 | Deploy recompiled version of DBD.pm to both PROD batch servers Will be needed for Amsterdam and another data centers |  | Michal |  |  |  |  | DONE | done for all future streams as well
| 2.6.18 | Prepare www-o.avon.com.pt, gr, eg, sa, ma will be working in PROD under AKAMAI - ensure all suffix are ok - |  | Maykon |  | 2021-09-16 |  |  |  | current prod we don't touch, new prod should work
| 2.6.18.1 | make sure that AKAMAI setup of all 5 markets is working |  | Maykon |  | 2021-09-16
| 2.6.19 | SMTP servers to be installed to batch and app servers - Check if it was done |  | Maykon |  |  |  |  | DONE
| 2.6.20 | to be discussed if we need AKAMAI for MAIMS markets |  | Maykon, Pavel, Laszlo Pinter |  |  |  |  | DONE | As long as there is no financial impact, Akamai is always recommended. Maykon will speak to Craig And a bit more thorough testing will be needed. Not sure if introducing Akamai can be anyhow tested in QA? -> YES, we can use AKAMAI staging env / AKAMAI live
| 2.6.21 | open the firewall form any ip on the internet to the new GI3 netscaler VIP in Amsterdan | [6 empty] | DONE
n/a | 2.6.22 | confirm with Michal if batch servers exists and file system needs to be resynch |  | Michal |  |  |  |  | DONE | no sych needed
| 2.6.24 | Install FTP in AMS amslxgi3pbt1.dc.avon.net |  | Vineet - Linux team to install + Michal, Paulo, Miguel to test | cutover plan update - Irena |  |  |  |  | - New servers are already created. On the 25-09 it will be a question of moving existing FTP processes to the new servers - GREECE - MAS FTP transfer was already moved to new server yesterday and tested between me and Michal Elias. - GREECE – PDF REPORTS FTP FOR GI3 - This will be covered outside MAIMS system by @George Thanos/ATH/GR - PT, EGY,MOR and SAU – PDF REPORTS FTP FOR GI3 – This will be covered by me, @Manuel Joao/SNA/PT and @Paulo Fortes during the day of 25-09 at any point in time after the conclusion of the daily PDF REPORTS FTP FOR GI3 processes. - PT and GR – PDF INVOICES FOR GI3 - This will be covered by me, @Manuel Joao/SNA/PT and @Paulo Fortes on 25-09 AFTER CONCLUSION OF LAST Billing in PT and GR
| 2.6.25 | hostfiles - SMG - to be updated for NAME/PT/GR markets Portugal, Greece, Morocco, Egypt, Saudi Arabia |  | Pavel / Gabor Hodi |  | 2021-09-20 |  |  | IN PROGRESS | GI3: 10.160.0.36 www.eg.avon.com www-o.avon.com.eg 10.160.0.36 www.ma.avon.com www-o.avon.co.ma 10.160.0.36 www.sa.avon.com www-o.avon.com.sa 10.160.0.36 rep.avon.com.pt 10.160.0.36 rep.avoncosmetics.gr MAS:
|  | Check and confirm LINX jobs (to be listed) |  | BA Team (Tamas Csiba) |  | 2021-09-21 |  |  |  | Linx jobs speaking to GOMAC / ODS databases to be confirmed by Tamas
| 3 | TRIAL CUTOVER (ODS and GOMAC -> full backup and restore) | planned 16th Sept, during daytime - as we agree (ODS and GOMAC -> full backup and restore) |  | 16th Sept, 9:30-17:50 CET |  | refresh database and smoke tests
| 4 | CUTOVER |  | CHG0062735 | [5 empty] | there are things that cannot be tested on QA nor new-prd; only after GoLive
created | 4.0 | PREPARATIONS FOR DOWNTIME |  |  | 2021-09-24 | till end of day
DCO-SPO-SERVER-SUPT-BR | 4.0.1 | purge queue depth for NAME/PT/GR in the new MQ if there is any |  | Maykon
DCO-SPO-SERVER-SUPT-BR | 4.0.2 | Disable Dynatrace alerts |  | Maykon
DCO-SPO-SERVER-SUPT-BR | 4.0.3 | Stop PT/GR/NAME / AGS-ams (classic) in the new env |  | Maykon | [5 empty] | https://amslxgi3pdmgr1.dc.avon.net:14001/ibm/console
DCO-SPO-SERVER-SUPT-BR | 4.0.4 | Applications to be stopped: AGS3 - new one, JVM: myavon-ams-cluster (MAKE SURE WE HAVE THE LATEST DEPLOYMENT + TESTING STRATEGY) |  | Maykon | [5 empty] | myavon-ams-cluster https://amslxags3pdmgr1.dc.avon.net:14001/ibm/console
ESO-OMS-ADMIN | 4.0.5 | Disable GOMAC QAP server connection |  | Gergo
| 4.0.6 | maint page GI3 on new servers |  | HCL MW |  | 2021-09-24 14:00
| 4.0.6.1 | test if maint page is uploading properly |  | HCL MW | [5 empty] | fake page to be pasted just to check
DCO-SPO-SERVER-SUPT-BR | 4.0.7 | applicate iframe parameters to another webseves for PT/GR (MAS markets) |  | Maykon
| 4.0.8 | level 0 backup - 5 dbs Friday |  | Ishan
| 4.0.9 | we need to clear down old archive logs so arch dest does not get full |  | Ishan
| 2.6.23 | Boomi Update Service registry master branch in Git |  | Zoli |  | 2021-09-23 16:00 |  |  |  | Update WEBE_DB_WEBEPTP.json and WEBE_DB_WEBEPL2P.json Create new release
n/a | 4.3.6 | Stop ePayment and eInvoice Boomi processes on PROD EG/GR |  | Zoli | Saturday 22:00 |  |  |  |  | need to be stopped before DBs are stopped [EG EPAY] (Sched) Processing Events Main.Sched.DB.ProcessInvoices [EG eInvoice] (Sched) Process invoices [ATM] (Sched) PT data sync [PT EPAY] (Sched) Processing Events [GR EPAY] (Sched) Processing Events
created | 4.1 | Setup maint page (old and new server) - load balancer team to be around (maybe maint page on akamai) |  |  | 2021-09-25 23:30 | 2021-09-25 23:50 | 20 mins | 4.0 |  | + validation if sites are ok, not randomly - few additional mins (added 15 mins)
ENT-MIDDLEWARE WAS | 4.1.1 | GI3 Portugal - Setup the maint page - old server (new server should be done earlier) |  | MW Team Manish Gurdal / Pradeep Arya Sunday / Ananya Sunday |  |  | 20 mins all |  |  | YES (10 min each) no AKAMAI - in case we face issues with maint - JVMs to be down and move to DNS change | 5:01 | 6:32 JVMs down
ENT-MIDDLEWARE WAS | 4.1.2 | GI3 Greece - Setup the maint page - old server (new server should be done earlier) |  | MW Team Manish Gurdal / Pradeep Arya Sunday / Ananya Sunday | [5 empty] | YES (10 min each) no AKAMAI | 5:01 | 6:32 JVMs down
ENT-MIDDLEWARE WAS | 4.1.3 | GI3 Saudi - Setup the maint page - old server (new server should be done earlier) |  | MW Team Manish Gurdal / Pradeep Arya Sunday / Ananya Sunday | [5 empty] | YES (10 min each) no AKAMAI | 5:01 | 5:42
ENT-MIDDLEWARE WAS | 4.1.4 | GI3 Morocco - Setup the maint page - old server (new server should be done earlier) |  | MW Team Manish Gurdal / Pradeep Arya Sunday / Ananya Sunday | [5 empty] | YES (10 min each) no AKAMAI | 5:01 | 5:42
ENT-MIDDLEWARE WAS | 4.1.5 | GI3 Egypt - Setup the maint page - old server (new server should be done earlier) |  | MW Team Manish Gurdal / Pradeep Arya Sunday / Ananya Sunday | [5 empty] | YES (10 min each) no AKAMAI | 5:01 | 5:42
|  | change DNS to the new Cname |  | Network team | [5 empty] | [14:14] Maykon Salvi/SPO/BR go live- network team: www-o.avon.com.sa --> We will change to new ip 134.65.161.46 during cutover www-o.avon.com.eg --> We will change to new ip 134.65.161.46 during cutover www-o.avon.co.ma --> We will change to new ip 134.65.161.46 during cutoverrep.avon.com.pt --> We will change to sanavoncom.edgekey.net rep.avoncosmetics.gr --> We will change to sanavoncom.edgekey.netwww.sa.avon.com --> We will change to sanavoncom.edgekey.netwww.eg.avon.com --> We will change to sanavoncom.edgekey.netwww.ma.avon.com --> We will change to sanavoncom.edgekey.net- Akamai Promote Europe-NANE-PT-GR v2 live
|  | promote AKAMAI golive |  | Maykon
ENT-MIDDLEWARE WAS | 4.1.6 | Magnolia PR for Egypt (NAME) - Setup the maint page |  | MW Team Manish Gurdal / Pradeep Arya Sunday / Ananya Sunday | [5 empty] | YES (check if only impacted markets has maint page up) | 5:24 | 5:31
ENT-MIDDLEWARE WAS | 4.1.7 | Magnolia PR for Morocco (NAME) - Setup the maint page |  | MW Team Manish Gurdal / Pradeep Arya Sunday / Ananya Sunday | [5 empty] | YES (check if only impacted markets has maint page up) | 5:24 | 5:31
ENT-MIDDLEWARE WAS | 4.1.8 | Magnolia PR for Saudi Arabia (NAME) - Setup the maint page |  | MW Team Manish Gurdal / Pradeep Arya Sunday / Ananya Sunday | [5 empty] | YES (check if only impacted markets has maint page up) | 5:24 | 5:31
MY-AVON-STORE-APSUPT-GLOBAL | 4.1.9 | MAS Portugal - Setup maintenance page |  | Levente Kiraly |  |  | 20 mins all |  |  | enable maintenance page for PT and GR log in to MST select Portugal, select Online Store, General, set IsMaintenancePageOn to true select Greece, select Online Store, General, set IsMaintenancePageOn to true restart shop.icena application pool on all EMEA non-UK webservers (web1-6) disable ODE for PT and GR log in to EMEA shared server go to ODE folder remove PT (26) and GR (61) from the config file MarketsToProcess | 5:01 | 5:12
MY-AVON-STORE-APSUPT-GLOBAL | 4.1.10 | MAS Greece - Setup maintenance page |  | Levente Kiraly |  |  | 20 mins all |  |  |  | 5:01 | 5:12
n/a | 4.1.11 | IMB - Setup the maint page |  | Alexandru | [5 empty] | YES (if needed Pavel on behalf of Alex) | 5:17 | 5:22
n/a | 4.1.12 | Avon Grow (EG and MA) - setup maintenance page |  | Owen (tbc if we have dev) |  |  | 20 mins |  |  | communicate to markets: New AGS PROD URL (https://ags-ws-eu-ams.prod.avon.com/agws/) will be down during migration/cut-over period. Once DB data migrated then MW team will bring up the new AGS URLs.
GWE-DEVELOPERS | 4.1.13 | Avon On - disable orders |  | Sai Chadalapaka | [5 empty] | NO maint page, disabling orders | 5:32 | 5:58
| 4.1.14 | MAIMS Egypt Billing process to be stopped |  | Marko Nasef |  |  | 1 min |  |  | stop when bill is done
| 4.1.15 | MAIMS Saudi Billing process to be stopped |  | Hassan Alsadig |  |  | 1 min |  |  | stop when bill is done
| 4.1.16 | MAIMS Greece Billing process to be stopped |  | Giouli Fanouraki |  |  | 1 min |  |  | stop when bill is done
| 4.1.17 | MAIMS Portugal Billing process to be stopped |  | Manuel João |  |  | 1 min |  |  | stop when bill is done
| 4.1.18 | MAIMS Morocco Billing process to be stopped |  | Manuel João |  |  | 1 min |  |  | stop when bill is done
|  | Disable selection rules on billing side |  | Billing operators (Gergo to inform)
|  | STOP WE interfaces to GI3 |  | Paulo |  |  | N/A |  |  | covered by stopping billings
| 4.1.19 | New Payment GW (APEXX) |  | Zoli | [5 empty] | no maintenance page, it is accessible only via GI3
| 4.1.20 | MAIMS PT, MO |  | Paulo | [5 empty] | no need maint
| 4.1.21 | MAIMS EG, SA, GR |  | HCL AS400 | [5 empty] | no need maint
| 4.1.22 | FUSE |  | Constantino | [5 empty] | NO maint
| 4.1.23 | NOEL |  | Jozsef Bodnar | [5 empty] | NO, but request to avoid using
| 4.1.24 | IMT |  | Anton K | [5 empty] | No
| 4.1.25 | AGS3 = Choice services |  | Infrasettings, Zoli | [5 empty] | NO, stay online
| 4.1.26 | GOMAC 7.0 (Linx) |  | Sławek | [5 empty] | No
created | 4.2 | PREPARATIONS BEFORE APPS STOP |  |  | 2021-09-25 23:50 | 2021-09-26 00:20 | 30 mins | 4.1
ENT-AWS-Terraform | 4.2.1 | Boomi Deploy Service Registry master branch via Jenkins in AWS |  | AWS DevOps (Task is usually assigned to Kapendra Singh) |  |  | 10 mins |  |  | Deploy master branch of service-registry-for-ipaas-infra-tf to PROD via Jenkins (https://jenkins.devops-prod.aws.avon.com/job/API%20GW/job/API%20GW%20Prod/job/Service%20Registry%20for%20iPaaS/job/Service%20Registry%20infra/) Add new entries in Secrets Manager (AWS account #121642321945): * Copy serviceReg/WEBEPL2P with its secret values to serviceReg/WEBEPTP
ENT-AUTOSYS | 4.2.4 | Stop OLD PROD (RYE*) Batch autosys jobs - use Michal's spreadsheet to list out all the jobs for Miguel. See tab "Jobs to be put offline" |  | autosys team / Miguel |  |  | 30 mins |  |  | to be confirmed if MAIMS related jobs are covered | 7:12 | 7:20
n/a | 4.2.6 | PDF reports: switch to the new FTP hostname |  | Geroge Thanos / Manuel Joao / Paulo - MAIMS |  | anytime when pdf reports concluded | 15 mins |  |  | new hostname to be shared in advance Ivan to Paulo & George Thanos * In Portugal/Morocco/Egypt and Saudi MAIMS sends ZM/SL/DSM PDF reports to: server IP: 134.65.189.42 * In GREECE, MAIMS do not send any PDF reports to Gi3. All and any GI3 PDF reports are sent outside MAIMS and trough an application developed from George Thanos. * IF the remote server destination of these PDF is to be changed, we need to know IN ADVANCE the new IP address, the new server name ) , the new folders and the new credentials, in order to be configured on MAIMS still on 24-09-2021 afternoon and by George Thanos on his application - New servers are already created. On the 25-09 it will be a question of moving existing FTP processes to the new servers - GREECE - MAS FTP transfer was already moved to new server and tested between Paulo and Michal Elias. - GREECE – PDF REPORTS FTP FOR GI3 - This will be covered outside MAIMS system by @George Thanos/ATH/GR - PT, EGY,MOR and SAU – PDF REPORTS FTP FOR GI3 – This will be covered by me, @Manuel Joao/SNA/PT and @Paulo Fortes during the day of 25-09 at any point in time after the conclusion of the daily PDF REPORTS FTP FOR GI3 processes. - PT and GR – PDF INVOICES FOR GI3 - This will be covered by me, @Manuel Joao/SNA/PT and @Paulo Fortes on 25-09 AFTER CONCLUSION OF LAST Billing in PT and GR | 7:16 | 7:16
n/a | 4.2.6.1 | change endpoints for PDF invoices (PT and GR) |  | Geroge Thanos / Manuel Joao / Paulo - MAIMS | [5 empty] | AMSLXGI3PBT1.DC.AVON.NET 10.160.140.9 * In Portugal MAIMS sends INVOICE PDF ( for GI3-Order Tracking page ) to: server IP: 10.200.130.190
created | 4.3 | APPLICATIONS STOP |  |  | 2021-09-26 00:20 | 2021-09-26 00:50 | 30 mins | 4.2
ENT-MIDDLEWARE WAS | 4.3.1 | Stop old GI3 PT |  | MW Team | [6 empty] | 6:30 | 6:40
ENT-MIDDLEWARE WAS | 4.3.2 | Stop old GI3 GR |  | MW Team | [6 empty] | 6:30 | 6:40
ENT-MIDDLEWARE WAS | 4.3.3 | Stop old GI3 MO |  | MW Team | [6 empty] | 6:30 | 6:40
ENT-MIDDLEWARE WAS | 4.3.4 | Stop old GI3 EG |  | MW Team
ENT-MIDDLEWARE WAS | 4.3.5 | Stop old GI3 SA |  | MW Team
ESO-OMS-ADMIN | 4.3.7 | Stop GOMAC processes for NAME/PT/GR (including billing processes) |  | Gergo | [6 empty] | 7:30 | 7:40
Disable Zoltan Engine subsystems
DCO-SPO-SERVER-SUPT-BR | 4.3.8 | Make sure queues are empty (make sure new are empty) |  | Maykon |  |  |  | 4.3.7
created | 4.4 | DB ACTIVITIES - names of dbs changes |  |  | 2021-09-26 00:50 | 2021-09-26 07:40 | 410 mins | 4.3 |  | 6h 50 min
|  | dropping and restoring from L0 backup for 2 databases |  |  |  |  | 150 mins
ENT-ORACLE | 4.4.2 | take level 1 backup dbs |  | Ishan |  |  | 50 mins | 4.4.1 |  |  | 7:56 | 8:17
ENT-ORACLE | 4.4.2.1 | webeptp (ODS db) |  | Ishan, Nakul
ENT-ORACLE | 4.4.2.3 | gmcgptp |  | Ishan, Nakul
ENT-ORACLE | 4.4.4 | DBS - recover and upgrade them (l1 backup) |  | Ishan |  |  | 150 mins | 4.4.3 |  | level 0 restore- 2.5 hours for gmcgptp and 1.5 hours for webeptp upgrade database -- 60 minutes | 8:25 | 10:13
ENT-ORACLE | 4.4.4.1 | webeptp (ODS db) |  | Ishan
ENT-ORACLE | 4.4.4.3 | gmcgptp |  | Ishan
| 4.4.4.4 | webwas2p (leave intact) | [7 empty] | Create session DB based on QAF webwasqf scripts: amslxgi3eupdb2.dc.avon.net/webwas2p
| 4.4.4.6 | agscep - (leave intact) | [7 empty] | No change is needed for the db side (confirmed by Shankar)
| 3.1.4.3 | Get data counts | Ivan/Ishan | Ivan |  |  | 10 mins
| 3.1.4.4 | cleanup - remove PL data partitions GI3 ODS | Ishan, Nakul | Ishan |  |  | 25 mins | 4.4.4.1 |  | partition clean up : 25 mins
|  | scripts from Gergo to DBAs |  | DBAs |  |  | 5 mins
| 3.1.4.5 | cleanup - remove UA, KZ, KG data partitions LINX | Gergo | Gergo |  |  | 40 mins | 4.4.4.2
| 3.1.4.6 | Get data counts | Ivan/Ishan | Ivan |  |  | 10 mins
ENT-ORACLE | 4.6.16 | DDL install db objects (external tables and directory changes) |  | Ishan |  |  | 5 mins |  |  | after db restoration directory changes : 5 minutes |  | 10:24
| 4.4.6 | run db stats jobs for 2 dbs (listed above) |  | Ishan |  |  | 0 mins | 4.4.4 |  | not stopping anything | 10:13 | ? Tbc on chat
created | 4.5 | TO BE DONE DURING DB ACTIVITIES |  |  | 2021-09-26 00:50 | 2021-09-26 07:40 | 120 mins | 4.3
ENT-AS400 DCO-SPO-SERVER-SUPT-BR | 4.6.15 | MQ to be changed for AS400 - sureshraj@hcl.com - NAME, GR Paulo - PT, MA -> MAIMS team & vendor change MQ (Suresh) - it will be done both for GOMAC and GI3 (the same MQ) - MQ changes to be shared with Paulo when Pavel is back |  | Maykon / MW / AS400 MQ team Suresh / vendor for PT /Manuel Joao (PT, MA) | 2021-09-26 02:00 |  | 30 mins |  |  | to make sure vendor is available @6 am, if not - what is the latest moment we can start this task Some weeks ago the remote server destination linked with the MQ sending channel from MAIMS to LINX/GI3 FOR QA ENVIRONMENT was changed to: dlslxmq9qcon3.dc.avon.net(1429) I assume that now that MQ sending channel from MAIMS to LINX/GI3 FOR PRODUCTION ENVIRONMENT will have to be changed also, correct? IF that is the case , then we need to receive the new details for the new remote server destination for all countries. MQ changes in the PT and MOR AS400 will need to be done between MAIMS/LUSODATA. For Egypt, Greece and Saudi HCL will need to make those changes on those As400. This is not under MAIMS COE control Changes need to be coordinated with HCL teams managing the remote destinations servers/MQ in order to RESET channels - PT and MOR - This will be covered by me, @Manuel Joao/SNA/PT and @Paulo Fortes on 25-09 AFTER CONCLUSION OF LAST Billing in PT and MOR in coordination and alignment with @Maykon Salvi/SPO/BR - GR, EG and SAU - This will NOT be covered by MAIMS COE- @Maykon Salvi/SPO/BR I assume that this is already scheduled and agreed with proper teams, right? | 10:36 | 10:43
DCO-SPO-SERVER-SUPT-BR | 4.5.1 | resync NAS folders GI3 - only PDFs |  | Maykon |  |  | 60 mins |  |  | /mounts/gi3_prod_ftp/reports/PT /mounts/gi3_prod_ftp/reports/GR /mounts/gi3_prod_ftp/reports/SA /mounts/gi3_prod_ftp/reports/MO /mounts/gi3_prod_ftp/reports/EG | 7:10 | 7:26
|  | resynch changed users and group owners for those folders |  | Maykon
DCO-SPO-SERVER-SUPT-BR | 4.5.2 | For GI3 content refresh engine: change to the new ip on /etc/hosts on dlslxpsmsgwap1 |  | Maykon |  |  | 10 mins |  |  | NEEDED ONLY IF AKAMAI SMS gateway - for GI3 Content Refresh engine only done once again when maint lifted |  | 8:16
ENT-AUTOSYS | 4.5.5 | supportal new db configuration |  | Michal |  |  | 5 mins |  |  |  | 8:00 CET | 8:15 CET
ENT-AUTOSYS | 4.5.6 | ezBrochure change point NAME/PT/GR markets to new DB (XML config change) |  | Michal |  |  | 10 mins |  |  |  | 8:10 CET | 8:15 CET
created | 4.6 | SWITCH TO NEW DATABASES |  |  | 2021-09-26 07:40 | 2021-09-26 08:40 | 60 mins | 4.4
GOMAC part
ESO-OMS-ADMIN | 4.6.1 | redirect db connection GOMAC AMSMSPPTLINX1 (GOMAC) to new db 19C - amslxgi3eupdb2.dc.avon.net:1521/gmcgptp |  | Gergo |  |  | 60 mins |  |  | to be tested when dbs are done | 10:26 | 10:31
ESO-OMS-ADMIN | 4.6.2 | redirect db connection GOMAC AMSMSPPTLINX1 (ODS) to new db 19C - amslxgi3eupdb2.dc.avon.net:1521/webeptp |  | Gergo | [5 empty] | to be tested when dbs are done
ESO-OMS-ADMIN | 4.6.3 | point GOMAC prod to new MQ |  | Gergo | [5 empty] | PRODGOMAC
ESO-OMS-ADMIN | 4.6.4 | start all subsystems on AMSMSPPTLINX1 (GOMAC) new db |  | Gergo |  |  |  | 4.5.4
ESO-OMS-ADMIN | 4.6.5 | admin GOMAC verify if system is working |  | Gergo
ESO-OMS-ADMIN | 4.6.6 | redirect db connection AMSMSPPTLINX2-4 (GOMAC) to new db 19C - amslxgi3eupdb2.dc.avon.net:1521/gmcgptp |  | Gergo |  |  |  | 4.6.1 |  |  | 10:31 | 10:57
ESO-OMS-ADMIN | 4.6.7 | redirect db connection GOMAC AMSMSPPTLINX2-4 (ODS) to new db 19C - amslxgi3eupdb2.dc.avon.net:1521/webeptp |  | Gergo | [5 empty] | ODS need to be ready
ESO-OMS-ADMIN | 4.6.8 | point GOMAC to new MQ |  | Gergo | [5 empty] | to be confirmed if MAIMS will be covered in this step otherwise we need to change MQ from AS400 side as well
ESO-OMS-ADMIN | 4.6.9 | start the subsystems on all nodes (GOMAC) new db |  | Gergo
ESO-OMS-ADMIN | 4.6.10 | Validate GOMAC offer feed Run it manually for all 5 markets |  | Gergo
ESO-OMS-ADMIN | 4.6.11 | Validate time period subsystem Run it manually for all 5 markets |  | Gergo
ESO-OMS-ADMIN | 4.6.12 | admin GOMAC verify if system is working |  | Gergo
ESO-OMS-ADMIN | 4.6.13 | GOMAC waiting now for prod checkout |  | Gergo
|  | test WE20 manually |  | Paulo + Marko, Hassan, Giuli, Manuel, Pavel, Michal | [5 empty] | no additional time is needed
|  | START WE interfaces |  | Paulo | 2021-09-26 06:30 |  |  | 4.6.17 |  | no additional time is needed
n/a |  | Release MAIMS activities - tbc with Paulo |  | Paulo (same ppl closed billing ) |  |  |  | 4.6.13 |  | for MAIMS start here normal day send orders received, send interfaces to GI3, received billed orders from Linx and data coming from GI3 NOEL - risk to be checked Avon Grow
n/a | 4.1.16 | MAIMS Egypt Billing process to be started |  | Marko Nasef | [5 empty] | automatic proceeding orders
n/a | 4.1.17 | MAIMS Saudi Billing process to be started |  | Hassan Alsadig | [5 empty] | automatic proceeding orders
n/a | 4.1.18 | MAIMS Greece Billing process to be started |  | Giouli Fanouraki | [5 empty] | they are not sending orders during weekend, here only - manually
n/a | 4.1.19 | MAIMS Portugal Billing process to be started |  | Manuel João | [5 empty] | automatic proceeding orders
n/a | 4.1.20 | MAIMS Morocco Billing process to be started |  | Manuel João | [5 empty] | automatic proceeding orders
non-GOMAC part
n/a | 4.2.2 | Boomi “PROD EG GR” environment WEBE connection config needs to be updated |  | Zoli |  |  | 5 mins |  |  | before 4.6.14 Details: Update CONN.Common.Oracle WEBE ODS * Host: amslxgi3eupdb2.dc.avon.net * Port: 1521 * DB name: webeptp
n/a | 4.6.14 | ePayment and eInvoice Boomi processes need to be started |  | Zoli |  |  | 5 mins |  |  | when new DBs are up [EG EPAY] (Sched) Processing Events Main.Sched.DB.ProcessInvoices [EG eInvoice] (Sched) Process invoices [ATM] (Sched) PT data sync [PT EPAY] (Sched) Processing Events [GR EPAY] (Sched) Processing Events
ENT-AUTOSYS | 4.6.14 | supportal configuration checkout if works with new db |  | Michal |  |  | 5 mins |  |  |  | 8:00 CET | 8:15 CET
ENT-AUTOSYS | 4.6.17 | DML scripts execution (autojob details) |  | Michal |  |  | 10 mins |  |  |  | 10:30 | 10:43
ENT-AUTOSYS | 4.6.18 | Run selected autosys jobs manually from cmd line and verify they are not failing |  | Michal |  |  | 15 mins |  |  |  | 10:43 | 10:53
created | 4.7 | RESTARTING APPS |  |  | 2021-09-26 08:40 | 2021-09-26 09:40 | 60 mins
ENT-MIDDLEWARE WAS | 4.7.1 | restart GI3 PT, GR, MO, SA, EG new environment |  | MW |  |  | 60 mins |  |  | https://amslxgi3pdmgr1.dc.avon.net:14001/ibm/console | 11:14 | 11:17
ENT-MIDDLEWARE WAS | 4.7.2 | restart AGS classic ags-ams new environment |  | MW |  |  | 60 mins |  |  | https://amslxgi3pdmgr1.dc.avon.net:14001/ibm/console | 11:02 | 11:09
ENT-MIDDLEWARE WAS | 4.7.3 | restart AGS3 myavon-ams new environment |  | MW |  |  | 60 mins |  |  | https://amslxags3pdmgr1.dc.avon.net:14001/ibm/console | 11:02 | 11:09
created | 4.8 | SMOKE TESTS (sanity - not needed) |  |  | 2021-09-26 09:40 | 2021-09-26 10:40 | 60 mins | 4.7
GWE-PRJ-MGMT | 4.8.1 | smoke tests GI3 - 5 markets we need more people to test |  | Anandhi |  |  | 60 mins |  |  | 12:45 AR ok; 13:21 CH; UY 13:15 | 11:20 | 13:15
n/a | 4.8.3 | smoke tests AGS |  | Shankar |  |  | 60 mins |  |  |  | 11:18 | 11:33
n/a | 4.8.4 | smoke tests AGS3 (db checked 10:32 by Zoli) |  | Zoli |  |  | 60 mins |  |  | NOEL, FUSE, | 11:20 | 11:23
n/a | 4.8.5 | Run EG eInvoice manually |  | Zoli
created | 4.9 | Enable autosys jobs |  |  | 2021-09-26 10:40 | 2021-09-26 11:40 | 60 mins | 4.8.1
ENT-AUTOSYS | 4.9.1 | Put new autosys jobs back online. See tab "Jobs to be put online" |  | Miguel |  |  | 30 mins |  |  |  | 14:20 | 14:50
ENT-AUTOSYS | 4.9.2 | Check for any job failures - AUTO_JOB_DETL, autsys log files |  | Michal |  |  | 30 mins | 4.9.1 |  |  | 14:50 | 15:18
created | 4.10 | CHANGES IN SATELLITE APPS - endpoints to be changed |  |  | 2021-09-26 10:40 | 2021-09-26 12:10 | 90 mins | 4.8.1, 3, 4
| 4.10.1 | MAS Portugal and Greece |  | Levente Kiraly |  |  | 45 mins
MY-AVON-STORE-APSUPT-GLOBAL | 4.10.1.1 | MAS Portugal and Greece - change AGS endpoint address |  | Levente Kiraly |  |  | 15 mins |  |  | * set up new classic AGS URL - log in to MST # select Portugal, select Wcf Services, Gi3Settings, set BaseAddress to https://ags-ws-eu-ams.prod.avon.com/agws/ # select Greece, select Wcf Services, Gi3Settings, set BaseAddress to https://ags-ws-eu-ams.prod.avon.com/agws/ - restart the shopsvc application pool on all EMEA non-UK webservers (web1-6) - smoke test # try to register a new user * check data transfer in DocumentDB for success * if you don’t see any change then check - MST, Wcf Services, General, EnableGi3MergeCustomer - and MST, Wcf Services, Gi3Settings, LogGi3Communication - if you change them then please change it back afterwards | 13:10 | 15:05
MY-AVON-STORE-APSUPT-GLOBAL | 4.10.1.2 | MAS Portugal and Greece - try to register new user |  | Levente Kiraly |  |  | 15 mins |  |  |  | 13:10 | 15:05
MY-AVON-STORE-APSUPT-GLOBAL | 2.6.13 | check the connectivity to AGS classic and AGS 3 endpoints |  | Levente Kiraly |  |  | 15 mins |  |  | This is basically a quick smoke-test from our side after the cutover, Levente will do it.
n/a | 4.10.2 | MAGNOLIA PR (Swetha Haridasan Uvaraj Murugesan as Neeharika will be off) |  | Uvaraj Murugesan |  |  | 90 mins |  |  | Swetha Haridasan, | 15:05
GWE-APP-SPT | 4.9.3.1 | Magnolia PR site for NAME markets - Change AGS endpoints |  |  |  |  | 30 mins |  |  | ags-ws-eu-ams.prod.avon.com | 13:10 | 13:13
GWE-APP-SPT | 4.9.3.3 | Magnolia testing - quick checkout |  |  |  |  | 60 mins |  |  |  | 13:20
GWE-DEVELOPERS | 4.9.5 | Avon On |  | Sai Chadalapaka |  |  | 30 mins
GWE-DEVELOPERS | 4.9.5.1 | Avon On - change endpoints |  | Sai Chadalapaka |  |  | 15 mins |  |  |  | 14:12 | 14:24
GWE-DEVELOPERS | 4.9.5.3 | Avon On - smoke testing (login only maint page is up) |  | Sai Chadalapaka |  |  | 5 mins
n/a | 4.9.6 | IMB endpoints update |  | Alexandru |  |  | 10 mins |  |  |  | 9:23 | 9:26
n/a | 4.9.6 | FUSE endpoints update |  | Pooja |  |  | 10 mins |  |  |  | 9:23 | 9:26
n/a | 4.9.2 | FUSE change webservice domain for 3 markets (switch FUSE to new AGS3 url) - POSTPONED TILL MONDAY/TUESDAY the reps and sales leaders will be able to go to Avon Connect (FUSE) through the vendorlinks located in GI3 |  | Constantino / Pooja Upadhyay <pooja.upadhyay@fuseuniversal.com> | [5 empty] | we need to have the new data sources on WebSphere before applying the change on the custom login page (to be done by Pooja) fuseSSO goes to GI3 to get some rep's kpis and send them to FUSE so we need the new GI3 database in place before applying the change
| 4.9.10 | NOEL |  |  |  |  | 10 mins |  |  | CA APIM change | in morning
ENT-INTEGRATION-SERVICES | 4.9.10.1 | switch NOEL to new AGS3 url |  | Laszlo Gecse | [5 empty] | myavon-ws-eu-ams.prod.avon.com
| 4.9.11 | Avon Grow |  | Ivetta Halajova | [5 empty] | Switch to new AGS PROD URL as given above to only EG & MA markets. | in morning
ENT-INTEGRATION-SERVICES | 4.9.10.1 | switch Avon Grow to new AGS url |  | Ivetta Halajova | [5 empty] | New AGS PROD URL https://ags-ws-eu-ams.prod.avon.com/agws/
n/a | 4.13 | Business tests - hostfiles for testing |  |  | 2021-09-26 12:10 | 2021-09-26 18:10 | 360 mins |  |  | 6 hours | 15:15
|  | GI3 incl. Billing processes (all markets) |  |  |  |  | 3h |  |  |  | 15:15 | 21:50
|  | Greece |  | Ioanna Tsoukala
|  | Portugal |  | Rui Gaspar
|  | Saudi Arabia |  | Noura Alshuaibi
|  | Morocco |  | Imane & Youssef Houdna
Egypt
|  | Magnolia PR (NAME markets) | [8 empty] | 15:15 | 19:20
Saudi Arabia
Morocco
Egypt
|  | MAS (PT and GR) | [7 empty] | MAS TEAM to support business testing * prepare hosts file for business - check a webserver’s IP address from a higher number (for example web3 or web6) - give the IP to the market * support market testing if they find something
Greece
Portugal
IMB
Avon Grow (EG and MA)
|  | Morocco |  | Imane & Youssef Houdna
Avon On
|  | Morocco |  | Imane & Youssef Houdna
|  | New Payment GW (APEXX) - ? | [7 empty] | ePayment
MAIMS (?)
Avon Connect - FUSE
|  | Morocco |  | Imane & Youssef Houdna
NOEL
GOMAC 7.0 (Linx) (?)
|  | Morocco (MAIMS Linx) |  | Nadia Safid | [5 empty] | Nadia.safid@avon.com
n/a |  | Buffer for backout |  |  | 2021-09-26 18:10 | 2021-09-26 23:10 | 300 mins |  | N/A | 5 hours
n/a | 4.10 | GO / NO GO decision |  | Irena, Monika, Business Team, ITBP, Tech Team | 2021-09-26 23:10 |  | 10 mins
created | 4.12 | Lifting maint pages (list to be updated) |  |  | 2021-09-26 23:20 | 2021-09-27 00:05 | 45 mins
DCO-SPO-SERVER-SUPT-BR | 4.5.2 | For GI3 content refresh engine: change www.ar.avon.com to the new ip on /etc/hosts on dlslxpsmsgwap1 - in case we introduce AKAMAI we need it |  | Maykon |  |  | 10 mins |  |  | t. 250: SMS gateway - for GI3 Content Refresh engine only done once again when maint lifted |  | 22:00
ENT-MIDDLEWARE WAS | 4.5.3 | GI3 Portugal - lift maint page from new server |  | MW Team |  |  | 45 mins all
ENT-MIDDLEWARE WAS | 4.5.4 | GI3 Greece - lift maint page from new server |  | MW Team
ENT-MIDDLEWARE WAS | 4.5.5 | GI3 Saudi - lift maint page from new server |  | MW Team
ENT-MIDDLEWARE WAS | 4.5.6 | GI3 Morocco - lift maint page from new server |  | MW Team
ENT-MIDDLEWARE WAS | 4.5.7 | GI3 Egypt - lift maint page from new server |  | MW Team
ENT-MIDDLEWARE WAS | 4.5.8 | Magnolia PR for Egypt (NAME) - lift maint page |  | MW Team
ENT-MIDDLEWARE WAS | 4.5.9 | Magnolia PR for Morocco (NAME) - lift maint page |  | MW Team
ENT-MIDDLEWARE WAS | 4.5.10 | Magnolia PR for Saudi Arabia (NAME) - lift maint page |  | MW Team
MY-AVON-STORE-APSUPT-GLOBAL | 4.5.11 | MAS Portugal - lift maint page |  | Levente Kiraly |  |  | 45 mins |  |  | * remove maintenance page - log in to MST # select Portugal, select Online Store, General, set IsMaintenancePageOn to false # select Greece, select Online Store, General, set IsMaintenancePageOn to false - restart shop.icena application pool on all EMEA non-UK webservers (web1-6)
MY-AVON-STORE-APSUPT-GLOBAL | 4.5.12 | MAS Greece - lift maint page |  | Levente Kiraly |  |  | 45 mins
n/a | 4.5.13 | IMB - lift maint page |  | Pavel Gas / Alex |  |  | 45 mins |  |  | YES (Pavel on behalf of Alex)
| 4.1.14 | Avon Grow |  | Ivetta Halajova |  |  | 45 mins
GWE-DEVELOPERS | 4.1.15 | Avon On - enable orders |  | Sai Chadalapaka |  |  | 45 mins
N/A | 4.13 | Business tests - part that can be done when maint page is lifted |  |  | 2021-09-27 00:05 |  |  |  |  | END of DOWNTIME
ENT-AUTOSYS | 4.8.2 | Content refresh - test the engine manually (connectivity - final proof) |  | Michal |  |  | 15 mins | 4.8.1 |  |  | 12:45 | 12:50
|  | Avon On - orders are enabled and can be tested | [8 empty] | 22:20 | 22:55
|  | Magnolia PR site - will be tested when page is lifted | [8 empty] | 22:15 | 22:21
|  | IMB - can be tested when maint page is lifted | [8 empty] | 19:10 | 20:00 | 50min
NOEL
POSTCUTOVER
| 5.1 | Disable "migrate" deployment option and leave prod only or next days |  | Anton Koptelov | 2021-07-31 |  |  |  |  | waiting Anton's confirmation
| 5.2 | NOEL testing / verification |  | Guido/Ivan/Jozsef | [5 empty] | waiting for Guido to process one testing order
EIM-INFDEL-ALM-CDW-MS | 5.3 | CDW (ftp, hostfile change) |  | Satyam Singh |  | 2021-08-03 |  |  | DONE
EIM-INFDEL-ALM-CDW-MS | 5.3.1 | CDW - Pay special attention to AR Leads CDW feeds. Do we need CDW team to change anything? Still unclear, check it with Zoltan and Michal. |  | CDW: satyam.singh@avon.com |  | 2021-08-03 |  |  | DONE
EIM-INFDEL-ALM-CDW-MS | 5.3.2 | CDW - MAS Rep feed - change SFTP endpoint (can be done till end of next campaign) - We are not ready! Will have to be postponed. |  | Satyam Singh |  | 2021-08-03 |  |  | DONE
| 5.4 | Ensure jobs to recalculate DB stats will be scheduled same as they were in old PROD. |  | Ishan | [5 empty] | to make sure
| 5.5 | AKAMAI |  | Maykon |  |  |  |  | DONE
| 5.6 | Camprep environment ready (after GoLive) |  | Irena |  |  |  |  | DONE | will be taken separately for all camprep envs
| 5.7 | Metting on IMT / offer feed checkout process |  | Pavel, Ivan, Gergo, Anton, Hernan | [5 empty] | after Pavel's holidays
| 2.4 | Decommission and shutdown |  | Irena | [5 empty] | Please search for these when adding the CI and it will pop up I believe those will be Jive, vtrends and gomacarssp respectively
DECOM | 2.1.1 | jive will be decom for AR, Chile (Forums) - just stop JVMs |  | Maykon / Imre | 2021-07-14 | 2021-07-14 |  |  |  | confirmed by Hernan and Ivan 12.07.2021; server will be decom after GoLive
|  | JVMs stopped |  | Maykon | 2021-07-14 | 2021-07-14 |  |  | DONE
|  | database to be shitdown / decom |  | Irena | 2021-07-15 | 2021-07-15
DECOM | 2.1.2 | VTTrans will be decom for AR Chile - just stop |  | Maykon / Imre | 2021-07-14 | 2021-07-14 |  |  |  | confirmed by Hernan and Ivan 12.07.2021; server will be decom after GoLive
JVMs stopped
|  | database to be shutdown / decom |  | CRQ Normal
SHUTDOWN | 2.1.3 | shutdown socialselling database for AR (old) + remove from new server (new - CHG not needed, Ishan can do that for new) |  | Imre | 2021-08-02 |  |  |  |  | confirmed by Hernan and Ivan 12.07.2021; stooped already we can shutdown even now - decom database after 1 week
|  | stopped new |  |  | 2021-07-22 |  |  |  | DONE | NEW: gmcarssp dlslxgi3lapdb2
shutdown
Decommission
DECOM | 2.1.4 | gmcarssp - decomm database |  | Imre | 2021-07-14
stopped
shutdown
Decommission

## backout plan 26st Sep
No | Task description | Responsible | START CET timezone | Start AR timezone | End AR TZ | Duration | Predecesor | Status | Comments
BACKOUT PLAN
5.1 | stop new autosys jobs | Miguel |  |  |  | 30 mins
5.2 | Preps before we stop apps on new |  |  |  |  | 30 mins
| Avon On - disable orders | Sai
MAIMS - billing to be stopped
| Ensure that queues are empty | Maykon
| Interface files: old FTP host for AS400 (plus make sure nothing is sent from AS400 to GOMAC) | Maykon / MW / AS400 MQ team Suresh / vendor for PT /Manuel Joao (PT, MA)
| PDF reports: switch to the old FTP hostname change endpoints for PDF invoices | Geroge Thanos / Manuel Joao / Paulo - MAIMS
| New IMT - Point TS to old DB (what need to be changed to what - Michal to help / details) | Anton
5.3 | APPS STOP |  |  |  |  | 30 mins
| Stop new GI3 NAME markets | MW team /Sweta
| Stop new GI3 PT | MW team /Sweta
| Stop new GI3 GR | MW team /Sweta
| Stop GOMAC processes for NAME/PT/GR | Gergo
5.4 | Tasks before we switch apps to old db and endpoints for sat apps |  |  |  |  | 60 mins
| change www.ar.avon.com to the old ip on /etc/hosts on dlslxpsmsgwap1 | Maykon
| purge AKAMAI cache (5 markets) | Maykon
| modify GI3 urls to the old IPs | Amit | [6 empty] | old servers pick up traffic backout origdc-www.ar.avon.com --> We will change to new ip 134.65.201.166 during cutover origdc-www-o.avon.com.ar --> We will change to new ip 134.65.201.168 during cutover origdc-www.cl.avon.com --> We will change to new ip 134.65.201.160 during cutover www-o.avon.com.uy -> We will change to new ip 134.65.201.160 during cutover www-o.avon.cl -> We will change to new ip 134.65.201.160 during cutover webeservicesla.avon.com -> We will change to new ip 134.65.201.160 during cutover www.uy.avon.com -> change cname to 134.65.201.160
5.5 | Switch to old databases |  |  |  |  | 30 mins
| start old databases | Ishan
| redirect db connection GOMAC SOLA node 1 (GOMAC) to old db | Gergo
| redirect db connection GOMAC SOLA node 1 (ODS) to old db | Gergo
| point old GI3 to new MQ | Maykon
| supportal old db configuration | Michal
| start all subsystems on node 1 (GOMAC) old db | Gergo
| admin GOMAC verify if system is working | Gergo
| redirect db connection SOLA node 2 (GOMAC) to old db | Gergo
| redirect db connection GOMAC SOLA node 2 (ODS) to old db | Gergo
| start all subsystems on node 2 (GOMAC) old db | Gergo
| admin GOMAC verify if system is working | Gergo
| GOMAC waiting now for prod checkout | Gergo
5.6 | Starting apps |  |  |  |  | 30 mins
| start GI3 for5 markets old environment | HCL MW
| Content refresh - test the engine manually (connectivity - final proof) | Michal
| ezBrochure change point SMG markets to new DB (XML config change) | Michal
5.7 | Smoke tests |  |  |  |  | 60 mins
| smoke tests GI3 - 3 markets | Jey
Raja
5.8 | Start old autosys jobs |  |  |  |  | 60 mins
| Put new Dallas autosys jobs back online. See tab "Jobs to be put online" | Miguel
| Logfiles, tabels for jobs to be checked | Michal
5.9 | satellite apps endpoints to be changed back to old env & smoke tested (tests when we have jobs done) |  |  |  |  | 120 mins |  |  | can be started anytime
| to be listed | Levente Kiraly
5.10 | Business tests on old env |  |  |  |  | 360 mins

## Timezones
CET | Portugal | Greece | Morocco | Egypt | Saudi Arabia | UTC | Billing end Friday
0:00 | 23:00 | 1:00 | 23:00 | 0:00 | 1:00 |  |  | local time | CET
1:00 | 0:00 | 2:00 | 0:00 | 1:00 | 2:00 |  | PT | 22:30 | 23:30 |  | 20h | SMG: 5:00 - 00:00
2:00 | 1:00 | 3:00 | 1:00 | 2:00 | 3:00 |  | GR | 18:00 | 17:00
3:00 | 2:00 | 4:00 | 2:00 | 3:00 | 4:00 |  | MO | 21:45 | 22:45
4:00 | 3:00 | 5:00 | 3:00 | 4:00 | 5:00 |  | EG | 21:05 | 21:05
5:00 | 4:00 | 6:00 | 4:00 | 5:00 | 6:00 |  | SA | 23:00 | 22:00
6:00 | 5:00 | 7:00 | 5:00 | 6:00 | 7:00
7:00 | 6:00 | 8:00 | 6:00 | 7:00 | 8:00 |  | Billing end Saturday
8:00 | 7:00 | 9:00 | 7:00 | 8:00 | 9:00 |  |  | local time | CET
9:00 | 8:00 | 10:00 | 8:00 | 9:00 | 10:00 |  | PT | 22:30 | 23:30
10:00 | 9:00 | 11:00 | 9:00 | 10:00 | 11:00 |  | GR | manual |  | need confirmation
11:00 | 10:00 | 12:00 | 10:00 | 11:00 | 12:00 |  | MO | 21:00 | 20:00
12:00 | 11:00 | 13:00 | 11:00 | 12:00 | 13:00 |  | EG | 21:15 | 21:15 | confirmed by Marko Nasef
13:00 | 12:00 | 14:00 | 12:00 | 13:00 | 14:00 |  | SA | 23:00 | 22:00 | confirmed by Hassan Alsadiq
14:00 | 13:00 | 15:00 | 13:00 | 14:00 | 15:00
15:00 | 14:00 | 16:00 | 14:00 | 15:00 | 16:00 |  | Billing start Sunday
16:00 | 15:00 | 17:00 | 15:00 | 16:00 | 17:00 |  | PT
17:00 | 16:00 | 18:00 | 16:00 | 17:00 | 18:00 |  | GR
18:00 | 17:00 | 19:00 | 17:00 | 18:00 | 19:00 |  | MO
19:00 | 18:00 | 20:00 | 18:00 | 19:00 | 20:00 |  | EG
20:00 | 19:00 | 21:00 | 19:00 | 20:00 | 21:00 |  | SA | 6:45 | 5:45
21:00 | 20:00 | 22:00 | 20:00 | 21:00 | 22:00
22:00 | 21:00 | 23:00 | 21:00 | 22:00 | 23:00
23:00 | 22:00 | 24:00 | 22:00 | 23:00 | 24:00
24:00 | 23:00 | 25:00 | 23:00 | 24:00 | 25:00

## Contacts and applications SMG
| System | Name | Mail | Group | Mobile | Comments
| PM | Irena Pstrągowska | irena.pstragowska@avon.com | IPC-PMO-PRJMGMT | +48501200470
| PM | Monika Zajączkowska | monika.zajaczkowska@avon.com | IPC-PMO-PRJMGMT | +48789222555
| MW Team | Manish Kumar Gudral |  | ENT-MIDDLEWARE WAS
| GI3 | Pavel Gas | pavel.gas@avon.com | n/a | +420602655005 | Michal and Ivan are substitutions for Pavel
| GI3 | Ivan Ferrer | ivan.ferrer@avon.cpm | n/a | +52 5538769324 | all cutover? Substitution? Mobile to be shared
| GI3 DEV | Jeyachandran Balachandran | Jeyachandran.Balachandran@avon.com | GWE-PRJ-MGMT |  | who from team can be available? Mobile to be shared
| LINX / GOMAC | Gergo Spielmann | gergo.spielmann@avon.com | ESO-OMS-ADMIN | +36308842023 | 4.3.5 Stop GOMAC processes for SMG Once this step comes (even if its earlier than 6:30 CET), please call Haziq If any delays and the above will happen later than 8:30 CET, please call me instead.
| LINX / GOMAC | Haziq Khalil | haziq.khalil@avon.com | ESO-OMS-ADMIN | +60 147209257
| AGS3 | Zoltan Kovacs | zoltan.kovacs@avon.com | n/a | +36 30 34 34 311 | ping on mobile before task
| AGS | Raja
| LEADS LA (smoke) | Raja
| Teamsite | Anoton Koptelov | anton.koptelov@avon.com |  | +79161722706 | not needed task
| MAS | Levente Kiraly | levente.kiraly@avon.com | MY-AVON-STORE-APSUPT-GLOBAL | +36 20 9587884 | Imre Balla is substitution
| IMB | Alexandru Darabam | alexandru.daraban@interactively.eu |  | 0040761342301
| Avon On | Sai Chadalapaka | Sai.Chadalapaka@avon.com | GWE-DEVELOPERS
| NOEL | Jozsef Bodnar | jozsef.bodnar@avon.com | ENT-INTEGRATION-SERVICES
| Autosys jobs | Michal Elias Miguel Poma | michal.elias@avon.com miguel.poma@avon.com | ENT-AUTOSYS
| DB activities | Imre Szabo Ishan Malik Nakul |  | ENT-ORACLE
| AS-400 | Suresh Rajagopal | sureshraj@hcl.com | ENT-AS400
| HCL Middleware Team | Sweta Sinha | sweta-s@hcl.com | ENT-MIDDLEWARE WAS
| HCL Network Team | Amit Kumar | amitkum-ka@hcl.com | ENT-Networkdata | mobile no/ Whatsapp is +918809562513
|  | Maykon Salvi | maykon.salvi@avon.com | DCO-SPO-SERVER-SUPT-BR | +55 (19) 9 8818-4532 +55 11 5546-8694
| MAO | Oliver Neczpal/BDP/HU Tamas Szeremy Jarka Marianne | . | n/a |  | not needed task in SNOW, created in Jira
| Magnolia PR | Uvaraj Murugesan |  | GWE-APP-SPT
| Local markets | Hernan |  |  | +54 911 6904 0022
| Local markets | Antonio |  |  | +54 911 6156 1012
| FUSE | Constantino Pooja Upadhyay | constantino.vazquez@avon.com pooja.upadhyay@fuseuniversal.com | n/a
On Stand-by
| LINX / GOMAC Arch | Tamas Csiba | tamas.csiba@avon.com
| LINX / GOMAC BA | SzeYin Soo Joanna Chan
| HCL DBA | DBA on duty 24/7
| Network | Vitaliy Krikun | vitaliy.krikun@avon.com
| Linux |  |  | ENT-LINUX |  | in case we need support from your team we will reach you
| Security |  |  | ENT-NETWORK SECURITY |  | in case we need support from your team we will reach you
Business testing team
| ePayment testing team | Sergio Miguel Pestana Abreu/SNA/PT <sergio.pestana@avon.com>
Vana Politopoulou/ATH/GR <vana.politopoulou@avon.com>
Agisilaos Koulopoulos/ATH/GR <agisilaos.koulopoulos@avon.com>
|  | Imane Ettaki |  |  | 212672280709

## Jobs to be put offline
This is a cutover task and lists out all the jobs Miguel will put offline
RYE_ALL_LMA_EMAIL_OUT_DAILY
RYE_ALL_LMA_ESCALATION_ALERT_DAILY
RYE_ALL_LMA_ESCALATION_DAILY
RYE_ALL_LMA_INITIAL_ESCALATION_DAILY
RYE_ALL_LMA_REJECTION_ALERT_DAILY
RYE_ALL_LMA_REPORT_DAILY
RYE_ALL_LMA_ZM_REPORT_DAILY
RYE_AR_LMA_MEDIA_SPEND_EXTRACTS_DAILY
RYE_AR_LMA_REJECTION_DAILY
RYE_AR_LMA_USER_LEADS_AUDIT_UPDATE_DAILY
RYE_AR_LMA_USER_LEADS_LOAD_DAILY
RYE_AR_LMA_USER_LEADS_LOAD_DAILY.FW1
RYE_WEBE_APPLY_EMAIL_LAAR_PERIOD_MEDPRI
RYE_WEBE_AUCTION_ORDER_ARG_PERDIC_HIGHPRI
RYE_WEBE_AUCTION_REVIEW_MW_ARG_PERDIC_HIGHPRI
RYE_WEBE_CDW_AR_DAILY_LOWPRI
RYE_WEBE_CDW_AR_DAILY_LOWPRI_FW1
RYE_WEBE_CDW_AR_DAILY_LOWPRI_FW2
RYE_WEBE_CDW_CL_DAILY_LOWPRI
RYE_WEBE_CDW_CL_DAILY_LOWPRI_FW1
RYE_WEBE_CDW_CL_DAILY_LOWPRI_FW2
RYE_WEBE_CDW_RPRTNG_AR_DAILY_MEDPRI
RYE_WEBE_CDW_RPRTNG_AR_DAILY_MEDPRI_FW1
RYE_WEBE_CDW_UY_DAILY_LOWPRI
RYE_WEBE_CDW_UY_DAILY_LOWPRI_FW1
RYE_WEBE_CDW_UY_DAILY_LOWPRI_FW2
RYE_WEBE_CM_LATAM3_DAILY_LOWPRI
RYE_WEBE_COLLECTIONTRANSFERS_ARG_PERDIC_HIGHPRI_FW1
RYE_WEBE_CUSTOMER_REVIEW_ARG_PERDIC_HIGHPRI
RYE_WEBE_DASHBOARD_ARG_DAILY_LOWPRI
RYE_WEBE_DASHBOARD_ARG_DAILY_LOWPRI_FW1
RYE_WEBE_DASHBOARD_ARG_DAILY_LOWPRI_FW2
RYE_WEBE_DASHBOARD_CHL_DAILY_LOWPRI
RYE_WEBE_DASHBOARD_CHL_DAILY_LOWPRI_FW1
RYE_WEBE_DASHBOARD_CHL_DAILY_LOWPRI_FW2
RYE_WEBE_DCE_REPDATA_SMG_DAILY_MEDPRI
RYE_WEBE_DCECDW_CHL_DAILY_LOWPRI
RYE_WEBE_DCECDW_CHL_DAILY_LOWPRI_FW1
RYE_WEBE_DWNLOAD_URUGUAY_PERDIC_CRITPRI
RYE_WEBE_DWNLOAD_URUGUAY_PERDIC_CRITPRI_FW1
RYE_WEBE_DWNLOAD_URUGUAY_PERDIC_CRITPRI_FW2
RYE_WEBE_EWAY_LAAR_PERIOD_MEDPRI
RYE_WEBE_FRESH_AUCTION_ORDER_ARG_PERDIC_HIGHPRI
RYE_WEBE_GENLOGY_LATAM3_PERIOD_MEDPRI
RYE_WEBE_GMASLFOI_ARG_PERDIC_CRTI
RYE_WEBE_HOUSEKEEP_LAAR_DAILY_MEDPRI
RYE_WEBE_IOGMCOFFR_ARG_MEDPRI
RYE_WEBE_IOGMCOFFR_ARG_MEDPRI_FW
RYE_WEBE_IOGMCOFFR_CHL_MEDPRI
RYE_WEBE_IOGMCOFFR_CHL_MEDPRI_FW
RYE_WEBE_IOGMCOFFR_UY_MEDPRI
RYE_WEBE_IOGMCOFFR_UY_MEDPRI_FW
RYE_WEBE_IOTRKG_LAAR_DAILY_LOWPRI
RYE_WEBE_LEAD_RECRUITMENT_ARG_PERDIC_HIGHPRI
RYE_WEBE_MACPAC_ARG_PERDIC_HIGHPRI_FW1
RYE_WEBE_MAOEMAIL_AR_FREQ_LOWPRI
RYE_WEBE_MAOKPI_ARG_PERDIC_CRTI
RYE_WEBE_MIGRATIONREP_ARG_PERDIC_HIGHPRI_FW1
RYE_WEBE_ORDDWNLD_ARG_PERDIC_CRITPRI
RYE_WEBE_ORDDWNLD_ARG_PERDIC_CRITPRI_FW1
RYE_WEBE_ORDDWNLD_ARG_PERDIC_CRITPRI_FW2
RYE_WEBE_ORDDWNLD_CHL_PERDIC_CRITPRI
RYE_WEBE_ORDDWNLD_CHL_PERDIC_CRITPRI_FW1
RYE_WEBE_OTHERDWNLD_ARG_DAILY_CRITPRI
RYE_WEBE_OTHERDWNLD_ARG_DAILY_CRITPRI_FW1
RYE_WEBE_OTHERDWNLD_CHL_DAILY_CRITPRI
RYE_WEBE_OTHERDWNLD_CHL_DAILY_CRITPRI_FW1
RYE_WEBE_PAYMENTS_ARG_PERDIC_HIGHPRI
RYE_WEBE_PAYMENTSGI3_ARG_PERDIC_HIGHPRI
RYE_WEBE_PRCNT_EMAIL_LAAR_PERIOD_MEDPRI
RYE_WEBE_PRODUCTCATEGORIZATION_ARG_PERDIC_HIGHPRI_FW1
RYE_WEBE_PRODUCTINVENTORY_ARG_PERDIC_HIGHPRI_FW1
RYE_WEBE_REFRESH_ARG_PERDIC_HIGHPRI
RYE_WEBE_REFRESH_ARG_PERDIC_HIGHPRI_FW1
RYE_WEBE_REFRESH_ARG_PERDIC_HIGHPRI_FW2
RYE_WEBE_REFRESH_CHL_PERDIC_HIGHPRI
RYE_WEBE_REFRESH_CHL_PERDIC_HIGHPRI_FW1
RYE_WEBE_REFRESH_CHL_PERDIC_HIGHPRI_FW2
RYE_WEBE_REFRESH_URUGUAY_PERDIC_HIGHPRI
RYE_WEBE_REFRESH_URUGUAY_PERDIC_HIGHPRI_FW1
RYE_WEBE_REFRESH_URUGUAY_PERDIC_HIGHPRI_FW2
RYE_WEBE_REPEARNINGS_ARG_DAILY_HIGHPRI_FW1
RYE_WEBE_REPPRFL_EMAILVRFCTN_LAAR_PERIOD_MEDPRI
RYE_WEBE_UIKPI_ARG_DAILY_HIGHPRI_FW1
RYE_WEBE_UNATNDORD_LAAR_DAILY_LOWPRI
RYE_WEBE_VT4ETIS_LAAR_DAILY_LOWPRI
RYE_WEBE_VT4OMS_LAAR_DAILY_LOWPRI
RYE_WEBE_ZEALL_LATAM3_PERIOD_LOWPRI
RYE_LA_HDS_CDWETL_LOAD_FREQ_LOWPRI

## Jobs to be put online
Jobs to be put online | To be tested manually - Michal to give a hint
DLS_ALL_LMA_EMAIL_OUT_DAILY
DLS_ALL_LMA_ESCALATION_ALERT_DAILY
DLS_ALL_LMA_ESCALATION_DAILY
DLS_ALL_LMA_INITIAL_ESCALATION_DAILY
DLS_ALL_LMA_REJECTION_ALERT_DAILY
DLS_ALL_LMA_REPORT_DAILY
DLS_ALL_LMA_ZM_REPORT_DAILY
DLS_AR_LMA_MEDIA_SPEND_EXTRACTS_DAILY
DLS_AR_LMA_REJECTION_DAILY
DLS_AR_LMA_USER_LEADS_AUDIT_UPDATE_DAILY
DLS_AR_LMA_USER_LEADS_LOAD_DAILY
DLS_AR_LMA_USER_LEADS_LOAD_DAILY.FW1
DLS_WEBE_APPLY_EMAIL_LAAR_PERIOD_MEDPRI
DLS_WEBE_CDW_RPRTNG_AR_DAILY_MEDPRI
DLS_WEBE_CDW_RPRTNG_AR_DAILY_MEDPRI_FW1
DLS_WEBE_CM_LATAM3_DAILY_LOWPRI
DLS_WEBE_DCE_REPDATA_SMG_DAILY_MEDPRI
DLS_WEBE_DCECDW_CHL_DAILY_LOWPRI
DLS_WEBE_DCECDW_CHL_DAILY_LOWPRI_FW1
DLS_WEBE_DWNLOAD_URUGUAY_PERDIC_CRITPRI
DLS_WEBE_DWNLOAD_URUGUAY_PERDIC_CRITPRI_FW1
DLS_WEBE_DWNLOAD_URUGUAY_PERDIC_CRITPRI_FW2
DLS_WEBE_EWAY_LAAR_PERIOD_MEDPRI
DLS_WEBE_GENLOGY_LATAM3_PERIOD_MEDPRI
DLS_WEBE_GMASLFOI_ARG_PERDIC_CRTI
DLS_WEBE_HOUSEKEEP_LAAR_DAILY_MEDPRI
DLS_WEBE_IOTRKG_LAAR_DAILY_LOWPRI
DLS_WEBE_LEAD_RECRUITMENT_ARG_PERDIC_HIGHPRI
DLS_WEBE_MAOEMAIL_AR_FREQ_LOWPRI
DLS_WEBE_MAOKPI_ARG_PERDIC_CRTI
DLS_WEBE_ORDDWNLD_ARG_PERDIC_CRITPRI
DLS_WEBE_ORDDWNLD_ARG_PERDIC_CRITPRI_FW1
DLS_WEBE_ORDDWNLD_ARG_PERDIC_CRITPRI_FW2
DLS_WEBE_ORDDWNLD_CHL_PERDIC_CRITPRI
DLS_WEBE_ORDDWNLD_CHL_PERDIC_CRITPRI_FW1
DLS_WEBE_OTHERDWNLD_ARG_DAILY_CRITPRI
DLS_WEBE_OTHERDWNLD_ARG_DAILY_CRITPRI_FW1
DLS_WEBE_OTHERDWNLD_CHL_DAILY_CRITPRI
DLS_WEBE_OTHERDWNLD_CHL_DAILY_CRITPRI_FW1
DLS_WEBE_PAYMENTS_ARG_PERDIC_HIGHPRI
DLS_WEBE_PAYMENTSGI3_ARG_PERDIC_HIGHPRI
DLS_WEBE_PRCNT_EMAIL_LAAR_PERIOD_MEDPRI
DLS_WEBE_REFRESH_ARG_PERDIC_HIGHPRI
DLS_WEBE_REFRESH_ARG_PERDIC_HIGHPRI_FW1
DLS_WEBE_REFRESH_ARG_PERDIC_HIGHPRI_FW2
DLS_WEBE_REFRESH_CHL_PERDIC_HIGHPRI
DLS_WEBE_REFRESH_CHL_PERDIC_HIGHPRI_FW1
DLS_WEBE_REFRESH_CHL_PERDIC_HIGHPRI_FW2
DLS_WEBE_REFRESH_URUGUAY_PERDIC_HIGHPRI
DLS_WEBE_REFRESH_URUGUAY_PERDIC_HIGHPRI_FW1
DLS_WEBE_REFRESH_URUGUAY_PERDIC_HIGHPRI_FW2
DLS_WEBE_REPPRFL_EMAILVRFCTN_LAAR_PERIOD_MEDPRI
DLS_WEBE_UNATNDORD_LAAR_DAILY_LOWPRI
DLS_WEBE_VT4ETIS_LAAR_DAILY_LOWPRI
DLS_WEBE_VT4OMS_LAAR_DAILY_LOWPRI
DLS_WEBE_ZEALL_LATAM3_PERIOD_LOWPRI
DLS_LA_HDS_CDWETL_LOAD_FREQ_LOWPRI

## SMG LL - issues faced
STATUS
DONE | 1. maint page - randomly appeared, Maykon needed to stop JVMs - ROUT C. to be identified -> load balancer issue; to be discuss option to put maint page on AKAMAI
DONE | 2. load balance issue (he is setting up the keep alive that was not set up in the new one - comment from Mayokn on Amit task) - Maykon
DONE | 3. IMT could not update deployment optin (IMT should point to content env, not new db - should be taken into consideration during next implementation - to be taken offline with Gergo)
DONE | 4. we have some issue in the netscaler vip 39 nd we will point to another vip.. i thnk secuity team di not open it well in the firewall.. so we will more to 46 which i working well (Maykon)
Via akamai is not workign to this ip 134.65.201.39
i was not able to load the pages
but this ip is working 134.65.201.46.. so we are moving the new urls to the other vip and adjusting the origdc
for next market.. i think we will have to test in different way..
I will set up a nex origdc and then we point users browser to akamai staging
then we will make sure this is working from akamai
but itis o.. i realied because iwas doing smoke test.. someting in th fireall not ok.
IN PROGRESS | 5. FUSE vendorlink issue (AR working fine, UY and CH are broken)
DONE | 6. IMB - test data, check for acounts, not setup in usual way
DONE | 7. testing accounts for ZM, Reps, SL - make sure we have proper number of accouts
DONE | 8. SSO in IMB- fixed - chat to be checked once again (Jey to check with Guido)
DONE | 9. SMS sending for UY, AR, CH - result of EOC in EU markets, PG had some problems
DONE | 10. MAS we don't know how to test it under maint page - NEED TO BE ADDRESSED stream by stream - we need to modify hostfile, Milos knows all details
11. MAO/CHOICE This DB was very likely shut down by mistake and it caused issue to CPE as KPI service was not available!